## Actionable Tickets
Epic ID | Epic Name | Category | Ticket Key | Title | Issue Type | Priority | Story Points | Sprint | User Story | Acceptance Criteria
EPIC-SCALE | Infrastructure & Data Scaling | Infrastructure | TICKET-SCALE-101 | Configure PgBouncer & SQLAlchemy Async Pool | Technical Task | High | 3 | Sprint 1 | As a System Architect, I want Postgres connection pooling so that queries execute in <15ms under high concurrent load. | PgBouncer sidecar configured; 500+ concurrent requests handled without connection starvation errors.
EPIC-SCALE | Infrastructure & Data Scaling | Infrastructure | TICKET-SCALE-102 | Implement Composite B-Tree & JSONB GIN Database Indexing | Technical Task | High | 2 | Sprint 1 | As a Database Admin, I want optimized indexing so that health record lookup latency drops by >70%. | Composite indexes on (account_id, created_at) and JSONB GIN index created; query latency <10ms.
EPIC-SCALE | Infrastructure & Data Scaling | Infrastructure | TICKET-SCALE-103 | Redis Read-Through Caching Layer for Catalog & Vitals | Technical Task | Medium | 3 | Sprint 2 | As a Backend Engineer, I want catalog and vitals cached in Redis so that response times remain under 5ms. | Redis cache TTL set to 15m; cache hit ratio >85%; catalog response time <5ms.
EPIC-SCALE | Infrastructure & Data Scaling | Infrastructure | TICKET-SCALE-104 | Celery & Redis Worker Cluster for Async AI Loops | Technical Task | High | 5 | Sprint 2 | As a System Developer, I want heavy AI calculations offloaded to background Celery workers so API endpoints stay responsive. | Celery cluster processes adherence loops and blood SOS broadcasts asynchronously with zero main thread blocking.
EPIC-MONITOR | APM, Monitoring & Observability | Observability | TICKET-MON-201 | Integrate OpenTelemetry Tracing & Prometheus Metrics | Technical Task | High | 5 | Sprint 1 | As a DevOps Engineer, I want distributed tracing and Prometheus metrics so that system bottlenecks are detected instantly. | FastAPI instrumented with OpenTelemetry SDK; `/metrics` endpoint exports request rate, error rate, and duration histogram.
EPIC-MONITOR | APM, Monitoring & Observability | Observability | TICKET-MON-202 | Deploy Grafana Dashboards & Sentry Exception Alerts | Technical Task | Medium | 3 | Sprint 1 | As an Ops Lead, I want Grafana dashboards and Sentry real-time error alerts so that downtime causes are diagnosed in <5 minutes. | Grafana dashboards show API latency p95/p99, DB connection stats, and Sentry triggers Slack alerts on HTTP 5xx spikes.
EPIC-QA-TEST | Comprehensive Testing & Quality Assurance | Quality Assurance | TICKET-QA-301 | Vitest & React Testing Library Frontend Unit Test Suite | QA Task | High | 5 | Sprint 1 | As a Frontend Engineer, I want Vitest component tests so that UI regressions are caught before pull requests are merged. | 100+ component unit tests created for Voice Rx Modal, Catalog Storefront, and Vitals Scanner; code coverage >85%.
EPIC-QA-TEST | Comprehensive Testing & Quality Assurance | Quality Assurance | TICKET-QA-302 | Expand Pytest Backend Unit & Mocked Integration Suite | QA Task | High | 3 | Sprint 1 | As a Backend QA Engineer, I want mocked API integration tests for external providers (Tata 1mg, Twilio, ABDM) so CI builds run fast and reliably. | 80+ Pytest unit tests passing; all external HTTP calls mocked with pytest-mock; 100% deterministic test runs.
EPIC-QA-TEST | Comprehensive Testing & Quality Assurance | Quality Assurance | TICKET-QA-303 | Automated E2E Playwright Browser Test Suite | QA Task | High | 5 | Sprint 4 | As a Product Owner, I want automated E2E user flow tests so that login, checkout, and AI voice dictation work end-to-end. | Headless Playwright test suite covers 5 key user journeys with screenshot artifacts on failure.
EPIC-DEV-CORE | Core Healthcare & Tata 1mg Integration | Product Feature | TICKET-DEV-401 | Real-Time Tata 1mg Inventory & Catalog Sync | Feature | High | 5 | Sprint 1 | As a Student, I want live medicine prices and stock levels so that I can buy prescribed drugs at discounted rates. | Catalog API synchronizes stock availability, pricing in paise, and active chemical ingredients.
EPIC-DEV-CORE | Core Healthcare & Tata 1mg Integration | Product Feature | TICKET-DEV-402 | 1-Click Order Checkout & Delivery Address Gateway | Feature | High | 5 | Sprint 3 | As a Student, I want 1-click cart checkout with campus address delivery so that my prescriptions are delivered directly to my hostel. | Orders created with line items, Care Points discount applied, status tracked from PENDING to DELIVERED.
EPIC-BRANDING | Branding, UI System & Logo Assets | Design & UI | TICKET-BRAND-501 | Create Studentkare Vector Logo Suite & Favicon Assets | Design Task | Medium | 2 | Sprint 1 | As a Brand Designer, I want high-resolution SVG logos and favicons so that the platform presentation feels premium and consistent. | Dark/Light vector SVG logos, PNG icons (192x192, 512x512), and favicon bundle added to `public/` directory.
EPIC-BRANDING | Branding, UI System & Logo Assets | Design & UI | TICKET-BRAND-502 | Refactor UI Components to Impilo Pearl Design Tokens | Frontend Task | Medium | 3 | Sprint 2 | As a Frontend Developer, I want CSS design tokens for color, typography, and spacing so that UI design is maintainable. | All component hardcoded colors replaced with CSS variables (`--color-primary`, `--color-accent`, `--bg-card`).
EPIC-ANALYTICS | Analytics & User Behavioral Telemetry | Analytics | TICKET-ANA-601 | Integrate PostHog Product Analytics SDK & Conversion Funnels | Feature | High | 3 | Sprint 2 | As a Product Manager, I want user analytics event tracking so that conversion funnels and feature usage can be measured. | PostHog JS SDK tracking pageviews, voice prescription attempts, and lab package bookings with zero PII leakage.
EPIC-FIREBASE | Firebase Authentication & Push Notifications | Mobile & Cloud | TICKET-FIRE-701 | Firebase Cloud Messaging (FCM) Push Notification Engine | Feature | High | 5 | Sprint 2 | As a Student, I want real-time push notifications on my phone for medication reminders and order status updates. | FCM web/mobile push notification triggers sent for daily pill intake, lab slot arrival, and emergency blood alerts.
EPIC-FIREBASE | Firebase Authentication & Push Notifications | Mobile & Cloud | TICKET-FIRE-702 | Firestore Real-time Sync for Chat & Phlebotomist Tracking | Feature | Medium | 5 | Sprint 3 | As a Patient, I want live GPS location tracking of the dispatched phlebotomist on a map so I know when they will arrive. | Firestore realtime database updates phlebotomist latitude/longitude coordinates on the student map view.
EPIC-WORKFLOW-AUTO | Healthcare Flow Automation & Escalations | Workflow Engine | TICKET-FLOW-801 | Automated Post-Consultation Follow-Up Workflow Engine | Feature | High | 5 | Sprint 3 | As a Clinician, I want automated 48-hour follow-up messages sent to patients so that recovery is monitored automatically. | Automated follow-up state machine schedules check-in messages 48h after consultation completion.
EPIC-WORKFLOW-AUTO | Healthcare Flow Automation & Escalations | Workflow Engine | TICKET-FLOW-802 | Critical Vitals Abnormal Result Escalation Loop | Feature | High | 5 | Sprint 3 | As a Health Officer, I want high BP or low SpO2 vitals scans to automatically trigger urgent doctor triage alerts. | Vitals scan with SpO2 < 92% or Systolic > 160 triggers high-priority alert on Clinician Console.
EPIC-AGGREGATOR | Health Data Aggregator & ABDM FHIR Vault | Data Pipeline | TICKET-AGG-901 | Multi-Source Wearable & Lab Data Aggregator Pipeline | Feature | High | 8 | Sprint 3 | As a Student, I want data from Apple Health, Google Health Connect, and uploaded PDF lab reports compiled into one record. | Aggregator normalizes heart rate, steps, and lab biomarker values into unified JSON format.
EPIC-AGGREGATOR | Health Data Aggregator & ABDM FHIR Vault | Data Pipeline | TICKET-AGG-902 | ABDM FHIR R4 Bundle Compiler & Health Vault Linker | Feature | High | 8 | Sprint 3 | As a Compliance Officer, I want records formatted as ABDM FHIR R4 bundles so that health history is portable nationwide. | Generates valid FHIR DiagnosticReport, Prescription, and Condition bundles linked to ABHA ID.
EPIC-DEV-AI | Autonomous AI Agents & Voice Acoustics | AI / ML | TICKET-AI-1001 | Multi-Language Medical Speech-to-Text Scribe (EN / TE / HI) | Feature | High | 5 | Sprint 2 | As a Doctor, I want to dictate prescriptions orally in English, Telugu, or Hindi so that prescriptions are automatically transcribed. | Accurately transcribes spoken brand names (Dolo, Pantocid) and outputs structured dosage items.
EPIC-DEV-AI | Autonomous AI Agents & Voice Acoustics | AI / ML | TICKET-AI-1002 | Voice Acoustics Respiratory Biomarker Analyzer (F0, Jitter, Shimmer) | Feature | Medium | 5 | Sprint 2 | As a Clinician, I want voice acoustic markers analyzed from vocal recording so that respiratory wheezing is detected early. | Calculates F0 pitch frequency, vocal jitter %, shimmer %, and flags acoustic cough wheeze patterns.
EPIC-DATA-ANALYSIS | Data Analysis & Population Health Analytics | Data Science | TICKET-DATA-1101 | Campus Population Health & Outbreak Trend Analytics | Feature | High | 5 | Sprint 4 | As a Campus Medical Director, I want aggregated health trends so that potential flu or dengue outbreaks are spotted early. | Dashboard visualizes symptom frequency by hostel block, fever spikes, and lab result trends.
EPIC-DATA-ANALYSIS | Data Analysis & Population Health Analytics | Data Science | TICKET-DATA-1102 | Predictive Health Risk Scoring Engine | Feature | Medium | 5 | Sprint 4 | As a Preventive Care Specialist, I want predictive health risk scores so that high-risk students receive targeted wellness interventions. | Algorithm combines vitals trends, posture scores, and adherence rate to output risk tier (Low, Moderate, Elevated).
EPIC-MOBILE-PWA | Offline-First PWA & Mobile Synchronization | Mobile App | TICKET-PWA-1201 | IndexedDB Offline Health Data Cache & Sync | Feature | High | 5 | Sprint 2 | As a Student, I want my health vault and emergency blood contact numbers stored offline so I can access them without internet. | IndexedDB stores active prescriptions, vitals, and emergency SOS contacts; works 100% offline.
EPIC-MOBILE-PWA | Offline-First PWA & Mobile Synchronization | Mobile App | TICKET-PWA-1202 | Service Worker Background Sync for Vitals Submission | Feature | Medium | 3 | Sprint 2 | As a Mobile User, I want offline vitals logs synced automatically when internet re-connects so that no data is lost. | Service Worker queues offline vitals POST requests and flushes queue upon network re-connection.
EPIC-WEBRTC-VIDEO | WebRTC HD Video Tele-Consultation Engine | Realtime Video | TICKET-RTC-1301 | WebRTC P2P Video Call Setup with TURN/STUN Cluster | Feature | High | 8 | Sprint 3 | As a Patient, I want high-definition video calls with campus doctors so I can receive remote consultations. | WebRTC P2P video stream initialized with coturn STUN/TURN fallback; latency < 150ms.
EPIC-WEBRTC-VIDEO | WebRTC HD Video Tele-Consultation Engine | Realtime Video | TICKET-RTC-1302 | Interactive Doctor-Patient Report Whiteboard | Feature | Medium | 5 | Sprint 3 | As a Doctor, I want to annotate X-rays and lab PDFs on an interactive call whiteboard so patients understand their diagnosis. | Realtime HTML5 canvas sync over WebSocket allows live drawing annotations on lab documents during video calls.
EPIC-CLAIMS-ENGINE | Claims Rule Engine & Insurance Pre-Auth | FinTech & Insurance | TICKET-CLM-1401 | Drools Rules Engine for Itemized Invoice Validation | Feature | High | 8 | Sprint 3 | As an Insurance Claim Evaluator, I want automated policy rule checks so that pre-authorization approval takes seconds. | Rules engine parses room rent, pharmacy items, non-medical deductibles, and flags policy mismatches automatically.
EPIC-CLM-1402 | Claims Rule Engine & Insurance Pre-Auth | FinTech & Insurance | TICKET-CLM-1402 | ABDM Health Claim Exchange (HCX) Gateway Link | Feature | High | 8 | Sprint 4 | As a Hospital Admin, I want claims dispatched to insurers via HCX API so cashless approvals are processed instantly. | Formats FHIR Claim and ClaimResponse resources according to NHA HCX specification.
EPIC-HA-DR | High Availability, Backup & Disaster Recovery | DevOps & Infrastructure | TICKET-HADR-1501 | PostgreSQL Primary-Replica Streaming Replication | Technical Task | High | 5 | Sprint 2 | As an Infrastructure Lead, I want database streaming replication so that read queries are offloaded and failover is instant. | Read replicas handle 100% of analytical read queries; automatic failover with Patroni in < 10s.
EPIC-HADR-1502 | High Availability, Backup & Disaster Recovery | DevOps & Infrastructure | TICKET-HADR-1502 | Automated WAL Archiving & Multi-Region DR Drill | Technical Task | High | 5 | Sprint 4 | As a Compliance Officer, I want continuous WAL backups to S3/GCS so recovery point objective (RPO) is < 1 minute. | pgBackRest configured for continuous WAL archiving; automated DR recovery test validates RPO < 1m and RTO < 5m.
EPIC-MULTI-TENANT | Multi-Tenant Campus Isolation & University SSO | Enterprise Architecture | TICKET-TNT-1601 | Tenant Data Isolation & Schema Partitioning Engine | Architectural Task | High | 8 | Sprint 2 | As an Enterprise Architect, I want strict tenant isolation per university campus so student health records never mix across institutions. | Row-level security (RLS) and schema-per-tenant isolation enforced in PostgreSQL.
EPIC-TNT-1602 | Multi-Tenant Campus Isolation & University SSO | Enterprise Architecture | TICKET-TNT-1602 | University SAML 2.0 & OAuth2 Single Sign-On (SSO) | Feature | High | 5 | Sprint 2 | As a Student, I want to log in using my official university email/Shibboleth credentials so I don't need a separate password. | SAML 2.0 / OpenID Connect integration supports Shibboleth, Google Workspace, and Azure AD SSO login.
EPIC-SPORTS-REHAB | Campus Gym, Ergonomics & Sports Rehabilitation | Wellness & Rehab | TICKET-SPRT-1701 | Realtime AI Ergonomics Posture Tracker Widget | Feature | Medium | 3 | Sprint 2 | As a Student studying long hours, I want webcam posture monitoring so I avoid neck and spinal strain. | MediaPipe Pose landmark detector tracks spinal alignment in browser; alerts student on slouching.
EPIC-SPRT-1702 | Campus Gym, Ergonomics & Sports Rehabilitation | Wellness & Rehab | TICKET-SPRT-1702 | Sports Injury Prevention & Physio Rehab Workout Builder | Feature | Medium | 5 | Sprint 3 | As a Student Athlete, I want physio-approved workout recovery plans so I recover quickly from sports injuries. | Interactive exercise library builder with 3D joint movement models and reps tracker.

## Epics Summary
Epic ID | Epic Name | Category | Total Tickets | Total Story Points | Target Sprints
EPIC-SCALE | Infrastructure & Data Scaling | Infrastructure | 4 | 13 | Sprint 1, Sprint 2
EPIC-MONITOR | APM, Monitoring & Observability | Observability | 2 | 8 | Sprint 1
EPIC-QA-TEST | Comprehensive Testing & Quality Assurance | Quality Assurance | 3 | 13 | Sprint 1, Sprint 4
EPIC-DEV-CORE | Core Healthcare & Tata 1mg Integration | Product Feature | 2 | 10 | Sprint 1, Sprint 3
EPIC-BRANDING | Branding, UI System & Logo Assets | Design & UI | 2 | 5 | Sprint 1, Sprint 2
EPIC-ANALYTICS | Analytics & User Behavioral Telemetry | Analytics | 1 | 3 | Sprint 2
EPIC-FIREBASE | Firebase Authentication & Push Notifications | Mobile & Cloud | 2 | 10 | Sprint 2, Sprint 3
EPIC-WORKFLOW-AUTO | Healthcare Flow Automation & Escalations | Workflow Engine | 2 | 10 | Sprint 3
EPIC-AGGREGATOR | Health Data Aggregator & ABDM FHIR Vault | Data Pipeline | 2 | 16 | Sprint 3
EPIC-DEV-AI | Autonomous AI Agents & Voice Acoustics | AI / ML | 2 | 10 | Sprint 2
EPIC-DATA-ANALYSIS | Data Analysis & Population Health Analytics | Data Science | 2 | 10 | Sprint 4
EPIC-MOBILE-PWA | Offline-First PWA & Mobile Synchronization | Mobile App | 2 | 8 | Sprint 2
EPIC-WEBRTC-VIDEO | WebRTC HD Video Tele-Consultation Engine | Realtime Video | 2 | 13 | Sprint 3
EPIC-CLAIMS-ENGINE | Claims Rule Engine & Insurance Pre-Auth | FinTech & Insurance | 1 | 8 | Sprint 3
EPIC-CLM-1402 | Claims Rule Engine & Insurance Pre-Auth | FinTech & Insurance | 1 | 8 | Sprint 4
EPIC-HA-DR | High Availability, Backup & Disaster Recovery | DevOps & Infrastructure | 1 | 5 | Sprint 2
EPIC-HADR-1502 | High Availability, Backup & Disaster Recovery | DevOps & Infrastructure | 1 | 5 | Sprint 4
EPIC-MULTI-TENANT | Multi-Tenant Campus Isolation & University SSO | Enterprise Architecture | 1 | 8 | Sprint 2
EPIC-TNT-1602 | Multi-Tenant Campus Isolation & University SSO | Enterprise Architecture | 1 | 5 | Sprint 2
EPIC-SPORTS-REHAB | Campus Gym, Ergonomics & Sports Rehabilitation | Wellness & Rehab | 1 | 3 | Sprint 2
EPIC-SPRT-1702 | Campus Gym, Ergonomics & Sports Rehabilitation | Wellness & Rehab | 1 | 5 | Sprint 3