## 100 Dev & QA Scaling Tickets
Ticket ID | Domain Category | Sub System | Priority | Status | Issue Title | Technical Specifications & Description | Assigned Engineering Team | Automation Automated Test Triaged | Logged Timestamp | Resolution & Deployment Notes
DEV-TCK-2001 | Development Scaling & Infrastructure | Database Connection Pool | CRITICAL | OPEN | Scale BigQuery / PostgreSQL connection pool for 50,000 concurrent student logins (#1) | Database connection pool saturated during morning 09:00 AM class attendance peak. Need to adjust MaxConnections to 500. [Target Environment: Production / Staging Kubernetes Cluster] | DevOps & Infrastructure Team | Yes (CI/CD Quality Gate Verified) | 2026-09-13 03:52:52 | Pending sprint execution / code review.
DEV-TCK-2002 | Development Scaling & Infrastructure | Redis Cache Layer | HIGH | RESOLVED | Implement Redis cluster caching for live wearable sensor telemetry endpoints (#2) | Direct DB queries for live heart rate and step counter telemetry causing query latency. Need Redis L2 caching with 60s TTL. [Target Environment: Production / Staging Kubernetes Cluster] | Backend Engineering | Yes (CI/CD Quality Gate Verified) | 2026-09-13 03:22:52 | Automated PR merged, passed Vitest regression test suite & deployed to staging.
DEV-TCK-2003 | Development Scaling & Infrastructure | Horizontal Pod Autoscaler | HIGH | RESOLVED | Configure Kubernetes HPA for API Gateway under 10k RPS load (#3) | Auto-scaling trigger threshold set too high (85% CPU). Lower CPU target to 65% for instant pod spin-up. [Target Environment: Production / Staging Kubernetes Cluster] | DevOps Team | Yes (CI/CD Quality Gate Verified) | 2026-09-13 02:52:52 | Automated PR merged, passed Vitest regression test suite & deployed to staging.
DEV-TCK-2004 | Development Scaling & Infrastructure | CDN Asset Optimization | MEDIUM | IN_PROGRESS | Static media and bundle asset distribution via Cloudflare / CloudFront CDN (#4) | Static JS bundles exceeding 2.5MB payload on slow 3G mobile devices. Implement Brotli compression & CDN edge caching. [Target Environment: Production / Staging Kubernetes Cluster] | Frontend Performance Team | Yes (CI/CD Quality Gate Verified) | 2026-09-13 02:22:52 | Pending sprint execution / code review.
DEV-TCK-2005 | Development Scaling & Infrastructure | WebSocket Heartbeat | HIGH | OPEN | Real-time vitals camera streaming WebSocket socket reconnection stability (#5) | WebSocket connections dropping after 5 minutes of idle posture coaching. Implement exponential backoff ping/pong heartbeat. [Target Environment: Production / Staging Kubernetes Cluster] | Realtime WebSockets Team | Yes (CI/CD Quality Gate Verified) | 2026-09-13 01:52:52 | Pending sprint execution / code review.
DEV-TCK-2006 | QA Backend & Test Automation | Playwright E2E Automation | HIGH | RESOLVED | Playwright End-to-End browser test suite failing on Signup Step 6 Plan Selection (#6) | Automated Playwright test `tests/e2e/signup_flow.spec.ts` failed due to missing plan selection modal selector `#plan-c-btn`. [Target Environment: Production / Staging Kubernetes Cluster] | QA Automation Team | Yes (CI/CD Quality Gate Verified) | 2026-09-13 01:22:52 | Automated PR merged, passed Vitest regression test suite & deployed to staging.
DEV-TCK-2007 | QA Backend & Test Automation | Vitest Coverage Gate | MEDIUM | IN_PROGRESS | Vitest unit test coverage dropped below mandatory 85% threshold (#7) | New health overview telemetry module added without unit test assertions. Need 100% coverage on `healthExperience.ts`. [Target Environment: Production / Staging Kubernetes Cluster] | QA Quality Engineers | Yes (CI/CD Quality Gate Verified) | 2026-09-13 00:52:52 | Pending sprint execution / code review.
DEV-TCK-2008 | QA Backend & Test Automation | API Contract Testing | HIGH | ESCALATED | OpenAPI schema validation mismatch on POST /api/v1/telemetry/vitals endpoint (#8) | Contract test flagged missing `sensorAccuracyIndex` field in JSON request payload. [Target Environment: Production / Staging Kubernetes Cluster] | Backend QA Team | Yes (CI/CD Quality Gate Verified) | 2026-09-13 00:22:52 | Pending sprint execution / code review.
DEV-TCK-2009 | QA Backend & Test Automation | Mock Service Worker (MSW) | LOW | OPEN | MSW mock server latency simulation for offline mode PWA testing (#9) | Mock service worker failing to intercept offline PWA sync requests in Vitest runner. [Target Environment: Production / Staging Kubernetes Cluster] | QA Tooling Team | Yes (CI/CD Quality Gate Verified) | 2026-09-12 23:52:52 | Pending sprint execution / code review.
DEV-TCK-2010 | QA Backend & Test Automation | Visual Regression Test | LOW | IN_PROGRESS | Percy / Chromatic visual regression diff detected on InterfaceBar theme header (#10) | Dark mode pill buttons shifted 2px out of alignment on 1440px viewport displays. [Target Environment: Production / Staging Kubernetes Cluster] | Frontend QA Team | Yes (CI/CD Quality Gate Verified) | 2026-09-12 23:22:52 | Pending sprint execution / code review.
DEV-TCK-2011 | AI Architecture & LLM Engineering | Crisis Gate Safety | CRITICAL | RESOLVED | Crisis Gate AI deterministic bypass latency under 10ms for URGENT_EMERGENCY prompts (#11) | Crisis detection gate must process self-harm / panic keywords strictly on-device in <10ms without hitting remote LLM. [Target Environment: Production / Staging Kubernetes Cluster] | AI Safety & Ethics Team | Yes (CI/CD Quality Gate Verified) | 2026-09-12 22:52:52 | Automated PR merged, passed Vitest regression test suite & deployed to staging.
DEV-TCK-2012 | AI Architecture & LLM Engineering | AI Voice Prescription | HIGH | RESOLVED | Optimize Speech-to-Text Whisper model latency for medical dosage parsing (#12) | Voice prescription recording parsing taking >3.2 seconds. Need streaming chunk parsing via WebSockets. [Target Environment: Production / Staging Kubernetes Cluster] | AI Speech Team | Yes (CI/CD Quality Gate Verified) | 2026-09-12 22:22:52 | Automated PR merged, passed Vitest regression test suite & deployed to staging.
DEV-TCK-2013 | AI Architecture & LLM Engineering | RAG Vector Store | HIGH | OPEN | Vector DB embedding index sync for 1,000+ medical guidelines & drug interactions (#13) | Pinecone / Qdrant vector index out of sync with new NABL lab test reference values. [Target Environment: Production / Staging Kubernetes Cluster] | AI Data Engineering | Yes (CI/CD Quality Gate Verified) | 2026-09-12 21:52:52 | Pending sprint execution / code review.
DEV-TCK-2014 | AI Architecture & LLM Engineering | Prompt Injection Defense | CRITICAL | RESOLVED | Harden AI Health Assistant system prompt against jailbreak injection attacks (#14) | Red team security scan identified prompt bypass attempt targeting system constitution rules. [Target Environment: Production / Staging Kubernetes Cluster] | AI Security Team | Yes (CI/CD Quality Gate Verified) | 2026-09-12 21:22:52 | Automated PR merged, passed Vitest regression test suite & deployed to staging.
DEV-TCK-2015 | AI Architecture & LLM Engineering | LLM Token Budget | MEDIUM | ESCALATED | Implement token capping and fallback model switching (Gemini Pro to Flash) (#15) | High token consumption on long multi-turn patient chats. Implement auto-summarization at 4,000 tokens. [Target Environment: Production / Staging Kubernetes Cluster] | AI Infra Team | Yes (CI/CD Quality Gate Verified) | 2026-09-12 20:52:52 | Pending sprint execution / code review.
DEV-TCK-2016 | Automation, CI/CD & SecOps | 4-Hr Scouting Agent Cron | HIGH | IN_PROGRESS | 4-Hour AI Scouting Agent background cron schedule execution monitoring (#16) | Background schedule task `task-524` verified running on `0 */4 * * *` cron schedule pulling campus telemetry. [Target Environment: Production / Staging Kubernetes Cluster] | Automation & Agent Ops | Yes (CI/CD Quality Gate Verified) | 2026-09-12 20:22:52 | Pending sprint execution / code review.
DEV-TCK-2017 | Automation, CI/CD & SecOps | GitHub Actions CI Gate | MEDIUM | OPEN | GitHub Actions CI pipeline execution time optimization (Reduce from 8m to 2m) (#17) | Cache node_modules and Vitest transform files to accelerate pull request quality gate checks. [Target Environment: Production / Staging Kubernetes Cluster] | DevOps & CI/CD Team | Yes (CI/CD Quality Gate Verified) | 2026-09-12 19:52:52 | Pending sprint execution / code review.
DEV-TCK-2018 | Automation, CI/CD & SecOps | Knip Dead Code Audit | LOW | RESOLVED | Automated Knip static analysis flagged 14 unused exports in legacy components (#18) | Run `knip --no-exit-code` and tree-shake unused mock data structures to reduce bundle size by 120KB. [Target Environment: Production / Staging Kubernetes Cluster] | Code Quality Team | Yes (CI/CD Quality Gate Verified) | 2026-09-12 19:22:52 | Automated PR merged, passed Vitest regression test suite & deployed to staging.
DEV-TCK-2019 | Automation, CI/CD & SecOps | Semgrep SAST Security | CRITICAL | IN_PROGRESS | Semgrep security rule scanner flagged potential XSS target in unescaped innerHTML (#19) | Static analysis identified unescaped user note rendering in legacy support widget. Replace with DOMPurify. [Target Environment: Production / Staging Kubernetes Cluster] | Application Security Team | Yes (CI/CD Quality Gate Verified) | 2026-09-12 18:52:52 | Pending sprint execution / code review.
DEV-TCK-2020 | Automation, CI/CD & SecOps | OWASP ZAP DAST Scan | HIGH | RESOLVED | OWASP ZAP dynamic application security test scan report remediation (#20) | Automated DAST scan flagged missing Strict-Transport-Security (HSTS) header on staging deployment. [Target Environment: Production / Staging Kubernetes Cluster] | SecOps Team | Yes (CI/CD Quality Gate Verified) | 2026-09-12 18:22:52 | Automated PR merged, passed Vitest regression test suite & deployed to staging.
DEV-TCK-2021 | Development Scaling & Infrastructure | Database Connection Pool | CRITICAL | OPEN | Scale BigQuery / PostgreSQL connection pool for 50,000 concurrent student logins (#21) | Database connection pool saturated during morning 09:00 AM class attendance peak. Need to adjust MaxConnections to 500. [Target Environment: Production / Staging Kubernetes Cluster] | DevOps & Infrastructure Team | Yes (CI/CD Quality Gate Verified) | 2026-09-12 17:52:52 | Pending sprint execution / code review.
DEV-TCK-2022 | Development Scaling & Infrastructure | Redis Cache Layer | HIGH | IN_PROGRESS | Implement Redis cluster caching for live wearable sensor telemetry endpoints (#22) | Direct DB queries for live heart rate and step counter telemetry causing query latency. Need Redis L2 caching with 60s TTL. [Target Environment: Production / Staging Kubernetes Cluster] | Backend Engineering | Yes (CI/CD Quality Gate Verified) | 2026-09-12 17:22:52 | Pending sprint execution / code review.
DEV-TCK-2023 | Development Scaling & Infrastructure | Horizontal Pod Autoscaler | HIGH | RESOLVED | Configure Kubernetes HPA for API Gateway under 10k RPS load (#23) | Auto-scaling trigger threshold set too high (85% CPU). Lower CPU target to 65% for instant pod spin-up. [Target Environment: Production / Staging Kubernetes Cluster] | DevOps Team | Yes (CI/CD Quality Gate Verified) | 2026-09-12 16:52:52 | Automated PR merged, passed Vitest regression test suite & deployed to staging.
DEV-TCK-2024 | Development Scaling & Infrastructure | CDN Asset Optimization | MEDIUM | RESOLVED | Static media and bundle asset distribution via Cloudflare / CloudFront CDN (#24) | Static JS bundles exceeding 2.5MB payload on slow 3G mobile devices. Implement Brotli compression & CDN edge caching. [Target Environment: Production / Staging Kubernetes Cluster] | Frontend Performance Team | Yes (CI/CD Quality Gate Verified) | 2026-09-12 16:22:52 | Automated PR merged, passed Vitest regression test suite & deployed to staging.
DEV-TCK-2025 | Development Scaling & Infrastructure | WebSocket Heartbeat | HIGH | OPEN | Real-time vitals camera streaming WebSocket socket reconnection stability (#25) | WebSocket connections dropping after 5 minutes of idle posture coaching. Implement exponential backoff ping/pong heartbeat. [Target Environment: Production / Staging Kubernetes Cluster] | Realtime WebSockets Team | Yes (CI/CD Quality Gate Verified) | 2026-09-12 15:52:52 | Pending sprint execution / code review.
DEV-TCK-2026 | QA Backend & Test Automation | Playwright E2E Automation | HIGH | RESOLVED | Playwright End-to-End browser test suite failing on Signup Step 6 Plan Selection (#26) | Automated Playwright test `tests/e2e/signup_flow.spec.ts` failed due to missing plan selection modal selector `#plan-c-btn`. [Target Environment: Production / Staging Kubernetes Cluster] | QA Automation Team | Yes (CI/CD Quality Gate Verified) | 2026-09-12 15:22:52 | Automated PR merged, passed Vitest regression test suite & deployed to staging.
DEV-TCK-2027 | QA Backend & Test Automation | Vitest Coverage Gate | MEDIUM | RESOLVED | Vitest unit test coverage dropped below mandatory 85% threshold (#27) | New health overview telemetry module added without unit test assertions. Need 100% coverage on `healthExperience.ts`. [Target Environment: Production / Staging Kubernetes Cluster] | QA Quality Engineers | Yes (CI/CD Quality Gate Verified) | 2026-09-12 14:52:52 | Automated PR merged, passed Vitest regression test suite & deployed to staging.
DEV-TCK-2028 | QA Backend & Test Automation | API Contract Testing | HIGH | IN_PROGRESS | OpenAPI schema validation mismatch on POST /api/v1/telemetry/vitals endpoint (#28) | Contract test flagged missing `sensorAccuracyIndex` field in JSON request payload. [Target Environment: Production / Staging Kubernetes Cluster] | Backend QA Team | Yes (CI/CD Quality Gate Verified) | 2026-09-12 14:22:52 | Pending sprint execution / code review.
DEV-TCK-2029 | QA Backend & Test Automation | Mock Service Worker (MSW) | LOW | OPEN | MSW mock server latency simulation for offline mode PWA testing (#29) | Mock service worker failing to intercept offline PWA sync requests in Vitest runner. [Target Environment: Production / Staging Kubernetes Cluster] | QA Tooling Team | Yes (CI/CD Quality Gate Verified) | 2026-09-12 13:52:52 | Pending sprint execution / code review.
DEV-TCK-2030 | QA Backend & Test Automation | Visual Regression Test | LOW | RESOLVED | Percy / Chromatic visual regression diff detected on InterfaceBar theme header (#30) | Dark mode pill buttons shifted 2px out of alignment on 1440px viewport displays. [Target Environment: Production / Staging Kubernetes Cluster] | Frontend QA Team | Yes (CI/CD Quality Gate Verified) | 2026-09-12 13:22:52 | Automated PR merged, passed Vitest regression test suite & deployed to staging.
DEV-TCK-2031 | AI Architecture & LLM Engineering | Crisis Gate Safety | CRITICAL | IN_PROGRESS | Crisis Gate AI deterministic bypass latency under 10ms for URGENT_EMERGENCY prompts (#31) | Crisis detection gate must process self-harm / panic keywords strictly on-device in <10ms without hitting remote LLM. [Target Environment: Production / Staging Kubernetes Cluster] | AI Safety & Ethics Team | Yes (CI/CD Quality Gate Verified) | 2026-09-12 12:52:52 | Pending sprint execution / code review.
DEV-TCK-2032 | AI Architecture & LLM Engineering | AI Voice Prescription | HIGH | RESOLVED | Optimize Speech-to-Text Whisper model latency for medical dosage parsing (#32) | Voice prescription recording parsing taking >3.2 seconds. Need streaming chunk parsing via WebSockets. [Target Environment: Production / Staging Kubernetes Cluster] | AI Speech Team | Yes (CI/CD Quality Gate Verified) | 2026-09-12 12:22:52 | Automated PR merged, passed Vitest regression test suite & deployed to staging.
DEV-TCK-2033 | AI Architecture & LLM Engineering | RAG Vector Store | HIGH | OPEN | Vector DB embedding index sync for 1,000+ medical guidelines & drug interactions (#33) | Pinecone / Qdrant vector index out of sync with new NABL lab test reference values. [Target Environment: Production / Staging Kubernetes Cluster] | AI Data Engineering | Yes (CI/CD Quality Gate Verified) | 2026-09-12 11:52:52 | Pending sprint execution / code review.
DEV-TCK-2034 | AI Architecture & LLM Engineering | Prompt Injection Defense | CRITICAL | IN_PROGRESS | Harden AI Health Assistant system prompt against jailbreak injection attacks (#34) | Red team security scan identified prompt bypass attempt targeting system constitution rules. [Target Environment: Production / Staging Kubernetes Cluster] | AI Security Team | Yes (CI/CD Quality Gate Verified) | 2026-09-12 11:22:52 | Pending sprint execution / code review.
DEV-TCK-2035 | AI Architecture & LLM Engineering | LLM Token Budget | MEDIUM | RESOLVED | Implement token capping and fallback model switching (Gemini Pro to Flash) (#35) | High token consumption on long multi-turn patient chats. Implement auto-summarization at 4,000 tokens. [Target Environment: Production / Staging Kubernetes Cluster] | AI Infra Team | Yes (CI/CD Quality Gate Verified) | 2026-09-12 10:52:52 | Automated PR merged, passed Vitest regression test suite & deployed to staging.
DEV-TCK-2036 | Automation, CI/CD & SecOps | 4-Hr Scouting Agent Cron | HIGH | ESCALATED | 4-Hour AI Scouting Agent background cron schedule execution monitoring (#36) | Background schedule task `task-524` verified running on `0 */4 * * *` cron schedule pulling campus telemetry. [Target Environment: Production / Staging Kubernetes Cluster] | Automation & Agent Ops | Yes (CI/CD Quality Gate Verified) | 2026-09-12 10:22:52 | Pending sprint execution / code review.
DEV-TCK-2037 | Automation, CI/CD & SecOps | GitHub Actions CI Gate | MEDIUM | OPEN | GitHub Actions CI pipeline execution time optimization (Reduce from 8m to 2m) (#37) | Cache node_modules and Vitest transform files to accelerate pull request quality gate checks. [Target Environment: Production / Staging Kubernetes Cluster] | DevOps & CI/CD Team | Yes (CI/CD Quality Gate Verified) | 2026-09-12 09:52:52 | Pending sprint execution / code review.
DEV-TCK-2038 | Automation, CI/CD & SecOps | Knip Dead Code Audit | LOW | RESOLVED | Automated Knip static analysis flagged 14 unused exports in legacy components (#38) | Run `knip --no-exit-code` and tree-shake unused mock data structures to reduce bundle size by 120KB. [Target Environment: Production / Staging Kubernetes Cluster] | Code Quality Team | Yes (CI/CD Quality Gate Verified) | 2026-09-12 09:22:52 | Automated PR merged, passed Vitest regression test suite & deployed to staging.
DEV-TCK-2039 | Automation, CI/CD & SecOps | Semgrep SAST Security | CRITICAL | RESOLVED | Semgrep security rule scanner flagged potential XSS target in unescaped innerHTML (#39) | Static analysis identified unescaped user note rendering in legacy support widget. Replace with DOMPurify. [Target Environment: Production / Staging Kubernetes Cluster] | Application Security Team | Yes (CI/CD Quality Gate Verified) | 2026-09-12 08:52:52 | Automated PR merged, passed Vitest regression test suite & deployed to staging.
DEV-TCK-2040 | Automation, CI/CD & SecOps | OWASP ZAP DAST Scan | HIGH | IN_PROGRESS | OWASP ZAP dynamic application security test scan report remediation (#40) | Automated DAST scan flagged missing Strict-Transport-Security (HSTS) header on staging deployment. [Target Environment: Production / Staging Kubernetes Cluster] | SecOps Team | Yes (CI/CD Quality Gate Verified) | 2026-09-12 08:22:52 | Pending sprint execution / code review.
DEV-TCK-2041 | Development Scaling & Infrastructure | Database Connection Pool | CRITICAL | OPEN | Scale BigQuery / PostgreSQL connection pool for 50,000 concurrent student logins (#41) | Database connection pool saturated during morning 09:00 AM class attendance peak. Need to adjust MaxConnections to 500. [Target Environment: Production / Staging Kubernetes Cluster] | DevOps & Infrastructure Team | Yes (CI/CD Quality Gate Verified) | 2026-09-12 07:52:52 | Pending sprint execution / code review.
DEV-TCK-2042 | Development Scaling & Infrastructure | Redis Cache Layer | HIGH | RESOLVED | Implement Redis cluster caching for live wearable sensor telemetry endpoints (#42) | Direct DB queries for live heart rate and step counter telemetry causing query latency. Need Redis L2 caching with 60s TTL. [Target Environment: Production / Staging Kubernetes Cluster] | Backend Engineering | Yes (CI/CD Quality Gate Verified) | 2026-09-12 07:22:52 | Automated PR merged, passed Vitest regression test suite & deployed to staging.
DEV-TCK-2043 | Development Scaling & Infrastructure | Horizontal Pod Autoscaler | HIGH | IN_PROGRESS | Configure Kubernetes HPA for API Gateway under 10k RPS load (#43) | Auto-scaling trigger threshold set too high (85% CPU). Lower CPU target to 65% for instant pod spin-up. [Target Environment: Production / Staging Kubernetes Cluster] | DevOps Team | Yes (CI/CD Quality Gate Verified) | 2026-09-12 06:52:52 | Pending sprint execution / code review.
DEV-TCK-2044 | Development Scaling & Infrastructure | CDN Asset Optimization | MEDIUM | RESOLVED | Static media and bundle asset distribution via Cloudflare / CloudFront CDN (#44) | Static JS bundles exceeding 2.5MB payload on slow 3G mobile devices. Implement Brotli compression & CDN edge caching. [Target Environment: Production / Staging Kubernetes Cluster] | Frontend Performance Team | Yes (CI/CD Quality Gate Verified) | 2026-09-12 06:22:52 | Automated PR merged, passed Vitest regression test suite & deployed to staging.
DEV-TCK-2045 | Development Scaling & Infrastructure | WebSocket Heartbeat | HIGH | OPEN | Real-time vitals camera streaming WebSocket socket reconnection stability (#45) | WebSocket connections dropping after 5 minutes of idle posture coaching. Implement exponential backoff ping/pong heartbeat. [Target Environment: Production / Staging Kubernetes Cluster] | Realtime WebSockets Team | Yes (CI/CD Quality Gate Verified) | 2026-09-12 05:52:52 | Pending sprint execution / code review.
DEV-TCK-2046 | QA Backend & Test Automation | Playwright E2E Automation | HIGH | IN_PROGRESS | Playwright End-to-End browser test suite failing on Signup Step 6 Plan Selection (#46) | Automated Playwright test `tests/e2e/signup_flow.spec.ts` failed due to missing plan selection modal selector `#plan-c-btn`. [Target Environment: Production / Staging Kubernetes Cluster] | QA Automation Team | Yes (CI/CD Quality Gate Verified) | 2026-09-12 05:22:52 | Pending sprint execution / code review.
DEV-TCK-2047 | QA Backend & Test Automation | Vitest Coverage Gate | MEDIUM | RESOLVED | Vitest unit test coverage dropped below mandatory 85% threshold (#47) | New health overview telemetry module added without unit test assertions. Need 100% coverage on `healthExperience.ts`. [Target Environment: Production / Staging Kubernetes Cluster] | QA Quality Engineers | Yes (CI/CD Quality Gate Verified) | 2026-09-12 04:52:52 | Automated PR merged, passed Vitest regression test suite & deployed to staging.
DEV-TCK-2048 | QA Backend & Test Automation | API Contract Testing | HIGH | RESOLVED | OpenAPI schema validation mismatch on POST /api/v1/telemetry/vitals endpoint (#48) | Contract test flagged missing `sensorAccuracyIndex` field in JSON request payload. [Target Environment: Production / Staging Kubernetes Cluster] | Backend QA Team | Yes (CI/CD Quality Gate Verified) | 2026-09-12 04:22:52 | Automated PR merged, passed Vitest regression test suite & deployed to staging.
DEV-TCK-2049 | QA Backend & Test Automation | Mock Service Worker (MSW) | LOW | OPEN | MSW mock server latency simulation for offline mode PWA testing (#49) | Mock service worker failing to intercept offline PWA sync requests in Vitest runner. [Target Environment: Production / Staging Kubernetes Cluster] | QA Tooling Team | Yes (CI/CD Quality Gate Verified) | 2026-09-12 03:52:52 | Pending sprint execution / code review.
DEV-TCK-2050 | QA Backend & Test Automation | Visual Regression Test | LOW | ESCALATED | Percy / Chromatic visual regression diff detected on InterfaceBar theme header (#50) | Dark mode pill buttons shifted 2px out of alignment on 1440px viewport displays. [Target Environment: Production / Staging Kubernetes Cluster] | Frontend QA Team | Yes (CI/CD Quality Gate Verified) | 2026-09-12 03:22:52 | Pending sprint execution / code review.
DEV-TCK-2051 | AI Architecture & LLM Engineering | Crisis Gate Safety | CRITICAL | RESOLVED | Crisis Gate AI deterministic bypass latency under 10ms for URGENT_EMERGENCY prompts (#51) | Crisis detection gate must process self-harm / panic keywords strictly on-device in <10ms without hitting remote LLM. [Target Environment: Production / Staging Kubernetes Cluster] | AI Safety & Ethics Team | Yes (CI/CD Quality Gate Verified) | 2026-09-12 02:52:52 | Automated PR merged, passed Vitest regression test suite & deployed to staging.
DEV-TCK-2052 | AI Architecture & LLM Engineering | AI Voice Prescription | HIGH | IN_PROGRESS | Optimize Speech-to-Text Whisper model latency for medical dosage parsing (#52) | Voice prescription recording parsing taking >3.2 seconds. Need streaming chunk parsing via WebSockets. [Target Environment: Production / Staging Kubernetes Cluster] | AI Speech Team | Yes (CI/CD Quality Gate Verified) | 2026-09-12 02:22:52 | Pending sprint execution / code review.
DEV-TCK-2053 | AI Architecture & LLM Engineering | RAG Vector Store | HIGH | OPEN | Vector DB embedding index sync for 1,000+ medical guidelines & drug interactions (#53) | Pinecone / Qdrant vector index out of sync with new NABL lab test reference values. [Target Environment: Production / Staging Kubernetes Cluster] | AI Data Engineering | Yes (CI/CD Quality Gate Verified) | 2026-09-12 01:52:52 | Pending sprint execution / code review.
DEV-TCK-2054 | AI Architecture & LLM Engineering | Prompt Injection Defense | CRITICAL | RESOLVED | Harden AI Health Assistant system prompt against jailbreak injection attacks (#54) | Red team security scan identified prompt bypass attempt targeting system constitution rules. [Target Environment: Production / Staging Kubernetes Cluster] | AI Security Team | Yes (CI/CD Quality Gate Verified) | 2026-09-12 01:22:52 | Automated PR merged, passed Vitest regression test suite & deployed to staging.
DEV-TCK-2055 | AI Architecture & LLM Engineering | LLM Token Budget | MEDIUM | IN_PROGRESS | Implement token capping and fallback model switching (Gemini Pro to Flash) (#55) | High token consumption on long multi-turn patient chats. Implement auto-summarization at 4,000 tokens. [Target Environment: Production / Staging Kubernetes Cluster] | AI Infra Team | Yes (CI/CD Quality Gate Verified) | 2026-09-12 00:52:52 | Pending sprint execution / code review.
DEV-TCK-2056 | Automation, CI/CD & SecOps | 4-Hr Scouting Agent Cron | HIGH | RESOLVED | 4-Hour AI Scouting Agent background cron schedule execution monitoring (#56) | Background schedule task `task-524` verified running on `0 */4 * * *` cron schedule pulling campus telemetry. [Target Environment: Production / Staging Kubernetes Cluster] | Automation & Agent Ops | Yes (CI/CD Quality Gate Verified) | 2026-09-12 00:22:52 | Automated PR merged, passed Vitest regression test suite & deployed to staging.
DEV-TCK-2057 | Automation, CI/CD & SecOps | GitHub Actions CI Gate | MEDIUM | OPEN | GitHub Actions CI pipeline execution time optimization (Reduce from 8m to 2m) (#57) | Cache node_modules and Vitest transform files to accelerate pull request quality gate checks. [Target Environment: Production / Staging Kubernetes Cluster] | DevOps & CI/CD Team | Yes (CI/CD Quality Gate Verified) | 2026-09-11 23:52:52 | Pending sprint execution / code review.
DEV-TCK-2058 | Automation, CI/CD & SecOps | Knip Dead Code Audit | LOW | IN_PROGRESS | Automated Knip static analysis flagged 14 unused exports in legacy components (#58) | Run `knip --no-exit-code` and tree-shake unused mock data structures to reduce bundle size by 120KB. [Target Environment: Production / Staging Kubernetes Cluster] | Code Quality Team | Yes (CI/CD Quality Gate Verified) | 2026-09-11 23:22:52 | Pending sprint execution / code review.
DEV-TCK-2059 | Automation, CI/CD & SecOps | Semgrep SAST Security | CRITICAL | RESOLVED | Semgrep security rule scanner flagged potential XSS target in unescaped innerHTML (#59) | Static analysis identified unescaped user note rendering in legacy support widget. Replace with DOMPurify. [Target Environment: Production / Staging Kubernetes Cluster] | Application Security Team | Yes (CI/CD Quality Gate Verified) | 2026-09-11 22:52:52 | Automated PR merged, passed Vitest regression test suite & deployed to staging.
DEV-TCK-2060 | Automation, CI/CD & SecOps | OWASP ZAP DAST Scan | HIGH | RESOLVED | OWASP ZAP dynamic application security test scan report remediation (#60) | Automated DAST scan flagged missing Strict-Transport-Security (HSTS) header on staging deployment. [Target Environment: Production / Staging Kubernetes Cluster] | SecOps Team | Yes (CI/CD Quality Gate Verified) | 2026-09-11 22:22:52 | Automated PR merged, passed Vitest regression test suite & deployed to staging.
DEV-TCK-2061 | Development Scaling & Infrastructure | Database Connection Pool | CRITICAL | OPEN | Scale BigQuery / PostgreSQL connection pool for 50,000 concurrent student logins (#61) | Database connection pool saturated during morning 09:00 AM class attendance peak. Need to adjust MaxConnections to 500. [Target Environment: Production / Staging Kubernetes Cluster] | DevOps & Infrastructure Team | Yes (CI/CD Quality Gate Verified) | 2026-09-11 21:52:52 | Pending sprint execution / code review.
DEV-TCK-2062 | Development Scaling & Infrastructure | Redis Cache Layer | HIGH | RESOLVED | Implement Redis cluster caching for live wearable sensor telemetry endpoints (#62) | Direct DB queries for live heart rate and step counter telemetry causing query latency. Need Redis L2 caching with 60s TTL. [Target Environment: Production / Staging Kubernetes Cluster] | Backend Engineering | Yes (CI/CD Quality Gate Verified) | 2026-09-11 21:22:52 | Automated PR merged, passed Vitest regression test suite & deployed to staging.
DEV-TCK-2063 | Development Scaling & Infrastructure | Horizontal Pod Autoscaler | HIGH | RESOLVED | Configure Kubernetes HPA for API Gateway under 10k RPS load (#63) | Auto-scaling trigger threshold set too high (85% CPU). Lower CPU target to 65% for instant pod spin-up. [Target Environment: Production / Staging Kubernetes Cluster] | DevOps Team | Yes (CI/CD Quality Gate Verified) | 2026-09-11 20:52:52 | Automated PR merged, passed Vitest regression test suite & deployed to staging.
DEV-TCK-2064 | Development Scaling & Infrastructure | CDN Asset Optimization | MEDIUM | IN_PROGRESS | Static media and bundle asset distribution via Cloudflare / CloudFront CDN (#64) | Static JS bundles exceeding 2.5MB payload on slow 3G mobile devices. Implement Brotli compression & CDN edge caching. [Target Environment: Production / Staging Kubernetes Cluster] | Frontend Performance Team | Yes (CI/CD Quality Gate Verified) | 2026-09-11 20:22:52 | Pending sprint execution / code review.
DEV-TCK-2065 | Development Scaling & Infrastructure | WebSocket Heartbeat | HIGH | OPEN | Real-time vitals camera streaming WebSocket socket reconnection stability (#65) | WebSocket connections dropping after 5 minutes of idle posture coaching. Implement exponential backoff ping/pong heartbeat. [Target Environment: Production / Staging Kubernetes Cluster] | Realtime WebSockets Team | Yes (CI/CD Quality Gate Verified) | 2026-09-11 19:52:52 | Pending sprint execution / code review.
DEV-TCK-2066 | QA Backend & Test Automation | Playwright E2E Automation | HIGH | RESOLVED | Playwright End-to-End browser test suite failing on Signup Step 6 Plan Selection (#66) | Automated Playwright test `tests/e2e/signup_flow.spec.ts` failed due to missing plan selection modal selector `#plan-c-btn`. [Target Environment: Production / Staging Kubernetes Cluster] | QA Automation Team | Yes (CI/CD Quality Gate Verified) | 2026-09-11 19:22:52 | Automated PR merged, passed Vitest regression test suite & deployed to staging.
DEV-TCK-2067 | QA Backend & Test Automation | Vitest Coverage Gate | MEDIUM | IN_PROGRESS | Vitest unit test coverage dropped below mandatory 85% threshold (#67) | New health overview telemetry module added without unit test assertions. Need 100% coverage on `healthExperience.ts`. [Target Environment: Production / Staging Kubernetes Cluster] | QA Quality Engineers | Yes (CI/CD Quality Gate Verified) | 2026-09-11 18:52:52 | Pending sprint execution / code review.
DEV-TCK-2068 | QA Backend & Test Automation | API Contract Testing | HIGH | RESOLVED | OpenAPI schema validation mismatch on POST /api/v1/telemetry/vitals endpoint (#68) | Contract test flagged missing `sensorAccuracyIndex` field in JSON request payload. [Target Environment: Production / Staging Kubernetes Cluster] | Backend QA Team | Yes (CI/CD Quality Gate Verified) | 2026-09-11 18:22:52 | Automated PR merged, passed Vitest regression test suite & deployed to staging.
DEV-TCK-2069 | QA Backend & Test Automation | Mock Service Worker (MSW) | LOW | OPEN | MSW mock server latency simulation for offline mode PWA testing (#69) | Mock service worker failing to intercept offline PWA sync requests in Vitest runner. [Target Environment: Production / Staging Kubernetes Cluster] | QA Tooling Team | Yes (CI/CD Quality Gate Verified) | 2026-09-11 17:52:52 | Pending sprint execution / code review.
DEV-TCK-2070 | QA Backend & Test Automation | Visual Regression Test | LOW | IN_PROGRESS | Percy / Chromatic visual regression diff detected on InterfaceBar theme header (#70) | Dark mode pill buttons shifted 2px out of alignment on 1440px viewport displays. [Target Environment: Production / Staging Kubernetes Cluster] | Frontend QA Team | Yes (CI/CD Quality Gate Verified) | 2026-09-11 17:22:52 | Pending sprint execution / code review.
DEV-TCK-2071 | AI Architecture & LLM Engineering | Crisis Gate Safety | CRITICAL | ESCALATED | Crisis Gate AI deterministic bypass latency under 10ms for URGENT_EMERGENCY prompts (#71) | Crisis detection gate must process self-harm / panic keywords strictly on-device in <10ms without hitting remote LLM. [Target Environment: Production / Staging Kubernetes Cluster] | AI Safety & Ethics Team | Yes (CI/CD Quality Gate Verified) | 2026-09-11 16:52:52 | Pending sprint execution / code review.
DEV-TCK-2072 | AI Architecture & LLM Engineering | AI Voice Prescription | HIGH | RESOLVED | Optimize Speech-to-Text Whisper model latency for medical dosage parsing (#72) | Voice prescription recording parsing taking >3.2 seconds. Need streaming chunk parsing via WebSockets. [Target Environment: Production / Staging Kubernetes Cluster] | AI Speech Team | Yes (CI/CD Quality Gate Verified) | 2026-09-11 16:22:52 | Automated PR merged, passed Vitest regression test suite & deployed to staging.
DEV-TCK-2073 | AI Architecture & LLM Engineering | RAG Vector Store | HIGH | OPEN | Vector DB embedding index sync for 1,000+ medical guidelines & drug interactions (#73) | Pinecone / Qdrant vector index out of sync with new NABL lab test reference values. [Target Environment: Production / Staging Kubernetes Cluster] | AI Data Engineering | Yes (CI/CD Quality Gate Verified) | 2026-09-11 15:52:52 | Pending sprint execution / code review.
DEV-TCK-2074 | AI Architecture & LLM Engineering | Prompt Injection Defense | CRITICAL | RESOLVED | Harden AI Health Assistant system prompt against jailbreak injection attacks (#74) | Red team security scan identified prompt bypass attempt targeting system constitution rules. [Target Environment: Production / Staging Kubernetes Cluster] | AI Security Team | Yes (CI/CD Quality Gate Verified) | 2026-09-11 15:22:52 | Automated PR merged, passed Vitest regression test suite & deployed to staging.
DEV-TCK-2075 | AI Architecture & LLM Engineering | LLM Token Budget | MEDIUM | RESOLVED | Implement token capping and fallback model switching (Gemini Pro to Flash) (#75) | High token consumption on long multi-turn patient chats. Implement auto-summarization at 4,000 tokens. [Target Environment: Production / Staging Kubernetes Cluster] | AI Infra Team | Yes (CI/CD Quality Gate Verified) | 2026-09-11 14:52:52 | Automated PR merged, passed Vitest regression test suite & deployed to staging.
DEV-TCK-2076 | Automation, CI/CD & SecOps | 4-Hr Scouting Agent Cron | HIGH | IN_PROGRESS | 4-Hour AI Scouting Agent background cron schedule execution monitoring (#76) | Background schedule task `task-524` verified running on `0 */4 * * *` cron schedule pulling campus telemetry. [Target Environment: Production / Staging Kubernetes Cluster] | Automation & Agent Ops | Yes (CI/CD Quality Gate Verified) | 2026-09-11 14:22:52 | Pending sprint execution / code review.
DEV-TCK-2077 | Automation, CI/CD & SecOps | GitHub Actions CI Gate | MEDIUM | OPEN | GitHub Actions CI pipeline execution time optimization (Reduce from 8m to 2m) (#77) | Cache node_modules and Vitest transform files to accelerate pull request quality gate checks. [Target Environment: Production / Staging Kubernetes Cluster] | DevOps & CI/CD Team | Yes (CI/CD Quality Gate Verified) | 2026-09-11 13:52:52 | Pending sprint execution / code review.
DEV-TCK-2078 | Automation, CI/CD & SecOps | Knip Dead Code Audit | LOW | ESCALATED | Automated Knip static analysis flagged 14 unused exports in legacy components (#78) | Run `knip --no-exit-code` and tree-shake unused mock data structures to reduce bundle size by 120KB. [Target Environment: Production / Staging Kubernetes Cluster] | Code Quality Team | Yes (CI/CD Quality Gate Verified) | 2026-09-11 13:22:52 | Pending sprint execution / code review.
DEV-TCK-2079 | Automation, CI/CD & SecOps | Semgrep SAST Security | CRITICAL | IN_PROGRESS | Semgrep security rule scanner flagged potential XSS target in unescaped innerHTML (#79) | Static analysis identified unescaped user note rendering in legacy support widget. Replace with DOMPurify. [Target Environment: Production / Staging Kubernetes Cluster] | Application Security Team | Yes (CI/CD Quality Gate Verified) | 2026-09-11 12:52:52 | Pending sprint execution / code review.
DEV-TCK-2080 | Automation, CI/CD & SecOps | OWASP ZAP DAST Scan | HIGH | RESOLVED | OWASP ZAP dynamic application security test scan report remediation (#80) | Automated DAST scan flagged missing Strict-Transport-Security (HSTS) header on staging deployment. [Target Environment: Production / Staging Kubernetes Cluster] | SecOps Team | Yes (CI/CD Quality Gate Verified) | 2026-09-11 12:22:52 | Automated PR merged, passed Vitest regression test suite & deployed to staging.
DEV-TCK-2081 | Development Scaling & Infrastructure | Database Connection Pool | CRITICAL | OPEN | Scale BigQuery / PostgreSQL connection pool for 50,000 concurrent student logins (#81) | Database connection pool saturated during morning 09:00 AM class attendance peak. Need to adjust MaxConnections to 500. [Target Environment: Production / Staging Kubernetes Cluster] | DevOps & Infrastructure Team | Yes (CI/CD Quality Gate Verified) | 2026-09-11 11:52:52 | Pending sprint execution / code review.
DEV-TCK-2082 | Development Scaling & Infrastructure | Redis Cache Layer | HIGH | IN_PROGRESS | Implement Redis cluster caching for live wearable sensor telemetry endpoints (#82) | Direct DB queries for live heart rate and step counter telemetry causing query latency. Need Redis L2 caching with 60s TTL. [Target Environment: Production / Staging Kubernetes Cluster] | Backend Engineering | Yes (CI/CD Quality Gate Verified) | 2026-09-11 11:22:52 | Pending sprint execution / code review.
DEV-TCK-2083 | Development Scaling & Infrastructure | Horizontal Pod Autoscaler | HIGH | RESOLVED | Configure Kubernetes HPA for API Gateway under 10k RPS load (#83) | Auto-scaling trigger threshold set too high (85% CPU). Lower CPU target to 65% for instant pod spin-up. [Target Environment: Production / Staging Kubernetes Cluster] | DevOps Team | Yes (CI/CD Quality Gate Verified) | 2026-09-11 10:52:52 | Automated PR merged, passed Vitest regression test suite & deployed to staging.
DEV-TCK-2084 | Development Scaling & Infrastructure | CDN Asset Optimization | MEDIUM | RESOLVED | Static media and bundle asset distribution via Cloudflare / CloudFront CDN (#84) | Static JS bundles exceeding 2.5MB payload on slow 3G mobile devices. Implement Brotli compression & CDN edge caching. [Target Environment: Production / Staging Kubernetes Cluster] | Frontend Performance Team | Yes (CI/CD Quality Gate Verified) | 2026-09-11 10:22:52 | Automated PR merged, passed Vitest regression test suite & deployed to staging.
DEV-TCK-2085 | Development Scaling & Infrastructure | WebSocket Heartbeat | HIGH | OPEN | Real-time vitals camera streaming WebSocket socket reconnection stability (#85) | WebSocket connections dropping after 5 minutes of idle posture coaching. Implement exponential backoff ping/pong heartbeat. [Target Environment: Production / Staging Kubernetes Cluster] | Realtime WebSockets Team | Yes (CI/CD Quality Gate Verified) | 2026-09-11 09:52:52 | Pending sprint execution / code review.
DEV-TCK-2086 | QA Backend & Test Automation | Playwright E2E Automation | HIGH | RESOLVED | Playwright End-to-End browser test suite failing on Signup Step 6 Plan Selection (#86) | Automated Playwright test `tests/e2e/signup_flow.spec.ts` failed due to missing plan selection modal selector `#plan-c-btn`. [Target Environment: Production / Staging Kubernetes Cluster] | QA Automation Team | Yes (CI/CD Quality Gate Verified) | 2026-09-11 09:22:52 | Automated PR merged, passed Vitest regression test suite & deployed to staging.
DEV-TCK-2087 | QA Backend & Test Automation | Vitest Coverage Gate | MEDIUM | RESOLVED | Vitest unit test coverage dropped below mandatory 85% threshold (#87) | New health overview telemetry module added without unit test assertions. Need 100% coverage on `healthExperience.ts`. [Target Environment: Production / Staging Kubernetes Cluster] | QA Quality Engineers | Yes (CI/CD Quality Gate Verified) | 2026-09-11 08:52:52 | Automated PR merged, passed Vitest regression test suite & deployed to staging.
DEV-TCK-2088 | QA Backend & Test Automation | API Contract Testing | HIGH | IN_PROGRESS | OpenAPI schema validation mismatch on POST /api/v1/telemetry/vitals endpoint (#88) | Contract test flagged missing `sensorAccuracyIndex` field in JSON request payload. [Target Environment: Production / Staging Kubernetes Cluster] | Backend QA Team | Yes (CI/CD Quality Gate Verified) | 2026-09-11 08:22:52 | Pending sprint execution / code review.
DEV-TCK-2089 | QA Backend & Test Automation | Mock Service Worker (MSW) | LOW | OPEN | MSW mock server latency simulation for offline mode PWA testing (#89) | Mock service worker failing to intercept offline PWA sync requests in Vitest runner. [Target Environment: Production / Staging Kubernetes Cluster] | QA Tooling Team | Yes (CI/CD Quality Gate Verified) | 2026-09-11 07:52:52 | Pending sprint execution / code review.
DEV-TCK-2090 | QA Backend & Test Automation | Visual Regression Test | LOW | RESOLVED | Percy / Chromatic visual regression diff detected on InterfaceBar theme header (#90) | Dark mode pill buttons shifted 2px out of alignment on 1440px viewport displays. [Target Environment: Production / Staging Kubernetes Cluster] | Frontend QA Team | Yes (CI/CD Quality Gate Verified) | 2026-09-11 07:22:52 | Automated PR merged, passed Vitest regression test suite & deployed to staging.
DEV-TCK-2091 | AI Architecture & LLM Engineering | Crisis Gate Safety | CRITICAL | IN_PROGRESS | Crisis Gate AI deterministic bypass latency under 10ms for URGENT_EMERGENCY prompts (#91) | Crisis detection gate must process self-harm / panic keywords strictly on-device in <10ms without hitting remote LLM. [Target Environment: Production / Staging Kubernetes Cluster] | AI Safety & Ethics Team | Yes (CI/CD Quality Gate Verified) | 2026-09-11 06:52:52 | Pending sprint execution / code review.
DEV-TCK-2092 | AI Architecture & LLM Engineering | AI Voice Prescription | HIGH | ESCALATED | Optimize Speech-to-Text Whisper model latency for medical dosage parsing (#92) | Voice prescription recording parsing taking >3.2 seconds. Need streaming chunk parsing via WebSockets. [Target Environment: Production / Staging Kubernetes Cluster] | AI Speech Team | Yes (CI/CD Quality Gate Verified) | 2026-09-11 06:22:52 | Pending sprint execution / code review.
DEV-TCK-2093 | AI Architecture & LLM Engineering | RAG Vector Store | HIGH | OPEN | Vector DB embedding index sync for 1,000+ medical guidelines & drug interactions (#93) | Pinecone / Qdrant vector index out of sync with new NABL lab test reference values. [Target Environment: Production / Staging Kubernetes Cluster] | AI Data Engineering | Yes (CI/CD Quality Gate Verified) | 2026-09-11 05:52:52 | Pending sprint execution / code review.
DEV-TCK-2094 | AI Architecture & LLM Engineering | Prompt Injection Defense | CRITICAL | IN_PROGRESS | Harden AI Health Assistant system prompt against jailbreak injection attacks (#94) | Red team security scan identified prompt bypass attempt targeting system constitution rules. [Target Environment: Production / Staging Kubernetes Cluster] | AI Security Team | Yes (CI/CD Quality Gate Verified) | 2026-09-11 05:22:52 | Pending sprint execution / code review.
DEV-TCK-2095 | AI Architecture & LLM Engineering | LLM Token Budget | MEDIUM | RESOLVED | Implement token capping and fallback model switching (Gemini Pro to Flash) (#95) | High token consumption on long multi-turn patient chats. Implement auto-summarization at 4,000 tokens. [Target Environment: Production / Staging Kubernetes Cluster] | AI Infra Team | Yes (CI/CD Quality Gate Verified) | 2026-09-11 04:52:52 | Automated PR merged, passed Vitest regression test suite & deployed to staging.
DEV-TCK-2096 | Automation, CI/CD & SecOps | 4-Hr Scouting Agent Cron | HIGH | RESOLVED | 4-Hour AI Scouting Agent background cron schedule execution monitoring (#96) | Background schedule task `task-524` verified running on `0 */4 * * *` cron schedule pulling campus telemetry. [Target Environment: Production / Staging Kubernetes Cluster] | Automation & Agent Ops | Yes (CI/CD Quality Gate Verified) | 2026-09-11 04:22:52 | Automated PR merged, passed Vitest regression test suite & deployed to staging.
DEV-TCK-2097 | Automation, CI/CD & SecOps | GitHub Actions CI Gate | MEDIUM | OPEN | GitHub Actions CI pipeline execution time optimization (Reduce from 8m to 2m) (#97) | Cache node_modules and Vitest transform files to accelerate pull request quality gate checks. [Target Environment: Production / Staging Kubernetes Cluster] | DevOps & CI/CD Team | Yes (CI/CD Quality Gate Verified) | 2026-09-11 03:52:52 | Pending sprint execution / code review.
DEV-TCK-2098 | Automation, CI/CD & SecOps | Knip Dead Code Audit | LOW | RESOLVED | Automated Knip static analysis flagged 14 unused exports in legacy components (#98) | Run `knip --no-exit-code` and tree-shake unused mock data structures to reduce bundle size by 120KB. [Target Environment: Production / Staging Kubernetes Cluster] | Code Quality Team | Yes (CI/CD Quality Gate Verified) | 2026-09-11 03:22:52 | Automated PR merged, passed Vitest regression test suite & deployed to staging.
DEV-TCK-2099 | Automation, CI/CD & SecOps | Semgrep SAST Security | CRITICAL | ESCALATED | Semgrep security rule scanner flagged potential XSS target in unescaped innerHTML (#99) | Static analysis identified unescaped user note rendering in legacy support widget. Replace with DOMPurify. [Target Environment: Production / Staging Kubernetes Cluster] | Application Security Team | Yes (CI/CD Quality Gate Verified) | 2026-09-11 02:52:52 | Pending sprint execution / code review.
DEV-TCK-2100 | Automation, CI/CD & SecOps | OWASP ZAP DAST Scan | HIGH | IN_PROGRESS | OWASP ZAP dynamic application security test scan report remediation (#100) | Automated DAST scan flagged missing Strict-Transport-Security (HSTS) header on staging deployment. [Target Environment: Production / Staging Kubernetes Cluster] | SecOps Team | Yes (CI/CD Quality Gate Verified) | 2026-09-11 02:22:52 | Pending sprint execution / code review.