## 100 Task Assignments
Ticket Reference ID | Domain Category | Sub-System Component | Priority Level | Assigned Engineering Team | Recommended Assignee Role | Estimated Hours (Est) | Execution Status | Task Title for Assignment | Technical Requirements & Execution Details | Target Environment | QA Verification Criteria
TICKET-DEV-001 | 1. Development Scaling & Infrastructure | Database Connection Pool | CRITICAL | DevOps & Infra Team | Senior DevOps Engineer | 8 | UNASSIGNED | Scale BigQuery / PostgreSQL connection pool for 50,000 concurrent logins [Task #1] | Database connection pool saturated during morning peak. Configure max_connections=500 and deploy pgBouncer. | Production Kubernetes / Staging CI Cluster | Must pass Vitest regression suite, tsc type check, and zero lint warnings.
TICKET-DEV-002 | 1. Development Scaling & Infrastructure | Redis Cache Layer | HIGH | Backend Engineering | Backend Tech Lead | 12 | COMPLETED | Implement Redis cluster caching for live wearable sensor telemetry [Task #2] | Direct DB queries for live heart rate telemetry causing query latency. Need Redis L2 cache with 60s TTL. | Production Kubernetes / Staging CI Cluster | Must pass Vitest regression suite, tsc type check, and zero lint warnings.
TICKET-DEV-003 | 1. Development Scaling & Infrastructure | Kubernetes HPA | HIGH | DevOps & Infra Team | Cloud Infra Specialist | 6 | COMPLETED | Configure Kubernetes Horizontal Pod Autoscaler for API Gateway under 10k RPS [Task #3] | Auto-scaling trigger threshold set too high (85% CPU). Lower CPU target to 65% for instant pod spin-up. | Production Kubernetes / Staging CI Cluster | Must pass Vitest regression suite, tsc type check, and zero lint warnings.
TICKET-DEV-004 | 1. Development Scaling & Infrastructure | CDN Asset Cache | MEDIUM | Frontend Performance Team | Frontend Lead | 5 | IN_PROGRESS | Static media and bundle asset distribution via Cloudflare CDN [Task #4] | Static JS bundles exceeding 2.5MB payload on slow 3G mobile devices. Implement Brotli compression & CDN edge caching. | Production Kubernetes / Staging CI Cluster | Must pass Vitest regression suite, tsc type check, and zero lint warnings.
TICKET-DEV-005 | 1. Development Scaling & Infrastructure | WebSocket Heartbeat | HIGH | Realtime WebSockets Team | WebSockets Developer | 8 | UNASSIGNED | Real-time vitals camera streaming WebSocket socket reconnection stability [Task #5] | WebSocket connections dropping after 5 minutes of idle posture coaching. Implement exponential backoff ping/pong heartbeat. | Production Kubernetes / Staging CI Cluster | Must pass Vitest regression suite, tsc type check, and zero lint warnings.
TICKET-DEV-006 | 2. QA Backend & Test Automation | Playwright E2E | HIGH | QA Automation Team | QA Lead Engineer | 6 | COMPLETED | Playwright End-to-End browser test suite failing on Signup Step 6 Plan Selection [Task #6] | Automated Playwright test `tests/e2e/signup_flow.spec.ts` failed due to missing plan selection modal selector. | Production Kubernetes / Staging CI Cluster | Must pass Vitest regression suite, tsc type check, and zero lint warnings.
TICKET-DEV-007 | 2. QA Backend & Test Automation | Vitest Unit Coverage | MEDIUM | QA Automation Team | Senior QA Automation Engineer | 4 | IN_PROGRESS | Vitest unit test coverage dropped below mandatory 85% threshold [Task #7] | New health overview telemetry module added without unit test assertions. Need 100% coverage on `healthExperience.ts`. | Production Kubernetes / Staging CI Cluster | Must pass Vitest regression suite, tsc type check, and zero lint warnings.
TICKET-DEV-008 | 2. QA Backend & Test Automation | API Contract Test | HIGH | Backend Engineering | API Integration Developer | 6 | REVIEW_PENDING | OpenAPI schema validation mismatch on POST /api/v1/telemetry/vitals endpoint [Task #8] | Contract test flagged missing `sensorAccuracyIndex` field in JSON request payload. | Production Kubernetes / Staging CI Cluster | Must pass Vitest regression suite, tsc type check, and zero lint warnings.
TICKET-DEV-009 | 3. AI Architecture & LLM Engineering | Crisis Gate Safety | CRITICAL | AI Safety & Ethics Team | Principal AI Architect | 16 | UNASSIGNED | Crisis Gate AI deterministic bypass latency under 10ms for URGENT_EMERGENCY prompts [Task #9] | Crisis detection gate must process self-harm / panic keywords strictly on-device in <10ms without hitting remote LLM. | Production Kubernetes / Staging CI Cluster | Must pass Vitest regression suite, tsc type check, and zero lint warnings.
TICKET-DEV-010 | 3. AI Architecture & LLM Engineering | AI Voice Prescription | HIGH | AI Speech & NLP Team | NLP / Speech Engineer | 14 | IN_PROGRESS | Optimize Speech-to-Text Whisper model latency for medical dosage parsing [Task #10] | Voice prescription recording parsing taking >3.2 seconds. Need streaming chunk parsing via WebSockets. | Production Kubernetes / Staging CI Cluster | Must pass Vitest regression suite, tsc type check, and zero lint warnings.
TICKET-DEV-011 | 3. AI Architecture & LLM Engineering | RAG Vector Store | HIGH | AI Data Engineering | Data / Vector DB Engineer | 10 | COMPLETED | Vector DB embedding index sync for 1,000+ medical guidelines & drug interactions [Task #11] | Pinecone / Qdrant vector index out of sync with new NABL lab test reference values. | Production Kubernetes / Staging CI Cluster | Must pass Vitest regression suite, tsc type check, and zero lint warnings.
TICKET-DEV-012 | 3. AI Architecture & LLM Engineering | Prompt Injection Defense | CRITICAL | AI Security Team | AI Security Researcher | 12 | COMPLETED | Harden AI Health Assistant system prompt against jailbreak injection attacks [Task #12] | Red team security scan identified prompt bypass attempt targeting system constitution rules. | Production Kubernetes / Staging CI Cluster | Must pass Vitest regression suite, tsc type check, and zero lint warnings.
TICKET-DEV-013 | 4. SecOps, CI/CD & Automation | 4-Hr Scouting Agent | HIGH | SecOps & Automation Team | Automation Engineer | 6 | UNASSIGNED | 4-Hour AI Scouting Agent background cron schedule execution monitoring [Task #13] | Background schedule task `task-524` verified running on `0 */4 * * *` cron schedule pulling campus telemetry. | Production Kubernetes / Staging CI Cluster | Must pass Vitest regression suite, tsc type check, and zero lint warnings.
TICKET-DEV-014 | 4. SecOps, CI/CD & Automation | GitHub Actions CI | MEDIUM | DevOps Team | CI/CD Specialist | 4 | COMPLETED | GitHub Actions CI pipeline execution time optimization (Reduce from 8m to 2m) [Task #14] | Cache node_modules and Vitest transform files to accelerate pull request quality gate checks. | Production Kubernetes / Staging CI Cluster | Must pass Vitest regression suite, tsc type check, and zero lint warnings.
TICKET-DEV-015 | 4. SecOps, CI/CD & Automation | Knip Dead Code Audit | LOW | Code Quality Team | Software Engineer | 3 | REVIEW_PENDING | Automated Knip static analysis flagged 14 unused exports in legacy components [Task #15] | Run `knip --no-exit-code` and tree-shake unused mock data structures to reduce bundle size by 120KB. | Production Kubernetes / Staging CI Cluster | Must pass Vitest regression suite, tsc type check, and zero lint warnings.
TICKET-DEV-016 | 4. SecOps, CI/CD & Automation | Semgrep SAST Security | CRITICAL | SecOps Team | AppSec Engineer | 6 | IN_PROGRESS | Semgrep security rule scanner flagged potential XSS target in unescaped innerHTML [Task #16] | Static analysis identified unescaped user note rendering in legacy support widget. Replace with DOMPurify. | Production Kubernetes / Staging CI Cluster | Must pass Vitest regression suite, tsc type check, and zero lint warnings.
TICKET-DEV-017 | 1. Development Scaling & Infrastructure | Database Connection Pool | CRITICAL | DevOps & Infra Team | Senior DevOps Engineer | 8 | UNASSIGNED | Scale BigQuery / PostgreSQL connection pool for 50,000 concurrent logins [Task #17] | Database connection pool saturated during morning peak. Configure max_connections=500 and deploy pgBouncer. | Production Kubernetes / Staging CI Cluster | Must pass Vitest regression suite, tsc type check, and zero lint warnings.
TICKET-DEV-018 | 1. Development Scaling & Infrastructure | Redis Cache Layer | HIGH | Backend Engineering | Backend Tech Lead | 12 | COMPLETED | Implement Redis cluster caching for live wearable sensor telemetry [Task #18] | Direct DB queries for live heart rate telemetry causing query latency. Need Redis L2 cache with 60s TTL. | Production Kubernetes / Staging CI Cluster | Must pass Vitest regression suite, tsc type check, and zero lint warnings.
TICKET-DEV-019 | 1. Development Scaling & Infrastructure | Kubernetes HPA | HIGH | DevOps & Infra Team | Cloud Infra Specialist | 6 | IN_PROGRESS | Configure Kubernetes Horizontal Pod Autoscaler for API Gateway under 10k RPS [Task #19] | Auto-scaling trigger threshold set too high (85% CPU). Lower CPU target to 65% for instant pod spin-up. | Production Kubernetes / Staging CI Cluster | Must pass Vitest regression suite, tsc type check, and zero lint warnings.
TICKET-DEV-020 | 1. Development Scaling & Infrastructure | CDN Asset Cache | MEDIUM | Frontend Performance Team | Frontend Lead | 5 | COMPLETED | Static media and bundle asset distribution via Cloudflare CDN [Task #20] | Static JS bundles exceeding 2.5MB payload on slow 3G mobile devices. Implement Brotli compression & CDN edge caching. | Production Kubernetes / Staging CI Cluster | Must pass Vitest regression suite, tsc type check, and zero lint warnings.
TICKET-DEV-021 | 1. Development Scaling & Infrastructure | WebSocket Heartbeat | HIGH | Realtime WebSockets Team | WebSockets Developer | 8 | UNASSIGNED | Real-time vitals camera streaming WebSocket socket reconnection stability [Task #21] | WebSocket connections dropping after 5 minutes of idle posture coaching. Implement exponential backoff ping/pong heartbeat. | Production Kubernetes / Staging CI Cluster | Must pass Vitest regression suite, tsc type check, and zero lint warnings.
TICKET-DEV-022 | 2. QA Backend & Test Automation | Playwright E2E | HIGH | QA Automation Team | QA Lead Engineer | 6 | IN_PROGRESS | Playwright End-to-End browser test suite failing on Signup Step 6 Plan Selection [Task #22] | Automated Playwright test `tests/e2e/signup_flow.spec.ts` failed due to missing plan selection modal selector. | Production Kubernetes / Staging CI Cluster | Must pass Vitest regression suite, tsc type check, and zero lint warnings.
TICKET-DEV-023 | 2. QA Backend & Test Automation | Vitest Unit Coverage | MEDIUM | QA Automation Team | Senior QA Automation Engineer | 4 | COMPLETED | Vitest unit test coverage dropped below mandatory 85% threshold [Task #23] | New health overview telemetry module added without unit test assertions. Need 100% coverage on `healthExperience.ts`. | Production Kubernetes / Staging CI Cluster | Must pass Vitest regression suite, tsc type check, and zero lint warnings.
TICKET-DEV-024 | 2. QA Backend & Test Automation | API Contract Test | HIGH | Backend Engineering | API Integration Developer | 6 | COMPLETED | OpenAPI schema validation mismatch on POST /api/v1/telemetry/vitals endpoint [Task #24] | Contract test flagged missing `sensorAccuracyIndex` field in JSON request payload. | Production Kubernetes / Staging CI Cluster | Must pass Vitest regression suite, tsc type check, and zero lint warnings.
TICKET-DEV-025 | 3. AI Architecture & LLM Engineering | Crisis Gate Safety | CRITICAL | AI Safety & Ethics Team | Principal AI Architect | 16 | UNASSIGNED | Crisis Gate AI deterministic bypass latency under 10ms for URGENT_EMERGENCY prompts [Task #25] | Crisis detection gate must process self-harm / panic keywords strictly on-device in <10ms without hitting remote LLM. | Production Kubernetes / Staging CI Cluster | Must pass Vitest regression suite, tsc type check, and zero lint warnings.
TICKET-DEV-026 | 3. AI Architecture & LLM Engineering | AI Voice Prescription | HIGH | AI Speech & NLP Team | NLP / Speech Engineer | 14 | COMPLETED | Optimize Speech-to-Text Whisper model latency for medical dosage parsing [Task #26] | Voice prescription recording parsing taking >3.2 seconds. Need streaming chunk parsing via WebSockets. | Production Kubernetes / Staging CI Cluster | Must pass Vitest regression suite, tsc type check, and zero lint warnings.
TICKET-DEV-027 | 3. AI Architecture & LLM Engineering | RAG Vector Store | HIGH | AI Data Engineering | Data / Vector DB Engineer | 10 | COMPLETED | Vector DB embedding index sync for 1,000+ medical guidelines & drug interactions [Task #27] | Pinecone / Qdrant vector index out of sync with new NABL lab test reference values. | Production Kubernetes / Staging CI Cluster | Must pass Vitest regression suite, tsc type check, and zero lint warnings.
TICKET-DEV-028 | 3. AI Architecture & LLM Engineering | Prompt Injection Defense | CRITICAL | AI Security Team | AI Security Researcher | 12 | IN_PROGRESS | Harden AI Health Assistant system prompt against jailbreak injection attacks [Task #28] | Red team security scan identified prompt bypass attempt targeting system constitution rules. | Production Kubernetes / Staging CI Cluster | Must pass Vitest regression suite, tsc type check, and zero lint warnings.
TICKET-DEV-029 | 4. SecOps, CI/CD & Automation | 4-Hr Scouting Agent | HIGH | SecOps & Automation Team | Automation Engineer | 6 | UNASSIGNED | 4-Hour AI Scouting Agent background cron schedule execution monitoring [Task #29] | Background schedule task `task-524` verified running on `0 */4 * * *` cron schedule pulling campus telemetry. | Production Kubernetes / Staging CI Cluster | Must pass Vitest regression suite, tsc type check, and zero lint warnings.
TICKET-DEV-030 | 4. SecOps, CI/CD & Automation | GitHub Actions CI | MEDIUM | DevOps Team | CI/CD Specialist | 4 | COMPLETED | GitHub Actions CI pipeline execution time optimization (Reduce from 8m to 2m) [Task #30] | Cache node_modules and Vitest transform files to accelerate pull request quality gate checks. | Production Kubernetes / Staging CI Cluster | Must pass Vitest regression suite, tsc type check, and zero lint warnings.
TICKET-DEV-031 | 4. SecOps, CI/CD & Automation | Knip Dead Code Audit | LOW | Code Quality Team | Software Engineer | 3 | IN_PROGRESS | Automated Knip static analysis flagged 14 unused exports in legacy components [Task #31] | Run `knip --no-exit-code` and tree-shake unused mock data structures to reduce bundle size by 120KB. | Production Kubernetes / Staging CI Cluster | Must pass Vitest regression suite, tsc type check, and zero lint warnings.
TICKET-DEV-032 | 4. SecOps, CI/CD & Automation | Semgrep SAST Security | CRITICAL | SecOps Team | AppSec Engineer | 6 | COMPLETED | Semgrep security rule scanner flagged potential XSS target in unescaped innerHTML [Task #32] | Static analysis identified unescaped user note rendering in legacy support widget. Replace with DOMPurify. | Production Kubernetes / Staging CI Cluster | Must pass Vitest regression suite, tsc type check, and zero lint warnings.
TICKET-DEV-033 | 1. Development Scaling & Infrastructure | Database Connection Pool | CRITICAL | DevOps & Infra Team | Senior DevOps Engineer | 8 | UNASSIGNED | Scale BigQuery / PostgreSQL connection pool for 50,000 concurrent logins [Task #33] | Database connection pool saturated during morning peak. Configure max_connections=500 and deploy pgBouncer. | Production Kubernetes / Staging CI Cluster | Must pass Vitest regression suite, tsc type check, and zero lint warnings.
TICKET-DEV-034 | 1. Development Scaling & Infrastructure | Redis Cache Layer | HIGH | Backend Engineering | Backend Tech Lead | 12 | IN_PROGRESS | Implement Redis cluster caching for live wearable sensor telemetry [Task #34] | Direct DB queries for live heart rate telemetry causing query latency. Need Redis L2 cache with 60s TTL. | Production Kubernetes / Staging CI Cluster | Must pass Vitest regression suite, tsc type check, and zero lint warnings.
TICKET-DEV-035 | 1. Development Scaling & Infrastructure | Kubernetes HPA | HIGH | DevOps & Infra Team | Cloud Infra Specialist | 6 | COMPLETED | Configure Kubernetes Horizontal Pod Autoscaler for API Gateway under 10k RPS [Task #35] | Auto-scaling trigger threshold set too high (85% CPU). Lower CPU target to 65% for instant pod spin-up. | Production Kubernetes / Staging CI Cluster | Must pass Vitest regression suite, tsc type check, and zero lint warnings.
TICKET-DEV-036 | 1. Development Scaling & Infrastructure | CDN Asset Cache | MEDIUM | Frontend Performance Team | Frontend Lead | 5 | REVIEW_PENDING | Static media and bundle asset distribution via Cloudflare CDN [Task #36] | Static JS bundles exceeding 2.5MB payload on slow 3G mobile devices. Implement Brotli compression & CDN edge caching. | Production Kubernetes / Staging CI Cluster | Must pass Vitest regression suite, tsc type check, and zero lint warnings.
TICKET-DEV-037 | 1. Development Scaling & Infrastructure | WebSocket Heartbeat | HIGH | Realtime WebSockets Team | WebSockets Developer | 8 | UNASSIGNED | Real-time vitals camera streaming WebSocket socket reconnection stability [Task #37] | WebSocket connections dropping after 5 minutes of idle posture coaching. Implement exponential backoff ping/pong heartbeat. | Production Kubernetes / Staging CI Cluster | Must pass Vitest regression suite, tsc type check, and zero lint warnings.
TICKET-DEV-038 | 2. QA Backend & Test Automation | Playwright E2E | HIGH | QA Automation Team | QA Lead Engineer | 6 | COMPLETED | Playwright End-to-End browser test suite failing on Signup Step 6 Plan Selection [Task #38] | Automated Playwright test `tests/e2e/signup_flow.spec.ts` failed due to missing plan selection modal selector. | Production Kubernetes / Staging CI Cluster | Must pass Vitest regression suite, tsc type check, and zero lint warnings.
TICKET-DEV-039 | 2. QA Backend & Test Automation | Vitest Unit Coverage | MEDIUM | QA Automation Team | Senior QA Automation Engineer | 4 | COMPLETED | Vitest unit test coverage dropped below mandatory 85% threshold [Task #39] | New health overview telemetry module added without unit test assertions. Need 100% coverage on `healthExperience.ts`. | Production Kubernetes / Staging CI Cluster | Must pass Vitest regression suite, tsc type check, and zero lint warnings.
TICKET-DEV-040 | 2. QA Backend & Test Automation | API Contract Test | HIGH | Backend Engineering | API Integration Developer | 6 | IN_PROGRESS | OpenAPI schema validation mismatch on POST /api/v1/telemetry/vitals endpoint [Task #40] | Contract test flagged missing `sensorAccuracyIndex` field in JSON request payload. | Production Kubernetes / Staging CI Cluster | Must pass Vitest regression suite, tsc type check, and zero lint warnings.
TICKET-DEV-041 | 3. AI Architecture & LLM Engineering | Crisis Gate Safety | CRITICAL | AI Safety & Ethics Team | Principal AI Architect | 16 | UNASSIGNED | Crisis Gate AI deterministic bypass latency under 10ms for URGENT_EMERGENCY prompts [Task #41] | Crisis detection gate must process self-harm / panic keywords strictly on-device in <10ms without hitting remote LLM. | Production Kubernetes / Staging CI Cluster | Must pass Vitest regression suite, tsc type check, and zero lint warnings.
TICKET-DEV-042 | 3. AI Architecture & LLM Engineering | AI Voice Prescription | HIGH | AI Speech & NLP Team | NLP / Speech Engineer | 14 | COMPLETED | Optimize Speech-to-Text Whisper model latency for medical dosage parsing [Task #42] | Voice prescription recording parsing taking >3.2 seconds. Need streaming chunk parsing via WebSockets. | Production Kubernetes / Staging CI Cluster | Must pass Vitest regression suite, tsc type check, and zero lint warnings.
TICKET-DEV-043 | 3. AI Architecture & LLM Engineering | RAG Vector Store | HIGH | AI Data Engineering | Data / Vector DB Engineer | 10 | IN_PROGRESS | Vector DB embedding index sync for 1,000+ medical guidelines & drug interactions [Task #43] | Pinecone / Qdrant vector index out of sync with new NABL lab test reference values. | Production Kubernetes / Staging CI Cluster | Must pass Vitest regression suite, tsc type check, and zero lint warnings.
TICKET-DEV-044 | 3. AI Architecture & LLM Engineering | Prompt Injection Defense | CRITICAL | AI Security Team | AI Security Researcher | 12 | COMPLETED | Harden AI Health Assistant system prompt against jailbreak injection attacks [Task #44] | Red team security scan identified prompt bypass attempt targeting system constitution rules. | Production Kubernetes / Staging CI Cluster | Must pass Vitest regression suite, tsc type check, and zero lint warnings.
TICKET-DEV-045 | 4. SecOps, CI/CD & Automation | 4-Hr Scouting Agent | HIGH | SecOps & Automation Team | Automation Engineer | 6 | UNASSIGNED | 4-Hour AI Scouting Agent background cron schedule execution monitoring [Task #45] | Background schedule task `task-524` verified running on `0 */4 * * *` cron schedule pulling campus telemetry. | Production Kubernetes / Staging CI Cluster | Must pass Vitest regression suite, tsc type check, and zero lint warnings.
TICKET-DEV-046 | 4. SecOps, CI/CD & Automation | GitHub Actions CI | MEDIUM | DevOps Team | CI/CD Specialist | 4 | IN_PROGRESS | GitHub Actions CI pipeline execution time optimization (Reduce from 8m to 2m) [Task #46] | Cache node_modules and Vitest transform files to accelerate pull request quality gate checks. | Production Kubernetes / Staging CI Cluster | Must pass Vitest regression suite, tsc type check, and zero lint warnings.
TICKET-DEV-047 | 4. SecOps, CI/CD & Automation | Knip Dead Code Audit | LOW | Code Quality Team | Software Engineer | 3 | COMPLETED | Automated Knip static analysis flagged 14 unused exports in legacy components [Task #47] | Run `knip --no-exit-code` and tree-shake unused mock data structures to reduce bundle size by 120KB. | Production Kubernetes / Staging CI Cluster | Must pass Vitest regression suite, tsc type check, and zero lint warnings.
TICKET-DEV-048 | 4. SecOps, CI/CD & Automation | Semgrep SAST Security | CRITICAL | SecOps Team | AppSec Engineer | 6 | COMPLETED | Semgrep security rule scanner flagged potential XSS target in unescaped innerHTML [Task #48] | Static analysis identified unescaped user note rendering in legacy support widget. Replace with DOMPurify. | Production Kubernetes / Staging CI Cluster | Must pass Vitest regression suite, tsc type check, and zero lint warnings.
TICKET-DEV-049 | 1. Development Scaling & Infrastructure | Database Connection Pool | CRITICAL | DevOps & Infra Team | Senior DevOps Engineer | 8 | UNASSIGNED | Scale BigQuery / PostgreSQL connection pool for 50,000 concurrent logins [Task #49] | Database connection pool saturated during morning peak. Configure max_connections=500 and deploy pgBouncer. | Production Kubernetes / Staging CI Cluster | Must pass Vitest regression suite, tsc type check, and zero lint warnings.
TICKET-DEV-050 | 1. Development Scaling & Infrastructure | Redis Cache Layer | HIGH | Backend Engineering | Backend Tech Lead | 12 | REVIEW_PENDING | Implement Redis cluster caching for live wearable sensor telemetry [Task #50] | Direct DB queries for live heart rate telemetry causing query latency. Need Redis L2 cache with 60s TTL. | Production Kubernetes / Staging CI Cluster | Must pass Vitest regression suite, tsc type check, and zero lint warnings.
TICKET-DEV-051 | 1. Development Scaling & Infrastructure | Kubernetes HPA | HIGH | DevOps & Infra Team | Cloud Infra Specialist | 6 | COMPLETED | Configure Kubernetes Horizontal Pod Autoscaler for API Gateway under 10k RPS [Task #51] | Auto-scaling trigger threshold set too high (85% CPU). Lower CPU target to 65% for instant pod spin-up. | Production Kubernetes / Staging CI Cluster | Must pass Vitest regression suite, tsc type check, and zero lint warnings.
TICKET-DEV-052 | 1. Development Scaling & Infrastructure | CDN Asset Cache | MEDIUM | Frontend Performance Team | Frontend Lead | 5 | IN_PROGRESS | Static media and bundle asset distribution via Cloudflare CDN [Task #52] | Static JS bundles exceeding 2.5MB payload on slow 3G mobile devices. Implement Brotli compression & CDN edge caching. | Production Kubernetes / Staging CI Cluster | Must pass Vitest regression suite, tsc type check, and zero lint warnings.
TICKET-DEV-053 | 1. Development Scaling & Infrastructure | WebSocket Heartbeat | HIGH | Realtime WebSockets Team | WebSockets Developer | 8 | UNASSIGNED | Real-time vitals camera streaming WebSocket socket reconnection stability [Task #53] | WebSocket connections dropping after 5 minutes of idle posture coaching. Implement exponential backoff ping/pong heartbeat. | Production Kubernetes / Staging CI Cluster | Must pass Vitest regression suite, tsc type check, and zero lint warnings.
TICKET-DEV-054 | 2. QA Backend & Test Automation | Playwright E2E | HIGH | QA Automation Team | QA Lead Engineer | 6 | COMPLETED | Playwright End-to-End browser test suite failing on Signup Step 6 Plan Selection [Task #54] | Automated Playwright test `tests/e2e/signup_flow.spec.ts` failed due to missing plan selection modal selector. | Production Kubernetes / Staging CI Cluster | Must pass Vitest regression suite, tsc type check, and zero lint warnings.
TICKET-DEV-055 | 2. QA Backend & Test Automation | Vitest Unit Coverage | MEDIUM | QA Automation Team | Senior QA Automation Engineer | 4 | IN_PROGRESS | Vitest unit test coverage dropped below mandatory 85% threshold [Task #55] | New health overview telemetry module added without unit test assertions. Need 100% coverage on `healthExperience.ts`. | Production Kubernetes / Staging CI Cluster | Must pass Vitest regression suite, tsc type check, and zero lint warnings.
TICKET-DEV-056 | 2. QA Backend & Test Automation | API Contract Test | HIGH | Backend Engineering | API Integration Developer | 6 | COMPLETED | OpenAPI schema validation mismatch on POST /api/v1/telemetry/vitals endpoint [Task #56] | Contract test flagged missing `sensorAccuracyIndex` field in JSON request payload. | Production Kubernetes / Staging CI Cluster | Must pass Vitest regression suite, tsc type check, and zero lint warnings.
TICKET-DEV-057 | 3. AI Architecture & LLM Engineering | Crisis Gate Safety | CRITICAL | AI Safety & Ethics Team | Principal AI Architect | 16 | UNASSIGNED | Crisis Gate AI deterministic bypass latency under 10ms for URGENT_EMERGENCY prompts [Task #57] | Crisis detection gate must process self-harm / panic keywords strictly on-device in <10ms without hitting remote LLM. | Production Kubernetes / Staging CI Cluster | Must pass Vitest regression suite, tsc type check, and zero lint warnings.
TICKET-DEV-058 | 3. AI Architecture & LLM Engineering | AI Voice Prescription | HIGH | AI Speech & NLP Team | NLP / Speech Engineer | 14 | IN_PROGRESS | Optimize Speech-to-Text Whisper model latency for medical dosage parsing [Task #58] | Voice prescription recording parsing taking >3.2 seconds. Need streaming chunk parsing via WebSockets. | Production Kubernetes / Staging CI Cluster | Must pass Vitest regression suite, tsc type check, and zero lint warnings.
TICKET-DEV-059 | 3. AI Architecture & LLM Engineering | RAG Vector Store | HIGH | AI Data Engineering | Data / Vector DB Engineer | 10 | COMPLETED | Vector DB embedding index sync for 1,000+ medical guidelines & drug interactions [Task #59] | Pinecone / Qdrant vector index out of sync with new NABL lab test reference values. | Production Kubernetes / Staging CI Cluster | Must pass Vitest regression suite, tsc type check, and zero lint warnings.
TICKET-DEV-060 | 3. AI Architecture & LLM Engineering | Prompt Injection Defense | CRITICAL | AI Security Team | AI Security Researcher | 12 | COMPLETED | Harden AI Health Assistant system prompt against jailbreak injection attacks [Task #60] | Red team security scan identified prompt bypass attempt targeting system constitution rules. | Production Kubernetes / Staging CI Cluster | Must pass Vitest regression suite, tsc type check, and zero lint warnings.
TICKET-DEV-061 | 4. SecOps, CI/CD & Automation | 4-Hr Scouting Agent | HIGH | SecOps & Automation Team | Automation Engineer | 6 | UNASSIGNED | 4-Hour AI Scouting Agent background cron schedule execution monitoring [Task #61] | Background schedule task `task-524` verified running on `0 */4 * * *` cron schedule pulling campus telemetry. | Production Kubernetes / Staging CI Cluster | Must pass Vitest regression suite, tsc type check, and zero lint warnings.
TICKET-DEV-062 | 4. SecOps, CI/CD & Automation | GitHub Actions CI | MEDIUM | DevOps Team | CI/CD Specialist | 4 | COMPLETED | GitHub Actions CI pipeline execution time optimization (Reduce from 8m to 2m) [Task #62] | Cache node_modules and Vitest transform files to accelerate pull request quality gate checks. | Production Kubernetes / Staging CI Cluster | Must pass Vitest regression suite, tsc type check, and zero lint warnings.
TICKET-DEV-063 | 4. SecOps, CI/CD & Automation | Knip Dead Code Audit | LOW | Code Quality Team | Software Engineer | 3 | COMPLETED | Automated Knip static analysis flagged 14 unused exports in legacy components [Task #63] | Run `knip --no-exit-code` and tree-shake unused mock data structures to reduce bundle size by 120KB. | Production Kubernetes / Staging CI Cluster | Must pass Vitest regression suite, tsc type check, and zero lint warnings.
TICKET-DEV-064 | 4. SecOps, CI/CD & Automation | Semgrep SAST Security | CRITICAL | SecOps Team | AppSec Engineer | 6 | IN_PROGRESS | Semgrep security rule scanner flagged potential XSS target in unescaped innerHTML [Task #64] | Static analysis identified unescaped user note rendering in legacy support widget. Replace with DOMPurify. | Production Kubernetes / Staging CI Cluster | Must pass Vitest regression suite, tsc type check, and zero lint warnings.
TICKET-DEV-065 | 1. Development Scaling & Infrastructure | Database Connection Pool | CRITICAL | DevOps & Infra Team | Senior DevOps Engineer | 8 | UNASSIGNED | Scale BigQuery / PostgreSQL connection pool for 50,000 concurrent logins [Task #65] | Database connection pool saturated during morning peak. Configure max_connections=500 and deploy pgBouncer. | Production Kubernetes / Staging CI Cluster | Must pass Vitest regression suite, tsc type check, and zero lint warnings.
TICKET-DEV-066 | 1. Development Scaling & Infrastructure | Redis Cache Layer | HIGH | Backend Engineering | Backend Tech Lead | 12 | COMPLETED | Implement Redis cluster caching for live wearable sensor telemetry [Task #66] | Direct DB queries for live heart rate telemetry causing query latency. Need Redis L2 cache with 60s TTL. | Production Kubernetes / Staging CI Cluster | Must pass Vitest regression suite, tsc type check, and zero lint warnings.
TICKET-DEV-067 | 1. Development Scaling & Infrastructure | Kubernetes HPA | HIGH | DevOps & Infra Team | Cloud Infra Specialist | 6 | IN_PROGRESS | Configure Kubernetes Horizontal Pod Autoscaler for API Gateway under 10k RPS [Task #67] | Auto-scaling trigger threshold set too high (85% CPU). Lower CPU target to 65% for instant pod spin-up. | Production Kubernetes / Staging CI Cluster | Must pass Vitest regression suite, tsc type check, and zero lint warnings.
TICKET-DEV-068 | 1. Development Scaling & Infrastructure | CDN Asset Cache | MEDIUM | Frontend Performance Team | Frontend Lead | 5 | COMPLETED | Static media and bundle asset distribution via Cloudflare CDN [Task #68] | Static JS bundles exceeding 2.5MB payload on slow 3G mobile devices. Implement Brotli compression & CDN edge caching. | Production Kubernetes / Staging CI Cluster | Must pass Vitest regression suite, tsc type check, and zero lint warnings.
TICKET-DEV-069 | 1. Development Scaling & Infrastructure | WebSocket Heartbeat | HIGH | Realtime WebSockets Team | WebSockets Developer | 8 | UNASSIGNED | Real-time vitals camera streaming WebSocket socket reconnection stability [Task #69] | WebSocket connections dropping after 5 minutes of idle posture coaching. Implement exponential backoff ping/pong heartbeat. | Production Kubernetes / Staging CI Cluster | Must pass Vitest regression suite, tsc type check, and zero lint warnings.
TICKET-DEV-070 | 2. QA Backend & Test Automation | Playwright E2E | HIGH | QA Automation Team | QA Lead Engineer | 6 | IN_PROGRESS | Playwright End-to-End browser test suite failing on Signup Step 6 Plan Selection [Task #70] | Automated Playwright test `tests/e2e/signup_flow.spec.ts` failed due to missing plan selection modal selector. | Production Kubernetes / Staging CI Cluster | Must pass Vitest regression suite, tsc type check, and zero lint warnings.
TICKET-DEV-071 | 2. QA Backend & Test Automation | Vitest Unit Coverage | MEDIUM | QA Automation Team | Senior QA Automation Engineer | 4 | REVIEW_PENDING | Vitest unit test coverage dropped below mandatory 85% threshold [Task #71] | New health overview telemetry module added without unit test assertions. Need 100% coverage on `healthExperience.ts`. | Production Kubernetes / Staging CI Cluster | Must pass Vitest regression suite, tsc type check, and zero lint warnings.
TICKET-DEV-072 | 2. QA Backend & Test Automation | API Contract Test | HIGH | Backend Engineering | API Integration Developer | 6 | COMPLETED | OpenAPI schema validation mismatch on POST /api/v1/telemetry/vitals endpoint [Task #72] | Contract test flagged missing `sensorAccuracyIndex` field in JSON request payload. | Production Kubernetes / Staging CI Cluster | Must pass Vitest regression suite, tsc type check, and zero lint warnings.
TICKET-DEV-073 | 3. AI Architecture & LLM Engineering | Crisis Gate Safety | CRITICAL | AI Safety & Ethics Team | Principal AI Architect | 16 | UNASSIGNED | Crisis Gate AI deterministic bypass latency under 10ms for URGENT_EMERGENCY prompts [Task #73] | Crisis detection gate must process self-harm / panic keywords strictly on-device in <10ms without hitting remote LLM. | Production Kubernetes / Staging CI Cluster | Must pass Vitest regression suite, tsc type check, and zero lint warnings.
TICKET-DEV-074 | 3. AI Architecture & LLM Engineering | AI Voice Prescription | HIGH | AI Speech & NLP Team | NLP / Speech Engineer | 14 | COMPLETED | Optimize Speech-to-Text Whisper model latency for medical dosage parsing [Task #74] | Voice prescription recording parsing taking >3.2 seconds. Need streaming chunk parsing via WebSockets. | Production Kubernetes / Staging CI Cluster | Must pass Vitest regression suite, tsc type check, and zero lint warnings.
TICKET-DEV-075 | 3. AI Architecture & LLM Engineering | RAG Vector Store | HIGH | AI Data Engineering | Data / Vector DB Engineer | 10 | COMPLETED | Vector DB embedding index sync for 1,000+ medical guidelines & drug interactions [Task #75] | Pinecone / Qdrant vector index out of sync with new NABL lab test reference values. | Production Kubernetes / Staging CI Cluster | Must pass Vitest regression suite, tsc type check, and zero lint warnings.
TICKET-DEV-076 | 3. AI Architecture & LLM Engineering | Prompt Injection Defense | CRITICAL | AI Security Team | AI Security Researcher | 12 | IN_PROGRESS | Harden AI Health Assistant system prompt against jailbreak injection attacks [Task #76] | Red team security scan identified prompt bypass attempt targeting system constitution rules. | Production Kubernetes / Staging CI Cluster | Must pass Vitest regression suite, tsc type check, and zero lint warnings.
TICKET-DEV-077 | 4. SecOps, CI/CD & Automation | 4-Hr Scouting Agent | HIGH | SecOps & Automation Team | Automation Engineer | 6 | UNASSIGNED | 4-Hour AI Scouting Agent background cron schedule execution monitoring [Task #77] | Background schedule task `task-524` verified running on `0 */4 * * *` cron schedule pulling campus telemetry. | Production Kubernetes / Staging CI Cluster | Must pass Vitest regression suite, tsc type check, and zero lint warnings.
TICKET-DEV-078 | 4. SecOps, CI/CD & Automation | GitHub Actions CI | MEDIUM | DevOps Team | CI/CD Specialist | 4 | REVIEW_PENDING | GitHub Actions CI pipeline execution time optimization (Reduce from 8m to 2m) [Task #78] | Cache node_modules and Vitest transform files to accelerate pull request quality gate checks. | Production Kubernetes / Staging CI Cluster | Must pass Vitest regression suite, tsc type check, and zero lint warnings.
TICKET-DEV-079 | 4. SecOps, CI/CD & Automation | Knip Dead Code Audit | LOW | Code Quality Team | Software Engineer | 3 | IN_PROGRESS | Automated Knip static analysis flagged 14 unused exports in legacy components [Task #79] | Run `knip --no-exit-code` and tree-shake unused mock data structures to reduce bundle size by 120KB. | Production Kubernetes / Staging CI Cluster | Must pass Vitest regression suite, tsc type check, and zero lint warnings.
TICKET-DEV-080 | 4. SecOps, CI/CD & Automation | Semgrep SAST Security | CRITICAL | SecOps Team | AppSec Engineer | 6 | COMPLETED | Semgrep security rule scanner flagged potential XSS target in unescaped innerHTML [Task #80] | Static analysis identified unescaped user note rendering in legacy support widget. Replace with DOMPurify. | Production Kubernetes / Staging CI Cluster | Must pass Vitest regression suite, tsc type check, and zero lint warnings.
TICKET-DEV-081 | 1. Development Scaling & Infrastructure | Database Connection Pool | CRITICAL | DevOps & Infra Team | Senior DevOps Engineer | 8 | UNASSIGNED | Scale BigQuery / PostgreSQL connection pool for 50,000 concurrent logins [Task #81] | Database connection pool saturated during morning peak. Configure max_connections=500 and deploy pgBouncer. | Production Kubernetes / Staging CI Cluster | Must pass Vitest regression suite, tsc type check, and zero lint warnings.
TICKET-DEV-082 | 1. Development Scaling & Infrastructure | Redis Cache Layer | HIGH | Backend Engineering | Backend Tech Lead | 12 | IN_PROGRESS | Implement Redis cluster caching for live wearable sensor telemetry [Task #82] | Direct DB queries for live heart rate telemetry causing query latency. Need Redis L2 cache with 60s TTL. | Production Kubernetes / Staging CI Cluster | Must pass Vitest regression suite, tsc type check, and zero lint warnings.
TICKET-DEV-083 | 1. Development Scaling & Infrastructure | Kubernetes HPA | HIGH | DevOps & Infra Team | Cloud Infra Specialist | 6 | COMPLETED | Configure Kubernetes Horizontal Pod Autoscaler for API Gateway under 10k RPS [Task #83] | Auto-scaling trigger threshold set too high (85% CPU). Lower CPU target to 65% for instant pod spin-up. | Production Kubernetes / Staging CI Cluster | Must pass Vitest regression suite, tsc type check, and zero lint warnings.
TICKET-DEV-084 | 1. Development Scaling & Infrastructure | CDN Asset Cache | MEDIUM | Frontend Performance Team | Frontend Lead | 5 | COMPLETED | Static media and bundle asset distribution via Cloudflare CDN [Task #84] | Static JS bundles exceeding 2.5MB payload on slow 3G mobile devices. Implement Brotli compression & CDN edge caching. | Production Kubernetes / Staging CI Cluster | Must pass Vitest regression suite, tsc type check, and zero lint warnings.
TICKET-DEV-085 | 1. Development Scaling & Infrastructure | WebSocket Heartbeat | HIGH | Realtime WebSockets Team | WebSockets Developer | 8 | UNASSIGNED | Real-time vitals camera streaming WebSocket socket reconnection stability [Task #85] | WebSocket connections dropping after 5 minutes of idle posture coaching. Implement exponential backoff ping/pong heartbeat. | Production Kubernetes / Staging CI Cluster | Must pass Vitest regression suite, tsc type check, and zero lint warnings.
TICKET-DEV-086 | 2. QA Backend & Test Automation | Playwright E2E | HIGH | QA Automation Team | QA Lead Engineer | 6 | COMPLETED | Playwright End-to-End browser test suite failing on Signup Step 6 Plan Selection [Task #86] | Automated Playwright test `tests/e2e/signup_flow.spec.ts` failed due to missing plan selection modal selector. | Production Kubernetes / Staging CI Cluster | Must pass Vitest regression suite, tsc type check, and zero lint warnings.
TICKET-DEV-087 | 2. QA Backend & Test Automation | Vitest Unit Coverage | MEDIUM | QA Automation Team | Senior QA Automation Engineer | 4 | COMPLETED | Vitest unit test coverage dropped below mandatory 85% threshold [Task #87] | New health overview telemetry module added without unit test assertions. Need 100% coverage on `healthExperience.ts`. | Production Kubernetes / Staging CI Cluster | Must pass Vitest regression suite, tsc type check, and zero lint warnings.
TICKET-DEV-088 | 2. QA Backend & Test Automation | API Contract Test | HIGH | Backend Engineering | API Integration Developer | 6 | IN_PROGRESS | OpenAPI schema validation mismatch on POST /api/v1/telemetry/vitals endpoint [Task #88] | Contract test flagged missing `sensorAccuracyIndex` field in JSON request payload. | Production Kubernetes / Staging CI Cluster | Must pass Vitest regression suite, tsc type check, and zero lint warnings.
TICKET-DEV-089 | 3. AI Architecture & LLM Engineering | Crisis Gate Safety | CRITICAL | AI Safety & Ethics Team | Principal AI Architect | 16 | UNASSIGNED | Crisis Gate AI deterministic bypass latency under 10ms for URGENT_EMERGENCY prompts [Task #89] | Crisis detection gate must process self-harm / panic keywords strictly on-device in <10ms without hitting remote LLM. | Production Kubernetes / Staging CI Cluster | Must pass Vitest regression suite, tsc type check, and zero lint warnings.
TICKET-DEV-090 | 3. AI Architecture & LLM Engineering | AI Voice Prescription | HIGH | AI Speech & NLP Team | NLP / Speech Engineer | 14 | COMPLETED | Optimize Speech-to-Text Whisper model latency for medical dosage parsing [Task #90] | Voice prescription recording parsing taking >3.2 seconds. Need streaming chunk parsing via WebSockets. | Production Kubernetes / Staging CI Cluster | Must pass Vitest regression suite, tsc type check, and zero lint warnings.
TICKET-DEV-091 | 3. AI Architecture & LLM Engineering | RAG Vector Store | HIGH | AI Data Engineering | Data / Vector DB Engineer | 10 | IN_PROGRESS | Vector DB embedding index sync for 1,000+ medical guidelines & drug interactions [Task #91] | Pinecone / Qdrant vector index out of sync with new NABL lab test reference values. | Production Kubernetes / Staging CI Cluster | Must pass Vitest regression suite, tsc type check, and zero lint warnings.
TICKET-DEV-092 | 3. AI Architecture & LLM Engineering | Prompt Injection Defense | CRITICAL | AI Security Team | AI Security Researcher | 12 | REVIEW_PENDING | Harden AI Health Assistant system prompt against jailbreak injection attacks [Task #92] | Red team security scan identified prompt bypass attempt targeting system constitution rules. | Production Kubernetes / Staging CI Cluster | Must pass Vitest regression suite, tsc type check, and zero lint warnings.
TICKET-DEV-093 | 4. SecOps, CI/CD & Automation | 4-Hr Scouting Agent | HIGH | SecOps & Automation Team | Automation Engineer | 6 | UNASSIGNED | 4-Hour AI Scouting Agent background cron schedule execution monitoring [Task #93] | Background schedule task `task-524` verified running on `0 */4 * * *` cron schedule pulling campus telemetry. | Production Kubernetes / Staging CI Cluster | Must pass Vitest regression suite, tsc type check, and zero lint warnings.
TICKET-DEV-094 | 4. SecOps, CI/CD & Automation | GitHub Actions CI | MEDIUM | DevOps Team | CI/CD Specialist | 4 | IN_PROGRESS | GitHub Actions CI pipeline execution time optimization (Reduce from 8m to 2m) [Task #94] | Cache node_modules and Vitest transform files to accelerate pull request quality gate checks. | Production Kubernetes / Staging CI Cluster | Must pass Vitest regression suite, tsc type check, and zero lint warnings.
TICKET-DEV-095 | 4. SecOps, CI/CD & Automation | Knip Dead Code Audit | LOW | Code Quality Team | Software Engineer | 3 | COMPLETED | Automated Knip static analysis flagged 14 unused exports in legacy components [Task #95] | Run `knip --no-exit-code` and tree-shake unused mock data structures to reduce bundle size by 120KB. | Production Kubernetes / Staging CI Cluster | Must pass Vitest regression suite, tsc type check, and zero lint warnings.
TICKET-DEV-096 | 4. SecOps, CI/CD & Automation | Semgrep SAST Security | CRITICAL | SecOps Team | AppSec Engineer | 6 | COMPLETED | Semgrep security rule scanner flagged potential XSS target in unescaped innerHTML [Task #96] | Static analysis identified unescaped user note rendering in legacy support widget. Replace with DOMPurify. | Production Kubernetes / Staging CI Cluster | Must pass Vitest regression suite, tsc type check, and zero lint warnings.
TICKET-DEV-097 | 1. Development Scaling & Infrastructure | Database Connection Pool | CRITICAL | DevOps & Infra Team | Senior DevOps Engineer | 8 | UNASSIGNED | Scale BigQuery / PostgreSQL connection pool for 50,000 concurrent logins [Task #97] | Database connection pool saturated during morning peak. Configure max_connections=500 and deploy pgBouncer. | Production Kubernetes / Staging CI Cluster | Must pass Vitest regression suite, tsc type check, and zero lint warnings.
TICKET-DEV-098 | 1. Development Scaling & Infrastructure | Redis Cache Layer | HIGH | Backend Engineering | Backend Tech Lead | 12 | COMPLETED | Implement Redis cluster caching for live wearable sensor telemetry [Task #98] | Direct DB queries for live heart rate telemetry causing query latency. Need Redis L2 cache with 60s TTL. | Production Kubernetes / Staging CI Cluster | Must pass Vitest regression suite, tsc type check, and zero lint warnings.
TICKET-DEV-099 | 1. Development Scaling & Infrastructure | Kubernetes HPA | HIGH | DevOps & Infra Team | Cloud Infra Specialist | 6 | REVIEW_PENDING | Configure Kubernetes Horizontal Pod Autoscaler for API Gateway under 10k RPS [Task #99] | Auto-scaling trigger threshold set too high (85% CPU). Lower CPU target to 65% for instant pod spin-up. | Production Kubernetes / Staging CI Cluster | Must pass Vitest regression suite, tsc type check, and zero lint warnings.
TICKET-DEV-100 | 1. Development Scaling & Infrastructure | CDN Asset Cache | MEDIUM | Frontend Performance Team | Frontend Lead | 5 | IN_PROGRESS | Static media and bundle asset distribution via Cloudflare CDN [Task #100] | Static JS bundles exceeding 2.5MB payload on slow 3G mobile devices. Implement Brotli compression & CDN edge caching. | Production Kubernetes / Staging CI Cluster | Must pass Vitest regression suite, tsc type check, and zero lint warnings.