## Read me
Student Kare — full build backlog
Every screen on the design canvas (StudentKare — Onboarding & Auth Flows, 239 artboards on 9 pages), split into buildable tickets. Built 29 Sep 2026.
How to use
• Tickets tab: one row per ticket. Edit only Status, Owner and Sprint (yellow headers).
• Status: To do · In progress · In review · Done · Blocked.
• Priority: P0 = needed for launch · P1 = launch month · P2 = later. Phase: 0 Foundations → 1 Launch → 2 Launch month → 3 Later.
• Tier (from DESIGN.md): 1 = safety-critical, needs named design + clinical/legal review before build · 2 = core flow · 3 = composable from components.
• Estimate is in story points (1, 2, 3, 5, 8) and is a first guess for planning — re-point in refinement.
• Depends on: ticket IDs that should be done first. Screens: exact artboard names on the canvas (and in the screens pack).
• Screens tab: every artboard → the ticket that builds it. Epics tab: totals per epic.
• This replaces studentkare-engineering-backlog.xlsx: its 41 tickets are folded in (see "Replaces" column). Tickets do not check what already exists in the repo — confirm in refinement.
• Jira/Linear import: use studentkare-full-backlog.csv from the same folder.
Summary (updates as you edit Status)
| Tickets | Points | Done | Open | % done (tickets)
P0 | 90 | 536 | 0 | 90 | 0%
P1 | 46 | 199 | 0 | 46 | 0%
P2 | 11 | 50 | 0 | 11 | 0%
Total | 147 | 785 | 0 | 147 | 0%
Open decisions that block tickets
• Student Plus price: ₹99 (code) or ₹199 (designs) — blocks SK-005 and pricing screens.
• Under-18 accounts: AGENTS.md says 18+ only; the guardian-consent tickets need a yes/no.
• D1 palette, D2 font, D3 dark mode (DESIGN.md) — blocks SK-007.
• Real grievance-officer details and legal review — blocks legal pages and launch.
• Named clinical reviewer for every Tier 1 ticket.

## Tickets
ID | Epic | Ticket | Type | Platform | Screens (canvas) | Canvas page | Tier | Priority | Phase | Estimate (pts) | Description | Acceptance criteria | Depends on | Depends on (names) | Backend / API needed | Rules, risks & decisions | Status | Owner | Sprint | Replaces
SK-001 | E0 · Launch blockers | Delete the fake X-ray diagnosis endpoint | Task | Backend | — | — | 1 | P0 | 0 · Foundations | 2 | The /ai/xray-diagnostic-scan route returns an AI "diagnosis". Student Kare never diagnoses. Remove the route, its service and any UI that calls it (patch SK-001 already prepared). | • Route removed; calling it returns 404 • No UI entry point remains • Test covers the 404 |  |  | Remove route + service | No AI diagnosis anywhere in the product. | To do |  |  | SKB-001
SK-002 | E0 · Launch blockers | Remove camera vitals and the fake readings they create | Task | Mobile + Backend | Devices | 2 · Student app (mobile) | 1 | P0 | 0 · Foundations | 3 | Camera-based vitals (rPPG) produced invented numbers. Remove /health/camera-scan and the four camera scanner components; Devices shows only real paired devices and typed readings (patch SK-002). | • Camera scan route and components deleted • No stored reading without a device or "Typed by you" source • Devices screen matches the redesigned board |  |  | Remove /health/camera-scan | Honest data: no invented numbers. | To do |  |  | SKB-002
SK-003 | E0 · Launch blockers | Turn demo mode off by default (no demo admin, no fixed OTP) | Task | Backend | SignIn, OtpVerify, AdminSignIn | 1 · Launch & onboarding, 7 · Super admin | 1 | P0 | 0 · Foundations | 3 | Demo seeding and the console OTP must only run when APP_ENV is development/testing AND SEED_DEMO_DATA=true. Production never creates a SUPER_ADMIN demo user or accepts 123456 (patch SK-004). | • Fresh production install has no admin and no demo users • OTP is random, 6 digits, 5-minute expiry, 5 tries • DEV_OTP_CONSOLE defaults to false • Tests cover both modes |  |  | workflow_auth demo_mode_enabled() |  | To do |  |  | SKB-003
SK-004 | E0 · Launch blockers | Lock the APILayer proxy endpoints behind super-admin auth | Task | Backend | AdminApiKeys, Integrations | 7 · Super admin | 1 | P0 | 0 · Foundations | 3 | The 14 APILayer proxy routes are open. Require super-admin auth on the router, rotate the keys, and log each call (patch SK-005). The API access & keys screen shows key status. | • Unauthenticated call returns 401 • Keys rotated and stored as secrets • Audit log entry per call (no request bodies) | SK-128 | Staff and admin sign-in, console home | Router dependency require_super_admin |  | To do |  |  | SKB-004
SK-005 | E0 · Launch blockers | One source of truth for the Student Plus price | Task | Web + Mobile + Backend | AdminPriceFix, AdminPlansPricing, WebPlans, PlanBilling | 7 · Super admin, 3a · Student web — public site, 2 · Student app (mobile) | 1 | P0 | 0 · Foundations | 3 | Code says ₹99, designs say ₹199. Pick the price (decision), store it once, and make every surface read it. The AdminPriceFix screen lists every place a price appears (patch SK-006). | • Decision recorded (₹99 or ₹199) • Price comes from one config/API value • Web Plans, Plan & billing, checkout and admin all show the same number |  |  | Plans endpoint returns price in paise | Price always shown before the student commits. | To do |  |  | SKB-005
SK-006 | E0 · Launch blockers | Keep LifeShare and on-hold module routes unreachable | Task | Web + Mobile | — | — | 2 | P0 | 0 · Foundations | 2 | On-hold modules (LifeShare, incident mocks) must not be reachable in production builds. Gate them behind VITE_ENABLE_ON_HOLD_MODULES (default off). | • Production build has no route to on-hold modules • Flag documented in env example |  |  |  |  | To do |  |  | SKB-006
SK-007 | E1 · Design system foundations | Apply design-token foundations and adopt one palette (D1) and font (D2) | Task | Web + Mobile | IconSystem, MotionSystem | 8 · Design system & flow map | 3 | P0 | 0 · Foundations | 5 | Merge the design-system foundations patch (DESIGN.md, token JSON, generator, contrast test). Then, after product sign-off, point tokens.ts and workflows.css at the generated values and use Plus Jakarta Sans everywhere. | • npm run tokens:check passes in CI • Runtime theme uses generated tokens • Plus Jakarta Sans loaded for UI, IBM Plex Mono for values • Contrast test green |  |  |  | Decisions D1 (palette), D2 (font), D3 (dark mode) need an owner. | To do
SK-008 | E1 · Design system foundations | Set up Storybook with accessibility and visual-regression checks | Task | Web | — | — | 3 | P0 | 0 · Foundations | 5 | Every core component needs stories for every state. Add Storybook (react-native-web), the a11y addon and a visual-regression step in CI. | • Storybook runs locally and in CI • axe checks fail the build on violations • Visual snapshots stored per story |  |  |  |  | To do
SK-009 | E1 · Design system foundations | Lint rule that blocks new hard-coded colours | Task | Web + Mobile | — | — | 3 | P1 | 2 · Launch month | 2 | About 3,090 raw hex values exist in 171 files. Add a lint rule that fails on new hex values outside the design-system folder; migrate old ones when a screen is touched. | • New hex value fails lint • Existing files allow-listed with a count that can only go down | SK-007 | Apply design-token foundations and adopt one palette (D1) and font (D2) |  |  | To do
SK-010 | E1 · Design system foundations | Buttons and form inputs | Story | Web + Mobile | Feedback, SignIn, OtpVerify, CreateAccount | 8 · Design system & flow map, 1 · Launch & onboarding | 3 | P0 | 0 · Foundations | 5 | Button (primary, secondary, ghost, danger) and inputs: text, select, 6-digit code, +91 phone. These are used on nearly every screen. | • All variants and states have stories (default, hover, focus, busy, disabled, invalid) • 50 px inputs/buttons, 54 px primary CTA, 44 px hit areas • Error message linked with aria-describedby | SK-008 | Set up Storybook with accessibility and visual-regression checks |  |  | To do
SK-011 | E1 · Design system foundations | Checkbox, switch, radio and chips | Story | Web + Mobile | OnboardingConsent, NotificationSettings, Permissions | 1 · Launch & onboarding, 2 · Student app (mobile) | 3 | P0 | 0 · Foundations | 3 | Selection controls used in consent, settings and filters. | • off/on/disabled/focus stories • Real input elements with labels • Consent checkboxes never pre-ticked | SK-008 | Set up Storybook with accessibility and visual-regression checks |  |  | To do
SK-012 | E1 · Design system foundations | Cards, list rows, section headers, notes and banners | Story | Web + Mobile | Feedback, MoreHub, YourCare | 8 · Design system & flow map, 2 · Student app (mobile) | 3 | P0 | 0 · Foundations | 5 | Layout building blocks: card, list row (with chevron/action), eyebrow section header, note/banner in info, positive, attention and danger. | • Stories for default, selected, with action • Note tones use semantic tokens (out-of-range = attention/amber, never red) | SK-008 | Set up Storybook with accessibility and visual-regression checks |  |  | To do
SK-013 | E1 · Design system foundations | Toasts and inline validation | Story | Web + Mobile | Feedback | 8 · Design system & flow map | 3 | P0 | 0 · Foundations | 3 | Neutral, success and error toasts (wrap on phone) and inline field validation from the Feedback board. | • role="status" for toasts • Toasts never carry health values | SK-010 | Buttons and form inputs |  |  | To do
SK-014 | E1 · Design system foundations | Bottom sheet, drawer, dialog and confirm dialogs | Story | Web + Mobile | Sheets, NavSheets, ConfirmDialogs | 8 · Design system & flow map | 3 | P0 | 0 · Foundations | 5 | Phone bottom sheets, web drawers and dialogs, plus the confirm dialogs for log out, cancel booking and revoke access. | • aria-modal + focus trap + Esc closes • open, busy, done states • Cancel as easy as confirm | SK-010 | Buttons and form inputs |  |  | To do
SK-015 | E1 · Design system foundations | Empty, loading, error and offline states | Story | Web + Mobile | StateScreens | 8 · Design system & flow map | 3 | P0 | 0 · Foundations | 5 | Shared full-screen and inline states for every role: skeleton loading, empty with one next step, error with retry and reference code, offline banner. | • One component per state with role-specific copy props • Error copy says whose side the problem is on | SK-012 | Cards, list rows, section headers, notes and banners |  |  | To do
SK-016 | E1 · Design system foundations | Result moments (success, failure, pending) | Story | Web + Mobile | StatusMoments | 8 · Design system & flow map | 3 | P1 | 2 · Launch month | 3 | Full-screen outcome for bookings and payments. | • Success animation only for commerce and bookings • Reduced motion respected • Failure shows what to do next | SK-015 | Empty, loading, error and offline states |  | Never celebrate anything about the body. | To do |  |  | SKB-027
SK-017 | E1 · Design system foundations | Navigation: phone tab bar, web header, footer and role sidebars | Story | Web + Mobile | NavSheets, Landing, WebHome, ClinicianConsole, VendorConsole, CampusAdminConsole, SuperAdminConsole | 8 · Design system & flow map, 3a · Student web — public site, 3b · Student web — signed in, 5 · Doctor, 6 · Partner — pharmacy, lab, clinic, 4 · Campus / hostel admin, 7 · Super admin | 3 | P0 | 0 · Foundations | 8 | Option B tab bar on phone (Discover, Shop, Your Care, Records, More), the public web header and footer, the signed-in student web menu, and one sidebar per console role with the current page highlighted. | • Same student web menu on every signed-in page • Console sidebars for doctor, partner, campus, super admin • Current page marked with aria-current | SK-010 | Buttons and form inputs |  |  | To do |  |  | SKB-017, SKB-037
SK-018 | E1 · Design system foundations | Icon set, illustrations and motion system | Story | Web + Mobile | IconSystem, IllustrationLibrary, MotionSystem | 8 · Design system & flow map | 3 | P1 | 2 · Launch month | 5 | Flat and 3D icons, the illustration library and motion tokens (160/320/420 ms) as reusable assets. | • Icons exported as components with aria-hidden by default • All motion stops under prefers-reduced-motion | SK-007 | Apply design-token foundations and adopt one palette (D1) and font (D2) |  |  | To do
SK-019 | E1 · Design system foundations | Console data table | Story | Web | CampusRoster, AdminAccounts, AuditExplorer, LabQueue | 4 · Campus / hostel admin, 7 · Super admin, 6 · Partner — pharmacy, lab, clinic | 3 | P0 | 0 · Foundations | 5 | Shared table for all consoles: sorting, filters, row actions, pagination, and loading/empty/error rows. | • Keyboard navigable • Stories for data, loading, empty, error • No PHI in exported CSV unless the role allows it | SK-015 | Empty, loading, error and offline states |  |  | To do |  |  | SKB-038
SK-020 | E1 · Design system foundations | Ayush chat component (web widget and phone sheet) | Story | Web + Mobile | AyushWidget, AyushSheet | 8 · Design system & flow map | 1 | P1 | 2 · Launch month | 5 | One chat component in two shells: the web widget and the phone bottom sheet with context chips. | • Crisis words show the crisis card instead of an AI answer • Dose or diagnosis questions route to a doctor • Web widget docks to the bottom-right of the viewport, never over page content | SK-014 | Bottom sheet, drawer, dialog and confirm dialogs |  | Ayush never diagnoses or prescribes. | To do |  |  | SKB-028
SK-021 | E1 · Design system foundations | Languages: English, Telugu and Hindi | Story | Web + Mobile | CrisisSupport, SosBeacon, EmergencyCard, SignIn, WebSignIn, OnboardingConsent | 2 · Student app (mobile), 1 · Launch & onboarding, 3b · Student web — signed in | 1 | P0 | 0 · Foundations | 5 | i18n set-up and translations, starting with safety, sign-in and consent screens. Names, phone numbers, "WhatsApp", "ABHA" and helpline names stay in English. | • Language switch persists • Noto Sans Telugu / Devanagari loaded • Native-speaker review on crisis copy before launch • No truncation in any language |  |  |  |  | To do |  |  | SKB-041
SK-022 | E1 · Design system foundations | Route map and deep links from the flow map | Task | Web + Mobile | FlowMap | 8 · Design system & flow map | 3 | P1 | 2 · Launch month | 3 | Use the canvas flow map (148 nodes) as the source for the route table, so every screen has a route and every link on the canvas has a destination. | • Route table documented • Deep links for pass, order tracking, guardian approval, report • No dead links between built screens |  |  |  |  | To do
SK-023 | E2 · Launch, sign-in & onboarding | Splash that changes with the time of day | Story | Mobile | Main, SplashPulse, SplashVault | 1 · Launch & onboarding | 3 | P1 | 2 · Launch month | 3 | One bright splash with three variants: morning (doctor), afternoon (heartbeat), evening (care circle), chosen by local hour. | • 5–12 doctor, 12–18 heartbeat, else care circle • Under 2 s; no blocking animation • Reduced motion shows a still frame | SK-018 | Icon set, illustrations and motion system |  |  | To do
SK-024 | E2 · Launch, sign-in & onboarding | Onboarding carousel | Story | Mobile | Onboarding1, Onboarding2, Onboarding3 | 1 · Launch & onboarding | 3 | P1 | 2 · Launch month | 3 | Three intro slides: campus care, health vault, Ayush. Skippable. | • Swipe and buttons both work • Skip goes to sign in • Screen reader announces slide n of 3 | SK-010 | Buttons and form inputs |  |  | To do
SK-025 | E2 · Launch, sign-in & onboarding | Sign in with phone and OTP | Story | Mobile | SignIn, OtpVerify | 1 · Launch & onboarding | 2 | P0 | 1 · Launch | 5 | Phone number sign-in with a 6-digit code, resend timer and lockout. | • +91 10-digit validation • 5 wrong codes → 10-minute lock with message • Resend after 30 s • Crisis/SOS link visible before sign-in | SK-003, SK-010 | Turn demo mode off by default (no demo admin, no fixed OTP); Buttons and form inputs | POST /auth/otp/send, /auth/otp/verify |  | To do
SK-026 | E2 · Launch, sign-in & onboarding | Create account, campus, care profile and permissions | Story | Mobile | CreateAccount, CampusVerify, ProfileSetup, Permissions, AccountReady | 1 · Launch & onboarding | 2 | P0 | 1 · Launch | 8 | The sign-up steps after the first OTP: name and email, campus and hostel, care basics, device permissions, then "Workspace ready". | • Progress shows step n of 6 • Each step saves; back keeps entries • Permissions explained before the OS prompt; all optional • Blood group defaults to "Not set" | SK-025 | Sign in with phone and OTP | POST /students, /students/{id}/campus |  | To do |  |  | SKB-012
SK-027 | E2 · Launch, sign-in & onboarding | Data-protection consent (DPDP) | Story | Mobile | OnboardingConsent | 1 · Launch & onboarding | 1 | P0 | 1 · Launch | 5 | Plain-language consent: what we keep, never do, what you can do, how long. Three required ticks, three optional switches off by default. | • Continue locked until the 3 required items are ticked • Consent version (v3.1) + timestamp stored • English, Telugu, Hindi • Link to full privacy notice and grievance officer | SK-026, SK-021 | Create account, campus, care profile and permissions; Languages: English, Telugu and Hindi | POST /consents (version, items, time) | No pre-ticked consent. Withdrawing is as easy as agreeing. | To do |  |  | SKB-012
SK-028 | E2 · Launch, sign-in & onboarding | Link ABHA | Story | Mobile | AbhaLink | 1 · Launch & onboarding | 2 | P1 | 2 · Launch month | 5 | Link or create an ABHA number so records can be pulled from ABDM. | • Create or link paths • Failure shows reason and a skip option • Only the ABHA number is shown masked | SK-026 | Create account, campus, care profile and permissions | ABDM gateway (ABHA create/link) |  | To do
SK-029 | E2 · Launch, sign-in & onboarding | Verify it’s you — four identity checks | Story | Mobile | VerifyIdentity | 1 · Launch & onboarding | 1 | P0 | 1 · Launch | 8 | Selfie, email code, college ID (roll number + card photo) and government ID (DigiLocker by default). All four needed before booking, ordering or sharing. | • States per check: to do, busy, done, failed, in review • Failures: photo unclear, college rejects, name mismatch, code locked — each with a fix • Only last 4 Aadhaar digits stored | SK-026 | Create account, campus, care profile and permissions | Identity verification service + college confirmation |  | To do |  |  | SKB-007, SKB-008
SK-030 | E2 · Launch, sign-in & onboarding | Verification gate on services | Story | Mobile | VerifyGate | 1 · Launch & onboarding | 1 | P0 | 1 · Launch | 3 | When an unverified student taps book, order or share, show the gate with progress and a way to finish. | • Crisis support, SOS, emergency card and help never gated • "Not now" returns to where the student was | SK-029 | Verify it’s you — four identity checks |  |  | To do |  |  | SKB-009
SK-031 | E2 · Launch, sign-in & onboarding | Under-18: ask a guardian and guardian approval | Story | Mobile + Web | GuardianConsent, GuardianApprove | 1 · Launch & onboarding | 1 | P0 | 1 · Launch | 8 | Students under 18 send an SMS link to a parent or guardian, who approves with an OTP. Limited account until approved; consent ends on the 18th birthday. | • Guardian page works without an app or account • Approve / decline / withdraw (reply STOP) • Student sees status and can still reach crisis support and SOS | SK-027 | Data-protection consent (DPDP) | Guardian consent + SMS | DECISION NEEDED: AGENTS.md says 18+ only. Guardian never sees records, counselling or sexual-health details. | To do |  |  | SKB-011
SK-032 | E2 · Launch, sign-in & onboarding | Sign out and logged-out page | Story | Mobile | SignOut, LoggedOut | 1 · Launch & onboarding | 3 | P1 | 2 · Launch month | 2 | Confirm popup before signing out, then a logged-out page with optional feedback. | • Confirm dialog busy → done • Tokens cleared; offline emergency card kept unless the student chooses otherwise | SK-014 | Bottom sheet, drawer, dialog and confirm dialogs |  |  | To do |  |  | SKB-013
SK-033 | E2 · Launch, sign-in & onboarding | Lost phone and moving to a new phone | Story | Mobile | LostPhone, NewDevice | 1 · Launch & onboarding | 1 | P0 | 1 · Launch | 8 | From a friend’s phone: cancel the check-in pass, sign the lost device out, review the last 24 h of check-ins. New phone: email code + selfie to move the account. | • Pass cancelled immediately • Offline card wiped on the lost device’s next connection • New-device move needs email code + selfie match | SK-057 | Student check-in pass and handover receipt | Device sessions revoke, pass revoke |  | To do |  |  | SKB-014
SK-034 | E3 · Student app — home, search & care | Home / Discover | Story | Mobile | HomeDiscover | 2 · Student app (mobile) | 2 | P0 | 1 · Launch | 5 | The first screen after sign-in: search, quick actions, campus services and the Ayush entry. | • Loading, first-time and offline states • Nothing on Home is chosen from health records • Ask Ayush opens the phone sheet | SK-017, SK-020 | Navigation: phone tab bar, web header, footer and role sidebars; Ayush chat component (web widget and phone sheet) |  |  | To do
SK-035 | E3 · Student app — home, search & care | Search: entry, suggestions, loading, results, no results | Story | Mobile | SearchEntry, SearchTyping, SearchLoading, SearchResults, NoResults | 2 · Student app (mobile) | 2 | P0 | 1 · Launch | 8 | One search across lab tests, doctors, medicines and products, with tabs. | • Suggestions after 2 characters, debounced • Skeletons while loading • No results suggests a next step • Recent searches can be cleared | SK-034 | Home / Discover | GET /search?q=&type= |  | To do
SK-036 | E3 · Student app — home, search & care | Lab test results and booking | Story | Mobile | LabResults, LabPackages, ResultLabBooked | 2 · Student app (mobile) | 2 | P0 | 1 · Launch | 8 | Browse and book lab tests and packages with dorm pickup slots; price shown before booking. | • Slots left per day shown • NABL badge from data, not hard-coded • Booking confirmation moment | SK-035, SK-030 | Search: entry, suggestions, loading, results, no results; Verification gate on services | Lab catalogue, slots, bookings |  | To do
SK-037 | E3 · Student app — home, search & care | Doctor results and appointments | Story | Mobile | DoctorResults, Appointments | 2 · Student app (mobile) | 2 | P0 | 1 · Launch | 5 | Find a doctor (NMC-registered), see price and next slot, book, and manage upcoming appointments. | • Price before booking • Reschedule and cancel with confirm dialog • Empty and offline states | SK-035, SK-030 | Search: entry, suggestions, loading, results, no results; Verification gate on services | Clinician directory, slots, appointments |  | To do
SK-038 | E3 · Student app — home, search & care | Teleconsult call | Story | Mobile | Teleconsult | 2 · Student app (mobile) | 1 | P0 | 1 · Launch | 8 | Video consult with a doctor: pre-call check, in-call controls, end call. | • Camera/mic permission explained • Reconnect on network drop • Ends into the visit summary | SK-037 | Doctor results and appointments | Video provider + consult session |  | To do
SK-039 | E3 · Student app — home, search & care | Visit summary and e-prescription | Story | Mobile + Web | ConsultSummary, WebConsultSummary | 2 · Student app (mobile), 3b · Student web — signed in | 1 | P0 | 1 · Launch | 8 | After a consult: plain-language notes, red flags, signed e-prescription, order medicines or take the Rx anywhere, follow-up, rating. | • Rx carries doctor NMC number and signature • Allergy check shown • Order here or download — student’s choice | SK-038 | Teleconsult call | Encounter summary + Rx |  | To do |  |  | SKB-025
SK-040 | E3 · Student app — home, search & care | Your Care overview | Story | Mobile | YourCare | 2 · Student app (mobile) | 2 | P0 | 1 · Launch | 5 | This week summary, items that need the student, and semester progress. | • First-time and offline states • Every number comes from real data • Ask Ayush opens with "care" context | SK-034 | Home / Discover |  |  | To do |  |  | SKB-039
SK-041 | E3 · Student app — home, search & care | Medicines and refill requests | Story | Mobile | Medications, RefillRequest | 2 · Student app (mobile) | 1 | P1 | 2 · Launch month | 5 | Medicine list with dose ticks and refill requests to a pharmacy or doctor. | • Ticking a dose records it; nothing is scored • Refill shows price and pickup before confirming | SK-040 | Your Care overview | Medication list, refill requests |  | To do
SK-042 | E3 · Student app — home, search & care | Preventive care | Story | Mobile | PreventiveCare | 2 · Student app (mobile) | 2 | P2 | 3 · Later | 3 | Vaccinations and routine checks due, with booking links. | • Due dates from records • No alarming language | SK-040 | Your Care overview |  |  | To do
SK-043 | E3 · Student app — home, search & care | Devices and typed readings | Story | Mobile | Devices | 2 · Student app (mobile) | 1 | P1 | 2 · Launch month | 5 | Pair real devices or type a reading. Each reading shows its source. | • "Typed by you" or device badge on every reading • No camera vitals | SK-002 | Remove camera vitals and the fake readings they create | Readings API with source field |  | To do
SK-044 | E3 · Student app — home, search & care | Movement | Story | Mobile | Movement | 2 · Student app (mobile) | 3 | P2 | 3 · Later | 3 | Sessions this week from guides the student chose. | • No body scores or rankings • Empty state with one next step | SK-040 | Your Care overview |  |  | To do
SK-045 | E3 · Student app — home, search & care | Vital trends | Story | Mobile | VitalTrends | 2 · Student app (mobile) | 1 | P1 | 2 · Launch month | 5 | Charts of readings over time with the lab or device reference range. | • Out of range shown in amber, never red • Source badge per point • Clinical values in mono font | SK-043 | Devices and typed readings |  | Tier 1: clinical review of design before build. | To do
SK-046 | E3 · Student app — home, search & care | Health vault (records) | Story | Mobile | RecordsVault | 2 · Student app (mobile) | 1 | P0 | 1 · Launch | 8 | All documents and reports, filterable, with upload and share. | • Upload photo/PDF • Every share shows who, what and until when, and can be revoked • Offline: cached list read-only | SK-040 | Your Care overview | Documents API, ABDM pull |  | To do
SK-047 | E3 · Student app — home, search & care | My lab tests and report insights | Story | Mobile | MyReports, ReportInsights | 2 · Student app (mobile) | 1 | P0 | 1 · Launch | 8 | Track lab bookings through collection to report, then a plain-language explanation of results. | • Status timeline per test • Out-of-range values amber with "talk to a doctor" link • No diagnosis language | SK-036 | Lab test results and booking | Lab orders + results |  | To do
SK-048 | E3 · Student app — home, search & care | Ayush chat (full screen) | Story | Mobile | AyushChat | 2 · Student app (mobile) | 1 | P1 | 2 · Launch month | 5 | Full-screen Ayush for longer conversations; same rules as the sheet. | • History can be cleared • Crisis words → crisis card • Clear label that Ayush is an assistant, not a doctor | SK-020 | Ayush chat component (web widget and phone sheet) |  |  | To do
SK-049 | E3 · Student app — home, search & care | Notifications inbox | Story | Mobile | Notifications | 2 · Student app (mobile) | 3 | P1 | 2 · Launch month | 3 | In-app list of updates with read/unread. | • Group by day • Tap opens the related screen • No health values in previews | SK-017 | Navigation: phone tab bar, web header, footer and role sidebars |  |  | To do
SK-050 | E4 · Student safety & privacy | Offline emergency card and emergency contacts | Story | Mobile | EmergencyCard, IceContacts | 2 · Student app (mobile) | 1 | P0 | 1 · Launch | 8 | An emergency card that works offline and from the lock screen, plus the contacts it lists. | • Blood group defaults to "Not set"; explicit "No known allergies" • +91 10-digit validation • Nothing on the card is sent anywhere | SK-026 | Create account, campus, care profile and permissions |  |  | To do |  |  | SKB-029
SK-051 | E4 · Student safety & privacy | Crisis support | Story | Mobile | CrisisSupport | 2 · Student app (mobile) | 1 | P0 | 1 · Launch | 5 | Always-reachable crisis screen: campus SOS, helplines, counsellor booking. | • Reachable without sign-in, verification or network • Campus never sees that it was opened • Telugu and Hindi reviewed | SK-021 | Languages: English, Telugu and Hindi |  | Never behind a login, gate, paywall or loading state. | To do
SK-052 | E4 · Student safety & privacy | SOS beacon and after-SOS | Story | Mobile | SosBeacon, SosDebrief | 2 · Student app (mobile) | 1 | P0 | 1 · Launch | 8 | Trigger SOS, share location with campus responders, then a debrief showing who was told. | • Hold-to-confirm with cancel window • Works on poor network (SMS fallback) • Debrief offers a counsellor call and a private note | SK-050 | Offline emergency card and emergency contacts | SOS event + responder notify |  | To do |  |  | SKB-026
SK-053 | E4 · Student safety & privacy | Consent inbox | Story | Mobile | ConsentInbox | 2 · Student app (mobile) | 1 | P0 | 1 · Launch | 5 | Requests from doctors, labs or campus to see records; approve, limit or decline. | • Each request shows who, what, until when • Revoke any time • Declined requests leave no trace for the requester beyond "declined" | SK-046 | Health vault (records) | ABDM consent manager |  | To do
SK-054 | E4 · Student safety & privacy | Care Circle | Story | Mobile | FamilyCircle | 2 · Student app (mobile) | 1 | P1 | 2 · Launch month | 5 | Share selected records with family members, each with a separate private record. | • Invite by phone • Per-person share scopes • Remove member instantly | SK-053 | Consent inbox |  |  | To do
SK-055 | E4 · Student safety & privacy | Download my data | Story | Mobile | DataExport | 2 · Student app (mobile) | 2 | P1 | 2 · Launch month | 3 | Export all records and account data. | • Choose scope and format • Link expires; sent only to the verified email | SK-046 | Health vault (records) | Export job |  | To do
SK-056 | E4 · Student safety & privacy | Hostel room visit | Story | Mobile | HostelVisit | 2 · Student app (mobile) | 2 | P2 | 3 · Later | 3 | Request a campus nurse or doctor visit to the hostel room. | • Time window and price shown • Status updates | SK-030 | Verification gate on services | Visit requests |  | To do
SK-057 | E4 · Student safety & privacy | Student check-in pass and handover receipt | Story | Mobile | MyPass, CheckinReceipt | 2 · Student app (mobile) | 1 | P0 | 1 · Launch | 8 | Rotating QR and 6-digit code for pharmacy, lab and clinic; history with "This wasn’t me"; receipt with bag photo after handover. | • QR and code rotate every 30 s, work offline • Screenshots fail (signed, time-bound) • Receipt links to report or return | SK-029 | Verify it’s you — four identity checks | Pass signing service |  | To do |  |  | SKB-018, SKB-023
SK-058 | E4 · Student safety & privacy | Leaving campus | Story | Mobile | LeaveCampus | 2 · Student app (mobile) | 2 | P1 | 2 · Launch month | 3 | Move to a personal account when leaving campus. | • Personal email required • Effective date by reason • Undo available | SK-069 | Account details |  |  | To do |  |  | SKB-015
SK-059 | E4 · Student safety & privacy | Delete my account | Story | Mobile | DeleteAccount | 2 · Student app (mobile) | 1 | P0 | 1 · Launch | 5 | Type DELETE and confirm with a phone code; 7 days to cancel; list what must legally be kept. | • 7-day cancel window • Erasure completed within 30 days after the window • "Having a hard time?" shows support | SK-069 | Account details | DPDP erasure request |  | To do |  |  | SKB-016
SK-060 | E4 · Student safety & privacy | Privacy notice, terms and grievance officer | Story | Mobile | Legal | 2 · Student app (mobile) | 1 | P0 | 1 · Launch | 3 | Legal pages and grievance form; every legal link in the app lands here. | • Grievance form returns a reference • 48 h acknowledgement, 30-day resolution stated |  |  |  | Real grievance officer details and legal review needed before launch. | To do |  |  | SKB-031
SK-061 | E4 · Student safety & privacy | Notification settings | Story | Mobile | NotificationSettings | 2 · Student app (mobile) | 2 | P1 | 2 · Launch month | 3 | Channels, categories, quiet hours and lock-screen privacy. | • Lock-screen privacy on by default • Safety alerts always on • Partner offers off by default | SK-011 | Checkbox, switch, radio and chips |  |  | To do |  |  | SKB-032
SK-062 | E5 · Student app — shop & orders | Shop home, product list and product detail | Story | Mobile | ShopHome, ProductList, ProductDetail | 2 · Student app (mobile) | 2 | P0 | 1 · Launch | 8 | Wellness shop with categories, dorm staples, product grid and detail. | • Prices and delivery shown before adding • "Nothing here is chosen from your health records" shown • Stock from the partner | SK-017 | Navigation: phone tab bar, web header, footer and role sidebars | Catalogue + stock | Rule L: no health data on commerce surfaces, no sponsored placement. | To do
SK-063 | E5 · Student app — shop & orders | Cart, checkout and payment | Story | Mobile | Cart, Checkout, Payment, PaymentResult, OrderSuccess | 2 · Student app (mobile) | 2 | P0 | 1 · Launch | 8 | Cart, delivery address (hostel block), payment (UPI, card) and result. | • Total incl. delivery shown before paying • Payment failed / pending states • Order placed moment (commerce only) | SK-062, SK-016 | Shop home, product list and product detail; Result moments (success, failure, pending) | Orders + payment gateway |  | To do
SK-064 | E5 · Student app — shop & orders | Order tracking and order history | Story | Mobile | OrderTracking, OrderHistory | 2 · Student app (mobile) | 2 | P0 | 1 · Launch | 5 | Live order status and past orders with reorder. | • Timeline with times • Handover with pass check shown • Offline shows last known status | SK-063 | Cart, checkout and payment | Order status |  | To do
SK-065 | E5 · Student app — shop & orders | Prescription upload | Story | Mobile | PrescriptionUpload | 2 · Student app (mobile) | 1 | P0 | 1 · Launch | 5 | Upload a prescription for Rx medicines; pharmacist reviews before dispatch. | • Photo or PDF • Status: in review / approved / needs a clearer copy • Rx items blocked until approved | SK-063 | Cart, checkout and payment | Rx upload + pharmacist review |  | To do
SK-066 | E5 · Student app — shop & orders | Returns and refunds | Story | Mobile | ReturnRequest, ResultRefund | 2 · Student app (mobile) | 2 | P1 | 2 · Launch month | 5 | Return an unopened item within 7 days and track the refund. | • Reason, photo, pickup from block • Refund started moment | SK-064 | Order tracking and order history | Returns + refunds |  | To do
SK-067 | E5 · Student app — shop & orders | Camp booking result | Story | Mobile | ResultCampBooked | 2 · Student app (mobile) | 2 | P1 | 2 · Launch month | 2 | Confirmation after booking a health camp slot. | • Slot, place, what to bring • Add to calendar | SK-016 | Result moments (success, failure, pending) |  |  | To do
SK-068 | E6 · Student app — account | More hub, profile and digital health ID | Story | Mobile | MoreHub, StudentProfile, DigitalId | 2 · Student app (mobile) | 2 | P0 | 1 · Launch | 5 | Account hub, profile card and the digital health ID with ABHA. | • Verified badge + 4 check chips • ABHA number masked • Log out confirm on every account screen | SK-017 | Navigation: phone tab bar, web header, footer and role sidebars |  |  | To do |  |  | SKB-010
SK-069 | E6 · Student app — account | Account details | Story | Mobile | AccountDetails | 2 · Student app (mobile) | 2 | P0 | 1 · Launch | 3 | Name, phone, email, campus, block; change with verification. | • Phone/email change needs a code • Verified status shown | SK-068 | More hub, profile and digital health ID |  |  | To do
SK-070 | E6 · Student app — account | Plan and billing | Story | Mobile | PlanBilling | 2 · Student app (mobile) | 2 | P1 | 2 · Launch month | 3 | Current plan, invoices, upgrade/cancel. | • Price from the single source • Cancel as easy as upgrade | SK-005 | One source of truth for the Student Plus price |  |  | To do
SK-071 | E6 · Student app — account | Cover and claims | Story | Mobile | ClaimsHub | 2 · Student app (mobile) | 2 | P2 | 3 · Later | 5 | Insurance cover and claim status. | • Claim timeline • Documents attached from the vault with consent | SK-046 | Health vault (records) | Claims API |  | To do
SK-072 | E6 · Student app — account | Help centre and my requests | Story | Mobile | HelpCentre, MyRequests | 2 · Student app (mobile) | 2 | P0 | 1 · Launch | 5 | Help articles, contact support, and a tracked list of every request. | • Every "support will call" promise creates a request with a timeline • Crisis link on help centre |  |  | Support tickets |  | To do |  |  | SKB-030
SK-073 | E7 · Public website | Landing — Discover | Story | Web | Landing | 3a · Student web — public site | 3 | P0 | 1 · Launch | 8 | Public home page for students: hero, what you can do, everyday wellness, lab checks, footer and newsletter. | • Responsive 320–1440 px • Videos lazy-load with a still poster and captions off by default • Lighthouse performance ≥ 80 | SK-017 | Navigation: phone tab bar, web header, footer and role sidebars | Public catalogue (read-only) |  | To do
SK-074 | E7 · Public website | Lab tests landing and category pages | Story | Web | WebLabTests, WebLabList | 3a · Student web — public site | 3 | P0 | 1 · Launch | 8 | Public lab test pages with packages and categories. | • Prices shown; booking requires sign-in • Structured data for tests (SEO) | SK-073 | Landing — Discover |  |  | To do
SK-075 | E7 · Public website | Consult a doctor page | Story | Web | WebConsult | 3a · Student web — public site | 3 | P0 | 1 · Launch | 5 | Public page explaining consults, pricing and NMC-registered doctors. | • Price from data • FAQ accordion accessible | SK-073 | Landing — Discover |  |  | To do
SK-076 | E7 · Public website | Care programmes and wellness training pages | Story | Web | WebPrograms, WebWellness | 3a · Student web — public site | 3 | P1 | 2 · Launch month | 8 | Programme and wellness pages with weekly schedules. | • Schedules from data • No body scores or before/after claims | SK-073 | Landing — Discover |  |  | To do
SK-077 | E7 · Public website | Plans page | Story | Web | WebPlans | 3a · Student web — public site | 3 | P0 | 1 · Launch | 5 | Basic free forever, Premium, Care Circle, Enterprise; comparison table. | • Prices from the single source • "Records never behind a paywall" message | SK-005 | One source of truth for the Student Plus price |  |  | To do
SK-078 | E7 · Public website | Landing pages for campuses, clinicians and partners | Story | Web | LandingCampus, LandingClinician, WebPartnerships | 3a · Student web — public site | 3 | P1 | 2 · Launch month | 8 | Three B2B landing pages that lead to the application forms. | • CTA to the right application • Rule L commitments stated for partners | SK-073 | Landing — Discover |  |  | To do
SK-079 | E8 · Student web — signed in | Web sign-in, sign-out, logged out and lost phone | Story | Web | WebSignIn, WebSignOut, WebLoggedOut, WebLostPhone | 3b · Student web — signed in, 1 · Launch & onboarding | 2 | P0 | 1 · Launch | 5 | Web versions of sign-in (phone + OTP or QR from the app), logged-out page and lost-phone flow. | • Same rules as phone • Session list visible afterwards | SK-025, SK-033 | Sign in with phone and OTP; Lost phone and moving to a new phone |  |  | To do
SK-080 | E8 · Student web — signed in | Web identity verification, gate and guardian consent | Story | Web | WebVerify, WebVerifyGate, WebGuardianConsent, WebGuardianApprove | 3b · Student web — signed in | 1 | P0 | 1 · Launch | 8 | Web layouts for the four identity checks, the service gate and under-18 guardian consent. | • Shares viewmodels with the phone tickets • Gate never blocks crisis, SOS, emergency card, help | SK-029, SK-031 | Verify it’s you — four identity checks; Under-18: ask a guardian and guardian approval |  |  | To do
SK-081 | E8 · Student web — signed in | Web home and care dashboard | Story | Web | WebHome, WebDashboard | 3b · Student web — signed in | 2 | P0 | 1 · Launch | 8 | Signed-in home and the care dashboard. | • First-time and offline states • Real data only | SK-040 | Your Care overview |  |  | To do
SK-082 | E8 · Student web — signed in | Web health vault | Story | Web | WebVault | 3b · Student web — signed in | 1 | P0 | 1 · Launch | 5 | Records list with upload, filters and sharing. | • Drag-and-drop upload • Share shows who, what, until when; revoke | SK-046 | Health vault (records) |  |  | To do
SK-083 | E8 · Student web — signed in | Web lab tests, report insights and report explainer | Story | Web | WebMyLabTests, WebReportInsights, WebReportAssistant | 3b · Student web — signed in | 1 | P0 | 1 · Launch | 8 | Track lab tests, read results and ask Ayush to explain a report. | • Out of range amber, never red • Explainer never diagnoses; links to a doctor | SK-047 | My lab tests and report insights |  |  | To do
SK-084 | E8 · Student web — signed in | Web Ayush | Story | Web | WebAyush | 3b · Student web — signed in | 1 | P1 | 2 · Launch month | 3 | Full-page Ayush on web. | • Same rules as the chat component | SK-020 | Ayush chat component (web widget and phone sheet) |  |  | To do
SK-085 | E8 · Student web — signed in | Web emergency card and check-in pass | Story | Web | WebEmergencyCard, WebPass | 3b · Student web — signed in | 1 | P0 | 1 · Launch | 5 | Edit the emergency card and show the check-in pass on a computer. | • Same validation as phone • Pass rotates every 30 s | SK-050, SK-057 | Offline emergency card and emergency contacts; Student check-in pass and handover receipt |  |  | To do
SK-086 | E8 · Student web — signed in | Web search, shop and product | Story | Web | WebSearchResults, WebShop, WebProduct | 3b · Student web — signed in | 2 | P0 | 1 · Launch | 8 | Search results, shop and product detail on web. | • Filters in a side panel • Rule L note on shop pages | SK-062 | Shop home, product list and product detail |  |  | To do
SK-087 | E8 · Student web — signed in | Web checkout, orders and buy again | Story | Web | WebCheckout, WebOrders, WebReorder | 3b · Student web — signed in | 2 | P0 | 1 · Launch | 8 | Checkout, order list and buy again with ratings. | • Total before paying • Ratings are about products and service, never about health | SK-063, SK-064 | Cart, checkout and payment; Order tracking and order history |  |  | To do
SK-088 | E8 · Student web — signed in | Web account, security and notifications | Story | Web | WebAccount, WebSecurity, WebNotifications | 3b · Student web — signed in | 2 | P0 | 1 · Launch | 8 | Account, sign-in and security (2FA, sessions) and notification settings. | • Sign out other sessions • Same notification rules as phone | SK-069, SK-061 | Account details; Notification settings |  |  | To do
SK-089 | E8 · Student web — signed in | Web requests, legal, leaving campus and delete account | Story | Web | WebRequests, WebLegal, WebLeaveCampus, WebDeleteAccount | 3b · Student web — signed in | 1 | P0 | 1 · Launch | 8 | Web versions of my requests, legal pages, leaving campus and delete account. | • Same rules as the phone tickets | SK-072, SK-060, SK-058, SK-059 | Help centre and my requests; Privacy notice, terms and grievance officer; Leaving campus; Delete my account |  |  | To do
SK-090 | E9 · Campus admin console | Campus console home and overview | Story | Web | CampusAdminConsole, CampusOverview | 4 · Campus / hostel admin | 3 | P0 | 1 · Launch | 5 | Landing page for campus admins with today’s numbers and shortcuts. | • Only aggregate, anonymous numbers (groups of 20+) • Loading/empty/error states | SK-017, SK-019 | Navigation: phone tab bar, web header, footer and role sidebars; Console data table |  | Campus never sees an individual’s health data. | To do
SK-091 | E9 · Campus admin console | Students roster, CSV import and verification queue | Story | Web | CampusRoster, CampusApprovals | 4 · Campus / hostel admin | 2 | P0 | 1 · Launch | 8 | Student list with enrolment status, CSV import of the roll list, and the college-ID verification queue. | • Four verification dots per student, never documents • CSV import validates and previews before saving | SK-019 | Console data table | Roster + verification queue |  | To do
SK-092 | E9 · Campus admin console | Health camps | Story | Web | CampusCamps | 4 · Campus / hostel admin | 2 | P1 | 2 · Launch month | 5 | Plan and run health camps with partners. | • Slots, partner, location • Bookings count only | SK-090 | Campus console home and overview |  |  | To do
SK-093 | E9 · Campus admin console | Health insights (aggregate) | Story | Web | CampusInsights | 4 · Campus / hostel admin | 1 | P1 | 2 · Launch month | 5 | Anonymous campus-level trends. | • Minimum group of 20; smaller groups hidden • Never mental or sexual health | SK-090 | Campus console home and overview |  |  | To do
SK-094 | E9 · Campus admin console | Access requests and emergency (break-glass) access | Story | Web | CampusAccessRequests, CampusBreakGlass | 4 · Campus / hostel admin | 1 | P0 | 1 · Launch | 8 | Staff request access to a student’s record; break-glass for emergencies with reason and audit. | • Break-glass needs reason + second person • Student is told afterwards • Every access logged | SK-090 | Campus console home and overview | Access requests + audit log |  | To do
SK-095 | E9 · Campus admin console | Incident desk and counsellor queue | Story | Web | CampusIncidents, CampusCounsellor | 4 · Campus / hostel admin | 1 | P0 | 1 · Launch | 8 | SOS and incident handling for campus responders; counsellor booking queue. | • SLA timers • Counsellor queue never visible to general admins | SK-052 | SOS beacon and after-SOS | Incidents + counselling bookings |  | To do
SK-096 | E9 · Campus admin console | Admin team and roles | Story | Web | CampusAdminTeam | 4 · Campus / hostel admin | 3 | P0 | 1 · Launch | 3 | Invite admins and assign roles. | • Removal signs out immediately • Role changes logged | SK-090 | Campus console home and overview |  |  | To do
SK-097 | E9 · Campus admin console | Isolation and discharge certificates | Story | Web | CampusIsolation, CampusDischarge | 4 · Campus / hostel admin | 1 | P1 | 2 · Launch month | 5 | Track students in isolation rooms and issue discharge/fitness certificates. | • Only what the student consented to share • Certificates signed by a clinician | SK-090 | Campus console home and overview |  |  | To do
SK-098 | E9 · Campus admin console | Outbreak, water and sanitary radars | Story | Web | CampusOutbreak, CampusWater, CampusSanitary | 4 · Campus / hostel admin | 2 | P2 | 3 · Later | 8 | Early-warning dashboards from aggregate symptom reports, water tests and sanitary audits. | • Aggregate only • Clear source and date on every number | SK-093 | Health insights (aggregate) |  |  | To do
SK-099 | E9 · Campus admin console | Mess and diet | Story | Web | CampusMess | 4 · Campus / hostel admin | 3 | P2 | 3 · Later | 3 | Special diet requests and mess hygiene checks. | • Diet requests without diagnosis details | SK-090 | Campus console home and overview |  |  | To do
SK-100 | E9 · Campus admin console | Ambulance dispatch and SLA escalation | Story | Web | CampusAmbulance, CampusSla | 4 · Campus / hostel admin | 1 | P1 | 2 · Launch month | 5 | Dispatch an ambulance and escalate when response targets are missed. | • Timers and escalation chain • Works with SOS incidents | SK-095 | Incident desk and counsellor queue |  |  | To do
SK-101 | E9 · Campus admin console | Hostel blocks | Story | Web | CampusBlocks | 4 · Campus / hostel admin | 3 | P1 | 2 · Launch month | 3 | Blocks, rooms and wardens for delivery and visits. | • CSV import • Used by delivery addresses | SK-090 | Campus console home and overview |  |  | To do
SK-102 | E9 · Campus admin console | Wellness workshops and announcements | Story | Web | CampusWellness, CampusAnnouncements | 4 · Campus / hostel admin | 3 | P2 | 3 · Later | 5 | Schedule workshops and send announcements. | • Announcements never target by health data | SK-090 | Campus console home and overview |  |  | To do
SK-103 | E9 · Campus admin console | Campus settings, certificate inbox and reports export | Story | Web | CampusSettings, CampusCertificates, CampusReports | 4 · Campus / hostel admin | 3 | P1 | 2 · Launch month | 5 | Campus requirements, medical certificates received from students, and report exports. | • Exports aggregate only • Certificates visible only as the student shared them | SK-090 | Campus console home and overview |  |  | To do
SK-104 | E9 · Campus admin console | Campus onboarding application | Story | Web | CampusApply | 4 · Campus / hostel admin | 3 | P1 | 2 · Launch month | 5 | Colleges apply: AISHE code, admins, health desk, roll list, plan, data agreement. | • Crisis support is non-negotiable in the plan • Status tracker after submitting |  |  | Tenant applications |  | To do |  |  | SKB-035
SK-105 | E10 · Doctor console | Doctor today, console and inbox | Story | Web | ClinicianToday, ClinicianConsole, ClinicianInbox | 5 · Doctor | 2 | P0 | 0 · Foundations | 8 | The doctor’s day: queue, messages and alerts in one inbox. | • Critical items first • Loading/empty/error states | SK-017, SK-019 | Navigation: phone tab bar, web header, footer and role sidebars; Console data table |  |  | To do
SK-106 | E10 · Doctor console | Consult room and encounter note | Story | Web | ClinicianConsultRoom, EncounterNote | 5 · Doctor | 1 | P0 | 0 · Foundations | 8 | Video consult with patient context and the structured encounter note. | • Only records the student shared • Note autosaves; signed on completion | SK-038 | Teleconsult call | Consult session + encounter |  | To do
SK-107 | E10 · Doctor console | Prescribe and renewals | Story | Web | Prescribe, ClinicianRenewals | 5 · Doctor | 1 | P0 | 0 · Foundations | 8 | E-prescription with allergy and interaction checks; renewal requests. | • NMC number and digital signature • Allergy warning blocks until acknowledged | SK-106 | Consult room and encounter note | Rx service |  | To do
SK-108 | E10 · Doctor console | Critical results and report reviews | Story | Web | ClinicalReview, ReportReviews | 5 · Doctor | 1 | P0 | 0 · Foundations | 5 | Review lab results that need a doctor, including critical values. | • Critical results page the doctor • Review recorded before release to student (where required) | SK-105 | Doctor today, console and inbox |  |  | To do
SK-109 | E10 · Doctor console | Lab orders and referrals | Story | Web | ClinicianLabOrder, ClinicianReferral | 5 · Doctor | 1 | P1 | 2 · Launch month | 5 | Order lab tests and refer to specialists. | • Price shown to the student before they accept | SK-106 | Consult room and encounter note |  |  | To do
SK-110 | E10 · Doctor console | Schedule and my patients | Story | Web | ClinicianSchedule, ClinicianPatients | 5 · Doctor | 2 | P0 | 0 · Foundations | 5 | Availability, slots and patient list (consented only). | • Slots feed student booking • Patient list shows only active consents | SK-105 | Doctor today, console and inbox |  |  | To do
SK-111 | E10 · Doctor console | Chronic care and AYUSH | Story | Web | ClinicianChronic, ClinicianAyush | 5 · Doctor | 1 | P2 | 3 · Later | 5 | Follow-up plans for long-term conditions and AYUSH practitioner views. | • Plans visible to the student | SK-110 | Schedule and my patients |  |  | To do
SK-112 | E10 · Doctor console | Decision support | Story | Web | ClinicianAi | 5 · Doctor | 1 | P2 | 3 · Later | 5 | Reference suggestions for the doctor. | • Clearly labelled as suggestions; doctor decides • Governed by AI governance settings | SK-132 | AI governance and knowledge base |  | Tier 1: clinical sign-off required. | To do
SK-113 | E10 · Doctor console | Earnings | Story | Web | ClinicianEarnings | 5 · Doctor | 3 | P1 | 2 · Launch month | 3 | Consult earnings and payouts. | • Matches the billing ledger | SK-142 | Billing ledger |  |  | To do
SK-114 | E10 · Doctor console | Doctor application | Story | Web + Mobile | ClinicianApply, WebClinicianApply | 5 · Doctor | 2 | P1 | 2 · Launch month | 5 | Doctors apply: NMC check, qualifications, consult set-up, clinical rules. | • NMC register check • Status tracker |  |  | Clinician applications |  | To do |  |  | SKB-034
SK-115 | E11 · Partner console & staff app | Partner home and console | Story | Web | VendorHome, VendorConsole | 6 · Partner — pharmacy, lab, clinic | 3 | P0 | 0 · Foundations | 5 | Home by provider type (pharmacy, lab, clinic) with today’s work. | • Loading/empty/error states | SK-017, SK-019 | Navigation: phone tab bar, web header, footer and role sidebars; Console data table |  |  | To do
SK-116 | E11 · Partner console & staff app | Orders, OTP handover and substitutions | Story | Web | VendorOrders, VendorHandover, VendorSubstitution | 6 · Partner — pharmacy, lab, clinic | 1 | P0 | 0 · Foundations | 8 | Accept, pack and hand over orders; propose substitutions for the student to approve. | • Handover needs pass check + bag photo (OTP alone not enough) • Substitution needs student approval | SK-123 | Staff app: verify student at the counter |  |  | To do |  |  | SKB-020
SK-117 | E11 · Partner console & staff app | Catalogue, stock and reorder rules | Story | Web | VendorCatalogue, VendorReorder | 6 · Partner — pharmacy, lab, clinic | 3 | P0 | 0 · Foundations | 5 | Products, prices and stock; reorder thresholds. | • Prices shown to students come from here • Bulk CSV update | SK-115 | Partner home and console | Catalogue + stock |  | To do
SK-118 | E11 · Partner console & staff app | Returns and settlement | Story | Web | VendorReturns, VendorSettlement | 6 · Partner — pharmacy, lab, clinic | 3 | P1 | 2 · Launch month | 5 | Handle returns and see earnings and settlement. | • Settlement matches the billing ledger | SK-116 | Orders, OTP handover and substitutions |  |  | To do
SK-119 | E11 · Partner console & staff app | Pharmacist Rx review and dispensing register | Story | Web | VendorRxReview, DispenseRegister | 6 · Partner — pharmacy, lab, clinic | 1 | P0 | 0 · Foundations | 8 | Pharmacist checks prescriptions before dispatch and keeps the dispensing register. | • Rx items held until approved • Register exportable for inspection | SK-065 | Prescription upload |  |  | To do
SK-120 | E11 · Partner console & staff app | Lab sample queue, run sheet and cold chain | Story | Web | LabQueue, LabCollection, LabColdChain | 6 · Partner — pharmacy, lab, clinic | 1 | P0 | 0 · Foundations | 8 | Collection runs, sample tracking and temperature log. | • Tube barcode linked to booking before collection • Cold-chain breach flags the sample | SK-124 | Staff app: hand over and collect sample |  |  | To do |  |  | SKB-021
SK-121 | E11 · Partner console & staff app | Release lab results | Story | Web | LabReporting | 6 · Partner — pharmacy, lab, clinic | 1 | P0 | 0 · Foundations | 5 | Enter/upload results and release them to the student. | • Critical values routed to a doctor first • Reference ranges from the lab | SK-120 | Lab sample queue, run sheet and cold chain | Results upload |  | To do
SK-122 | E11 · Partner console & staff app | Camp intake and camp day | Story | Web + Mobile | VendorCampIntake, CampDay | 6 · Partner — pharmacy, lab, clinic | 2 | P1 | 2 · Launch month | 5 | Partner side of health camps: intake list and the day-of view. | • Works offline with sync | SK-125 | Staff app: camp fast mode |  |  | To do |  |  | SKB-022
SK-123 | E11 · Partner console & staff app | Staff app: verify student at the counter | Story | Mobile + Web | ScanVerify, WebScanVerify | 6 · Partner — pharmacy, lab, clinic | 1 | P0 | 0 · Foundations | 8 | Scan the pass (or type the code), see the student, take a live photo, compare, confirm same/not same. | • Expired code and offline states • Photo match is a hint only; staff decide • Live photo deleted after 24 h unless disputed | SK-057 | Student check-in pass and handover receipt | Pass verify |  | To do |  |  | SKB-019
SK-124 | E11 · Partner console & staff app | Staff app: hand over and collect sample | Story | Mobile | StaffHandover, StaffCollect | 6 · Partner — pharmacy, lab, clinic | 1 | P0 | 0 · Foundations | 5 | Hand over with bag photo and counselling tick; collect with fasting confirm and tube scan. | • Hand over locked until bag photo + counselling tick • Rx only to the matched student | SK-123 | Staff app: verify student at the counter |  |  | To do |  |  | SKB-020, SKB-021
SK-125 | E11 · Partner console & staff app | Staff app: camp fast mode | Story | Mobile | StaffCampFast | 6 · Partner — pharmacy, lab, clinic | 2 | P1 | 2 · Launch month | 3 | High-volume check-in for camps. | • Counter, stop, manual, pending sync • Works offline | SK-123 | Staff app: verify student at the counter |  |  | To do |  |  | SKB-022
SK-126 | E11 · Partner console & staff app | Partner application | Story | Web + Mobile | PartnerApply, WebPartnerApply | 6 · Partner — pharmacy, lab, clinic | 2 | P1 | 2 · Launch month | 5 | Type, GSTIN, licences (register-checked), ₹1 penny drop, rules, tracker. | • Licences checked against registers • Status tracker |  |  | Partner applications |  | To do |  |  | SKB-033
SK-127 | E11 · Partner console & staff app | Partner staff and roles | Story | Web | PartnerStaff | 6 · Partner — pharmacy, lab, clinic | 2 | P1 | 2 · Launch month | 3 | Add staff and roles; roles decide who can hand over Rx. | • Removal signs out immediately | SK-126 | Partner application |  |  | To do |  |  | SKB-036
SK-128 | E12 · Super admin console | Staff and admin sign-in, console home | Story | Web | AdminSignIn, SuperAdminConsole | 7 · Super admin | 1 | P0 | 0 · Foundations | 5 | Separate staff sign-in with 2FA, then the super-admin home. | • No demo admin in production • 2FA required • Session timeout | SK-003, SK-017 | Turn demo mode off by default (no demo admin, no fixed OTP); Navigation: phone tab bar, web header, footer and role sidebars |  |  | To do
SK-129 | E12 · Super admin console | Accounts, roles and organisations | Story | Web | AdminAccounts, AdminTenants | 7 · Super admin | 2 | P0 | 0 · Foundations | 5 | Manage all accounts, roles and tenant organisations (campuses, partners). | • Role changes logged • Least privilege by default | SK-128, SK-019 | Staff and admin sign-in, console home; Console data table |  |  | To do
SK-130 | E12 · Super admin console | Audit explorer, break-glass log and check-in audit | Story | Web | AuditExplorer, AdminBreakGlassLog, AdminCheckins | 7 · Super admin | 1 | P0 | 0 · Foundations | 8 | Search every access and check-in event. | • Audit never shows face photos, purchases or ID numbers • 3 strikes in 7 days pauses a counter | SK-129 | Accounts, roles and organisations |  |  | To do |  |  | SKB-024
SK-131 | E12 · Super admin console | Support case detail ("This wasn’t me") | Story | Web | AdminCase | 7 · Super admin | 1 | P0 | 0 · Foundations | 5 | Case page for disputed check-ins and support requests. | • Closes only after a call is logged • Held photo deleted on close | SK-130 | Audit explorer, break-glass log and check-in audit |  |  | To do |  |  | SKB-024
SK-132 | E12 · Super admin console | AI governance and knowledge base | Story | Web | AiGovernance, AdminKnowledge | 7 · Super admin | 1 | P1 | 2 · Launch month | 5 | Rules and sources Ayush may use; review and versioning. | • Every source versioned and reviewed • Change log | SK-128 | Staff and admin sign-in, console home |  |  | To do
SK-133 | E12 · Super admin console | Catalogue ops, plans and pricing | Story | Web | CatalogOps, AdminPlansPricing | 7 · Super admin | 2 | P0 | 0 · Foundations | 5 | Central catalogue moderation and plan prices. | • Price change shows every surface it affects | SK-005 | One source of truth for the Student Plus price |  |  | To do
SK-134 | E12 · Super admin console | Integrations, API keys and token sync | Story | Web | Integrations, AdminApiKeys, AdminTokens | 7 · Super admin | 2 | P0 | 0 · Foundations | 5 | Third-party integrations, key rotation and design-token sync status. | • Keys masked; rotate button • Last-used time per key | SK-004 | Lock the APILayer proxy endpoints behind super-admin auth |  |  | To do
SK-135 | E12 · Super admin console | Erasure requests and consent policy | Story | Web | DpdpQueue, AdminConsentPolicy | 7 · Super admin | 1 | P0 | 0 · Foundations | 5 | DPDP erasure queue and consent policy versions. | • Erasure within 30 days, legally retained items listed • Consent version change forces re-consent | SK-059, SK-027 | Delete my account; Data-protection consent (DPDP) |  |  | To do
SK-136 | E12 · Super admin console | Clinician verification and partner applications | Story | Web | AdminVerification, AdminPartners | 7 · Super admin | 2 | P0 | 0 · Foundations | 5 | Approve doctors and partners after register checks. | • Reason required for rejection • Applicant notified | SK-114, SK-126 | Doctor application; Partner application |  |  | To do
SK-137 | E12 · Super admin console | Claims adjudication | Story | Web | ClaimsAdjudication | 7 · Super admin | 2 | P2 | 3 · Later | 5 | Review and decide claims. | • Only consented documents visible | SK-071 | Cover and claims |  |  | To do
SK-138 | E12 · Super admin console | Operations, SOS and casualty handover | Story | Web | AdminOps, AdminHandover | 7 · Super admin | 1 | P0 | 0 · Foundations | 8 | Live SOS and incident view across campuses; handover to hospitals. | • Real-time updates • Handover packet shares only emergency card data | SK-052 | SOS beacon and after-SOS |  |  | To do
SK-139 | E12 · Super admin console | Surveillance map and Rule L firewall | Story | Web | AdminSurveillance, AdminRuleL | 7 · Super admin | 1 | P1 | 2 · Launch month | 5 | Aggregate disease surveillance and the commerce firewall monitor. | • Aggregate only • Rule L violations listed with the surface | SK-129 | Accounts, roles and organisations |  |  | To do
SK-140 | E12 · Super admin console | Code sentinel and feature flags | Story | Web | AdminSentinel, AdminFlags | 7 · Super admin | 3 | P1 | 2 · Launch month | 5 | Code health checks and per-campus feature flags. | • Flag changes logged • Safety features cannot be turned off | SK-128 | Staff and admin sign-in, console home |  |  | To do
SK-141 | E12 · Super admin console | Message and notification templates | Story | Web | AdminTemplates, NotificationTemplates | 7 · Super admin, 8 · Design system & flow map | 1 | P1 | 2 · Launch month | 5 | WhatsApp, SMS and push templates with the copy rules. | • No result values, medicine names or diagnoses • Never ask for codes or passwords | SK-061 | Notification settings |  |  | To do |  |  | SKB-032
SK-142 | E12 · Super admin console | Billing ledger | Story | Web | AdminBilling | 7 · Super admin | 2 | P1 | 2 · Launch month | 5 | All payments, refunds and settlements. | • Reconciles with payment gateway • Export | SK-063 | Cart, checkout and payment |  |  | To do
SK-143 | E12 · Super admin console | Intake and OCR queue | Story | Web | AdminIntake | 7 · Super admin | 2 | P2 | 3 · Later | 5 | Review uploaded documents that OCR could not read confidently. | • Reviewer sees only what is needed • Student notified if a clearer copy is needed | SK-046 | Health vault (records) |  |  | To do
SK-144 | E13 · Quality & launch readiness | Accessibility pass on built screens | Task | Web + Mobile | All | — | 3 | P1 | 2 · Launch month | 5 | Audit every built screen: contrast, 44 px targets, labels, focus, dialogs, reduced motion. | • axe clean on every page • Screen reader walk-through of sign-in, booking, crisis |  |  |  |  | To do |  |  | SKB-040
SK-145 | E13 · Quality & launch readiness | First-time and offline states on student screens | Task | Web + Mobile | YourCare, RecordsVault, LabResults, OrderHistory, Appointments, Medications | 2 · Student app (mobile) | 3 | P1 | 2 · Launch month | 5 | Make sure every student screen has its first-time and offline states from the canvas. | • Offline banner + what still works • First-time steps | SK-015 | Empty, loading, error and offline states |  |  | To do |  |  | SKB-039
SK-146 | E13 · Quality & launch readiness | End-to-end tests for core flows | Task | Web + Mobile | — | — | 3 | P0 | 0 · Foundations | 8 | Automated tests: sign up → verify → book lab → pay → track; consult → Rx → order; SOS; delete account. | • Run in CI on every PR to main • Seeded test data only in test env |  |  |  |  | To do
SK-147 | E13 · Quality & launch readiness | Launch content and legal review | Task | Web + Mobile | Legal, WebLegal, OnboardingConsent, CrisisSupport | 2 · Student app (mobile), 3b · Student web — signed in, 1 · Launch & onboarding | 1 | P0 | 0 · Foundations | 3 | Real grievance officer details, legal review of consent and terms, clinical review of Tier 1 copy. | • Named reviewers signed off • Placeholders removed |  |  |  |  | To do

## Epics
Epic | Tickets | Points | P0 | P1 | P2 | Done | % done
E0 · Launch blockers | 6 | 16 | 6 | 0 | 0 | 0 | 0%
E1 · Design system foundations | 16 | 72 | 11 | 5 | 0 | 0 | 0%
E2 · Launch, sign-in & onboarding | 11 | 58 | 7 | 4 | 0 | 0 | 0%
E3 · Student app — home, search & care | 16 | 92 | 9 | 5 | 2 | 0 | 0%
E4 · Student safety & privacy | 12 | 59 | 7 | 4 | 1 | 0 | 0%
E5 · Student app — shop & orders | 6 | 33 | 4 | 2 | 0 | 0 | 0%
E6 · Student app — account | 5 | 21 | 3 | 1 | 1 | 0 | 0%
E7 · Public website | 6 | 42 | 4 | 2 | 0 | 0 | 0%
E8 · Student web — signed in | 11 | 74 | 10 | 1 | 0 | 0 | 0%
E9 · Campus admin console | 15 | 81 | 5 | 7 | 3 | 0 | 0%
E10 · Doctor console | 10 | 57 | 5 | 3 | 2 | 0 | 0%
E11 · Partner console & staff app | 13 | 73 | 8 | 5 | 0 | 0 | 0%
E12 · Super admin console | 16 | 86 | 9 | 5 | 2 | 0 | 0%
E13 · Quality & launch readiness | 4 | 21 | 2 | 2 | 0 | 0 | 0%
Total | 147 | 785 | 90 | 46 | 11 | 0 | 0%

## Screens
Canvas page | Screen | Title on canvas | Built in ticket(s)
1 · Launch & onboarding | WebSignOut |  | SK-079
1 · Launch & onboarding | Main | Splash — changes with the time of day (morning · afternoon · evening) | SK-023
1 · Launch & onboarding | SplashPulse | Splash variant — afternoon (heartbeat) | SK-023
1 · Launch & onboarding | SplashVault | Splash variant — evening (care circle) | SK-023
1 · Launch & onboarding | Onboarding1 | Onboarding 1 — Campus care | SK-024
1 · Launch & onboarding | Onboarding2 | Onboarding 2 — Health vault | SK-024
1 · Launch & onboarding | Onboarding3 | Onboarding 3 — Ayush AI | SK-024
1 · Launch & onboarding | SignIn | Sign in | SK-003, SK-010, SK-021, SK-025
1 · Launch & onboarding | OtpVerify | OTP verification | SK-003, SK-010, SK-025
1 · Launch & onboarding | CreateAccount | Create account — step 1 | SK-010, SK-026
1 · Launch & onboarding | CampusVerify | Campus verify — step 2 | SK-026
1 · Launch & onboarding | ProfileSetup | Care profile — step 3 | SK-026
1 · Launch & onboarding | Permissions | Permissions — step 4 | SK-011, SK-026
1 · Launch & onboarding | AccountReady | Workspace ready | SK-026
1 · Launch & onboarding | SignOut | Sign out | SK-032
1 · Launch & onboarding | AbhaLink | Link ABHA | SK-028
1 · Launch & onboarding | OnboardingConsent | Onboarding 4/5 — DPDP consent | SK-011, SK-021, SK-027, SK-147
1 · Launch & onboarding | VerifyIdentity | Verify it’s you — photo, email, college ID, government ID | SK-029
1 · Launch & onboarding | VerifyGate | Verification required (shown on any service) | SK-030
1 · Launch & onboarding | LoggedOut | Logged out (mobile) | SK-032
1 · Launch & onboarding | GuardianConsent | Under 18 — ask a guardian (student) | SK-031
1 · Launch & onboarding | GuardianApprove | Guardian’s approval page (SMS link) | SK-031
1 · Launch & onboarding | LostPhone | Lost your phone — from a friend’s phone | SK-033
1 · Launch & onboarding | NewDevice | New phone — move your account | SK-033
2 · Student app (mobile) | HomeDiscover | Home / Discover | SK-034
2 · Student app (mobile) | SearchEntry | Search entry | SK-035
2 · Student app (mobile) | SearchTyping | Typing & suggestions | SK-035
2 · Student app (mobile) | SearchLoading | Searching (skeletons) | SK-035
2 · Student app (mobile) | SearchResults | All results — tabbed | SK-035
2 · Student app (mobile) | NoResults | No results | SK-035
2 · Student app (mobile) | LabResults | Lab test results | SK-036, SK-145
2 · Student app (mobile) | DoctorResults | Doctor results | SK-037
2 · Student app (mobile) | Teleconsult | Teleconsult call | SK-038
2 · Student app (mobile) | Appointments | Appointments | SK-037, SK-145
2 · Student app (mobile) | YourCare | Your Care overview | SK-012, SK-040, SK-145
2 · Student app (mobile) | Medications | Medicines | SK-041, SK-145
2 · Student app (mobile) | PreventiveCare | Preventive care | SK-042
2 · Student app (mobile) | Devices | Devices & sensors | SK-002, SK-043
2 · Student app (mobile) | Movement | Movement | SK-044
2 · Student app (mobile) | RecordsVault | Health vault | SK-046, SK-145
2 · Student app (mobile) | AyushChat | Agent Ayush | SK-048
2 · Student app (mobile) | Notifications | Notifications | SK-049
2 · Student app (mobile) | EmergencyCard | Offline emergency card | SK-021, SK-050
2 · Student app (mobile) | CrisisSupport | Crisis support | SK-021, SK-051, SK-147
2 · Student app (mobile) | ShopHome | Shop — Home | SK-062
2 · Student app (mobile) | ProductList | Shop — Product grid | SK-062
2 · Student app (mobile) | ProductDetail | Shop — Product detail | SK-062
2 · Student app (mobile) | LabPackages | Shop — Lab packages | SK-036
2 · Student app (mobile) | Cart | Shop — Cart | SK-063
2 · Student app (mobile) | Checkout | Checkout — delivery | SK-063
2 · Student app (mobile) | Payment | Checkout — payment | SK-063
2 · Student app (mobile) | OrderSuccess | Order placed | SK-063
2 · Student app (mobile) | OrderTracking | Order tracking | SK-064
2 · Student app (mobile) | OrderHistory | Order history | SK-064, SK-145
2 · Student app (mobile) | PrescriptionUpload | Prescription upload | SK-065
2 · Student app (mobile) | MoreHub | More / account | SK-012, SK-068
2 · Student app (mobile) | StudentProfile | Student profile (flat + glass) | SK-068
2 · Student app (mobile) | DigitalId | Digital health ID | SK-068
2 · Student app (mobile) | PlanBilling | Plan & billing | SK-005, SK-070
2 · Student app (mobile) | ClaimsHub | Cover & claims | SK-071
2 · Student app (mobile) | HelpCentre | Help centre | SK-072
2 · Student app (mobile) | AccountDetails | Account details | SK-069
2 · Student app (mobile) | MyReports | My lab tests | SK-047
2 · Student app (mobile) | ReportInsights | Report insights | SK-047
2 · Student app (mobile) | ConsentInbox | Consent inbox | SK-053
2 · Student app (mobile) | SosBeacon | SOS beacon | SK-021, SK-052
2 · Student app (mobile) | DataExport | Download my data | SK-055
2 · Student app (mobile) | IceContacts | Emergency contacts | SK-050
2 · Student app (mobile) | FamilyCircle | Care Circle | SK-054
2 · Student app (mobile) | RefillRequest | Refill request | SK-041
2 · Student app (mobile) | VitalTrends | Vital trends | SK-045
2 · Student app (mobile) | HostelVisit | Hostel room visit | SK-056
2 · Student app (mobile) | ReturnRequest | Return or refund | SK-066
2 · Student app (mobile) | PaymentResult | Payment result (mobile) | SK-063
2 · Student app (mobile) | ResultLabBooked | Result — lab test booked | SK-036
2 · Student app (mobile) | ResultCampBooked | Result — camp booked | SK-067
2 · Student app (mobile) | ResultRefund | Result — return & refund | SK-066
2 · Student app (mobile) | MyPass | My check-in pass (QR + code) | SK-057
2 · Student app (mobile) | CheckinReceipt | Handover receipt (bag photo, how you were checked) | SK-057
2 · Student app (mobile) | LeaveCampus | Leaving campus — personal account | SK-058
2 · Student app (mobile) | DeleteAccount | Delete my account (7 days to cancel) | SK-059
2 · Student app (mobile) | NotificationSettings | Notification settings | SK-011, SK-061
2 · Student app (mobile) | ConsultSummary | Visit summary + e-prescription | SK-039
2 · Student app (mobile) | SosDebrief | After an SOS | SK-052
2 · Student app (mobile) | MyRequests | My requests | SK-072
2 · Student app (mobile) | Legal | Privacy, terms, grievance officer | SK-060, SK-147
3a · Student web — public site | Landing | Landing — Discover (live) | SK-017, SK-073
3a · Student web — public site | WebLabTests | Web — Lab tests landing | SK-074
3a · Student web — public site | WebLabList | Web — Lab test category | SK-074
3a · Student web — public site | WebConsult | Web — Consult a doctor | SK-075
3a · Student web — public site | WebPrograms | Web — Care programmes | SK-076
3a · Student web — public site | WebWellness | Web — Wellness training | SK-076
3a · Student web — public site | WebPlans | Web — Plans | SK-005, SK-077
3a · Student web — public site | LandingCampus | Landing — for campuses | SK-078
3a · Student web — public site | LandingClinician | Landing — for clinicians | SK-078
3a · Student web — public site | WebPartnerships | Web — Partnerships | SK-078
3b · Student web — signed in | WebSignIn | Web — Sign in | SK-021, SK-079
3b · Student web — signed in | WebLoggedOut | Web — logged out (confirmation + feedback) | SK-079
3b · Student web — signed in | WebLostPhone | Web — lost your phone | SK-079
3b · Student web — signed in | WebVerify | Web — Verify it’s you (photo, email, college ID, government ID) | SK-080
3b · Student web — signed in | WebVerifyGate | Web — verification required (shown on any service) | SK-080
3b · Student web — signed in | WebGuardianConsent | Web — under 18, ask a guardian | SK-080
3b · Student web — signed in | WebGuardianApprove | Web — guardian’s approval page | SK-080
3b · Student web — signed in | WebHome | Web — Home | SK-017, SK-081
3b · Student web — signed in | WebDashboard | Web — Care dashboard | SK-081
3b · Student web — signed in | WebVault | Web — Health vault | SK-082
3b · Student web — signed in | WebMyLabTests | Web — My lab tests | SK-083
3b · Student web — signed in | WebReportInsights | Web — Report insights | SK-083
3b · Student web — signed in | WebReportAssistant | Web — Ayush report explainer | SK-083
3b · Student web — signed in | WebAyush | Web — Ayush | SK-084
3b · Student web — signed in | WebConsultSummary | Web — visit summary | SK-039
3b · Student web — signed in | WebEmergencyCard | Web — emergency card editor | SK-085
3b · Student web — signed in | WebPass | Web — my check-in pass | SK-085
3b · Student web — signed in | WebSearchResults | Web — Search results | SK-086
3b · Student web — signed in | WebShop | Web — Shop | SK-086
3b · Student web — signed in | WebProduct | Web — Product | SK-086
3b · Student web — signed in | WebCheckout | Web — Checkout | SK-087
3b · Student web — signed in | WebOrders | Web — My orders | SK-087
3b · Student web — signed in | WebReorder | Web — Buy again & ratings | SK-087
3b · Student web — signed in | WebAccount | Web — Account | SK-088
3b · Student web — signed in | WebSecurity | Web — sign-in & security (2FA, sessions) | SK-088
3b · Student web — signed in | WebNotifications | Web — notifications | SK-088
3b · Student web — signed in | WebRequests | Web — my requests | SK-089
3b · Student web — signed in | WebLegal | Web — privacy, terms, grievance | SK-089, SK-147
3b · Student web — signed in | WebLeaveCampus | Web — leaving campus | SK-089
3b · Student web — signed in | WebDeleteAccount | Web — delete my account | SK-089
4 · Campus / hostel admin | CampusAdminConsole | Campus admin console | SK-017, SK-090
4 · Campus / hostel admin | CampusCamps | Campus — health camps | SK-092
4 · Campus / hostel admin | CampusApprovals | Campus — verification queue | SK-091
4 · Campus / hostel admin | CampusOverview | Campus — overview | SK-090
4 · Campus / hostel admin | CampusRoster | Campus — students & CSV import | SK-019, SK-091
4 · Campus / hostel admin | CampusInsights | Campus — health insights | SK-093
4 · Campus / hostel admin | CampusAccessRequests | Campus — access requests | SK-094
4 · Campus / hostel admin | CampusBreakGlass | Campus — emergency access (break-glass) | SK-094
4 · Campus / hostel admin | CampusIncidents | Campus — incident desk | SK-095
4 · Campus / hostel admin | CampusCounsellor | Campus — counsellor queue | SK-095
4 · Campus / hostel admin | CampusAdminTeam | Campus — admin team & roles | SK-096
4 · Campus / hostel admin | CampusIsolation | Campus — isolation | SK-097
4 · Campus / hostel admin | CampusOutbreak | Campus — outbreak radar | SK-098
4 · Campus / hostel admin | CampusWater | Campus — water radar | SK-098
4 · Campus / hostel admin | CampusSanitary | Campus — sanitary audit | SK-098
4 · Campus / hostel admin | CampusMess | Campus — mess & diet | SK-099
4 · Campus / hostel admin | CampusAmbulance | Campus — ambulance dispatch | SK-100
4 · Campus / hostel admin | CampusSla | Campus — SLA escalation | SK-100
4 · Campus / hostel admin | CampusBlocks | Campus — hostel blocks | SK-101
4 · Campus / hostel admin | CampusDischarge | Campus — discharge certificates | SK-097
4 · Campus / hostel admin | CampusWellness | Campus — wellness workshops | SK-102
4 · Campus / hostel admin | CampusSettings | Campus — settings & requirements | SK-103
4 · Campus / hostel admin | CampusCertificates | Campus — certificate inbox | SK-103
4 · Campus / hostel admin | CampusAnnouncements | Campus — announcements | SK-102
4 · Campus / hostel admin | CampusReports | Campus — reports export | SK-103
4 · Campus / hostel admin | CampusApply | Campus onboarding | SK-104
5 · Doctor | ClinicianConsole | Clinician console | SK-017, SK-105
5 · Doctor | ClinicalReview | Clinician — critical results | SK-108
5 · Doctor | EncounterNote | Clinician — encounter note | SK-106
5 · Doctor | Prescribe | Clinician — prescribe | SK-107
5 · Doctor | ReportReviews | Clinician — report reviews | SK-108
5 · Doctor | ClinicianSchedule | Clinician — schedule | SK-110
5 · Doctor | ClinicianPatients | Clinician — my patients | SK-110
5 · Doctor | ClinicianEarnings | Clinician — earnings | SK-113
5 · Doctor | ClinicianLabOrder | Clinician — lab orders | SK-109
5 · Doctor | ClinicianReferral | Clinician — referrals | SK-109
5 · Doctor | ClinicianRenewals | Clinician — renewals | SK-107
5 · Doctor | ClinicianChronic | Clinician — chronic care | SK-111
5 · Doctor | ClinicianAyush | Clinician — AYUSH | SK-111
5 · Doctor | ClinicianAi | Clinician — decision support | SK-112
5 · Doctor | ClinicianToday | Clinician — today | SK-105
5 · Doctor | ClinicianInbox | Clinician — unified inbox | SK-105
5 · Doctor | ClinicianConsultRoom | Clinician — consult room | SK-106
5 · Doctor | WebClinicianApply | Doctor application — web | SK-114
5 · Doctor | ClinicianApply | Doctor application — phone | SK-114
6 · Partner — pharmacy, lab, clinic | CampDay | Camp day | SK-122
6 · Partner — pharmacy, lab, clinic | LabQueue | Lab — sample queue | SK-019, SK-120
6 · Partner — pharmacy, lab, clinic | DispenseRegister | Pharmacy — dispensing register | SK-119
6 · Partner — pharmacy, lab, clinic | VendorConsole | Vendor console | SK-017, SK-115
6 · Partner — pharmacy, lab, clinic | VendorSettlement | Vendor — earnings & settlement | SK-118
6 · Partner — pharmacy, lab, clinic | VendorOrders | Partner — orders | SK-116
6 · Partner — pharmacy, lab, clinic | VendorCatalogue | Partner — catalogue & stock | SK-117
6 · Partner — pharmacy, lab, clinic | LabCollection | Lab — run sheet | SK-120
6 · Partner — pharmacy, lab, clinic | LabColdChain | Lab — cold chain | SK-120
6 · Partner — pharmacy, lab, clinic | LabReporting | Lab — release results | SK-121
6 · Partner — pharmacy, lab, clinic | VendorReturns | Partner — returns | SK-118
6 · Partner — pharmacy, lab, clinic | VendorHandover | Partner — OTP handover | SK-116
6 · Partner — pharmacy, lab, clinic | VendorSubstitution | Partner — substitutions | SK-116
6 · Partner — pharmacy, lab, clinic | VendorReorder | Partner — reorder rules | SK-117
6 · Partner — pharmacy, lab, clinic | VendorCampIntake | Partner — camp intake | SK-122
6 · Partner — pharmacy, lab, clinic | VendorHome | Partner — home by provider type | SK-115
6 · Partner — pharmacy, lab, clinic | VendorRxReview | Partner — pharmacist Rx review | SK-119
6 · Partner — pharmacy, lab, clinic | ScanVerify | Staff app — verify student (scan, photo match) | SK-123
6 · Partner — pharmacy, lab, clinic | WebScanVerify | Counter / reception — verify student | SK-123
6 · Partner — pharmacy, lab, clinic | StaffHandover | Staff app — hand over (bag photo) | SK-124
6 · Partner — pharmacy, lab, clinic | StaffCollect | Staff app — collect sample (tube scan) | SK-124
6 · Partner — pharmacy, lab, clinic | StaffCampFast | Staff app — camp fast mode | SK-125
6 · Partner — pharmacy, lab, clinic | PartnerApply | Partner application — phone | SK-126
6 · Partner — pharmacy, lab, clinic | WebPartnerApply | Partner application — web | SK-126
6 · Partner — pharmacy, lab, clinic | PartnerStaff | Partner — staff & roles | SK-127
7 · Super admin | SuperAdminConsole | Super admin console | SK-017, SK-128
7 · Super admin | AdminAccounts | Super admin — accounts & roles | SK-019, SK-129
7 · Super admin | AuditExplorer | Super admin — audit explorer | SK-019, SK-130
7 · Super admin | AiGovernance | Super admin — AI governance | SK-132
7 · Super admin | CatalogOps | Super admin — catalogue ops | SK-133
7 · Super admin | Integrations | Super admin — integrations & index | SK-004, SK-134
7 · Super admin | DpdpQueue | Super admin — erasure requests | SK-135
7 · Super admin | ClaimsAdjudication | Claims adjudication (M22–M25) | SK-137
7 · Super admin | AdminVerification | Super admin — clinician verification | SK-136
7 · Super admin | AdminPartners | Super admin — partner applications | SK-136
7 · Super admin | AdminOps | Super admin — operations & SOS | SK-138
7 · Super admin | AdminSurveillance | Super admin — surveillance map | SK-139
7 · Super admin | AdminTenants | Super admin — organisations | SK-129
7 · Super admin | AdminRuleL | Super admin — Rule L firewall | SK-139
7 · Super admin | AdminConsentPolicy | Super admin — consent policy | SK-135
7 · Super admin | AdminHandover | Super admin — casualty handover | SK-138
7 · Super admin | AdminSentinel | Super admin — code sentinel | SK-140
7 · Super admin | AdminTokens | Super admin — token sync | SK-134
7 · Super admin | AdminBreakGlassLog | Super admin — break-glass log | SK-130
7 · Super admin | AdminPlansPricing | Super admin — plans & pricing | SK-005, SK-133
7 · Super admin | AdminFlags | Super admin — feature flags per campus | SK-140
7 · Super admin | AdminTemplates | Super admin — WhatsApp & message templates | SK-141
7 · Super admin | AdminBilling | Super admin — billing ledger | SK-142
7 · Super admin | AdminKnowledge | Super admin — Ayush knowledge base | SK-132
7 · Super admin | AdminIntake | Super admin — intake & OCR queue | SK-143
7 · Super admin | AdminCheckins | Super admin — check-in audit | SK-130
7 · Super admin | AdminCase | Super admin — case detail (“This wasn’t me”) | SK-131
7 · Super admin | AdminPriceFix | Fix the Premium price (SK-006) | SK-005
7 · Super admin | AdminApiKeys | API access & keys (SK-005) | SK-004, SK-134
7 · Super admin | AdminSignIn | Staff & admin sign-in (SK-004) | SK-003, SK-128
8 · Design system & flow map | FlowMap | Flow map — whole application | SK-022
8 · Design system & flow map | Sheets | System — bottom sheets | SK-014
8 · Design system & flow map | NavSheets | System — navigation & sheets | SK-014, SK-017
8 · Design system & flow map | StateScreens | System — full-screen states | SK-015
8 · Design system & flow map | AyushWidget | Ayush — chat widget (web, shared) | SK-020
8 · Design system & flow map | AyushSheet | Ayush — phone bottom sheet (Discover, Your Care) | SK-020
8 · Design system & flow map | MotionSystem | Motion & interaction system | SK-007, SK-018
8 · Design system & flow map | IconSystem | Design system — icons (3D + flat, animated) | SK-007, SK-018
8 · Design system & flow map | IllustrationLibrary | Design system — illustration library | SK-018
8 · Design system & flow map | StatusMoments | Design system — result moments (success, failure, pending) | SK-016
8 · Design system & flow map | ConfirmDialogs | Design system — confirm dialogs (log out, cancel, revoke) | SK-014
8 · Design system & flow map | NotificationTemplates | Notification templates (copy + rules) | SK-141
8 · Design system & flow map | Feedback | System — feedback (toasts, banners, validation) | SK-010, SK-012, SK-013